## alltasks 22012020
Workstream | Task/Milestone | Task owner | Required completion date | Planned start date | Actual start date | Status | Comments
Procurement | Confirm Office supply route | Sarah Hadland | 2020-02-28 | 2020-02-01 | 2020-01-23 | Completed | confirm with ICT and procurement suppliers for office supplys Draw off staples contract
HR | Determine pension scheme type | Kevin O'Leary |  |  |  | Completed | 28/11/2019: Option to adopt the Government 'Nest' (National Employment Savings Trust) scheme for Amey staff & new recruits who were never part of the previous Ealing TUPE transfer group. Decided June 2019.
HR | Agree contribution levels | Kevin O'Leary | 2019-11-28 |  |  | Completed | 28/11/2019: 5% minimum contribution level was agreed.
HR | Decide main contact for Nest/ other scheme who makes decisions about the scheme | Kevin O'Leary | 2019-11-28 |  |  | Completed | 28/11/2019: it has been agreed that the GEL MD and the Company Board will hold this decision making authority.
HR | Names of delegates / internal and external (Finance, Payroll provider) | Lara Balogun/ Chris Neale |  |  |  | Completed
HR | Specify pay period/frequency | Lara Balogun | 2020-12-20 |  |  | Completed | Monthly - 26th of each month or nearest working day i.e. if 26th falls on Saturday will pay on Friday.
HR | Develop JDs and person specs | Sharon Brown/ Gel Mgmt team/KO'L | 2020-02-28 |  |  | Completed | 16/12 Hays Recruitment Agency commissioned to recruit to HR and Finance roles
H&S | Recruitment of a health and safety consultant to deliver workplan | John Arnold and Somayya Yaqub | 2020-01-27 | 2020-01-06 |  | Completed
H&S | Secure requisite approval and funding | John Arnold | 2020-01-07 | 2020-01-06 |  | Completed
H&S | Appoint candidate to start W/C 27/01/2020 | Health and safety consultant | 2020-01-27 | 2020-01-14 |  | Completed | 23/01/2020 (KRD): H&S consultant met with on 21/01/2020, to begin conducitng gap analsysis. After which, project plan can be created
Finance | Finalise budget allocation per service | Chris Neale | 2020-01-31 | 2019-12-02 | 2019-12-02 | Completed | 9/1/2020 Completed, though pre any refinement by service or further change re LLW. Chris to share file (copy viewable without links) cWed 15/1/2020. JA 04/12/2019 -JA & CNe met 02/12/2019 and split remaining costs, Chris now to input to complete by mid Jan
Finance | Sort out if tax advisor required | Chris Neale / Simon Peet | 2020-01-06 | 2020-02-01 | 2020-01-06 | Completed | 9/1/2020 Chris contacted PwC outlining main points on which may seek advice. 6/1/2020 Chris got info from Simon Peet re PwC tax advisor.
ICT | Send payroll info to HR |  | 2019-11-08 | 2019-11-08 |  | Completed
ICT | Design |  | 2019-12-30 | 2019-12-19 |  | Completed
ICT | System set up |  | 2020-01-14 | 2020-01-01 |  | Completed
ICT | Initiation |  | 2020-11-14 | 2019-09-25 |  | Completed
ICT | ICT technical standards and FOI |  | 2019-11-18 | 2019-11-07 |  | Completed
ICT | Gcloud ICT requirements and plan |  | 2019-11-28 | 2019-10-22 |  | Completed
ICT | Procurement elements |  | 2019-11-28 | 2019-10-22 |  | Completed
ICT | Prepare LLPG data |  | 2019-10-31 | 2019-10-14 |  | Completed
ICT | Prepare FTP |  | 2019-11-08 | 2019-10-14 |  | Completed
ICT | FTP LLPG data to WS |  | 2019-11-12 | 2019-11-11 |  | Completed
ICT | Whitespace data gather |  | 2019-11-28 | 2019-11-13 |  | Completed
ICT | COU process in place |  | 2019-11-29 | 2019-11-29 |  | Completed
ICT | Whitespace configuration |  | 2019-01-02 | 2019-11-29 |  | Completed
ICT | Whitespace mobile configuration |  | 2019-11-27 | 2019-11-25 |  | Completed
ICT | Whitespace workshop |  | 2019-12-06 | 2019-12-06 |  | Completed
ICT | Requirement - initial meet with Contender |  | 2019-11-04 | 2019-11-04 |  | Completed
ICT | Receive quote from Contender |  | 2019-11-11 | 2019-11-05 |  | Completed
ICT | Confirm Contender quote as acceptable |  | 2019-11-25 | 2019-11-12 |  | Completed
ICT | Generate PO and send to Contender |  | 2019-11-28 | 2019-11-26 |  | Completed
ICT | Contender integration specification |  | 2019-11-29 | 2019-11-29 |  | Completed
ICT | Requirements |  | 2019-10-01 | 2019-10-01 |  | Completed
ICT | Domain names |  | 2019-10-07 | 2019-10-01 |  | Completed
ICT | Site surveys |  | 2019-10-22 | 2019-10-22 |  | Completed
Legal | Shareholder representative appointment | Helen Harris | 10.01.20 |  |  | Completed | 09/12/2019: Gary Alderson appointed at October 2019 Cabinet
Legal | Company secretarial services | Kevin O'Leary | 2020-01-03 |  |  | Completed
Legal | Broadway Living to be approached | Kevin O'Leary | 24.12.2019 |  |  | Completed | Maxine Sawford to set bridgehouse up as a supplier for GEL to use.
Legal | Provision of company secretarial services to GEL | Kevin O'Leary | 2020-01-03 |  |  | Completed | 09/12/2019: KL to speak to BL - Phillip Brown on secretarial services pending
ICT (Depot) | Mobilize on site |  | Thu 02/01/20 | Thu 02/01/20 |  | Completed
ICT (Depot) | Sheet up Plant Room |  | Thu 02/01/20 | Thu 02/01/20 |  | Completed
ICT (Depot) | Scaffold in Plant Room |  | Thu 02/01/20 | Thu 02/01/20 |  | Completed
ICT (Depot) | Encapsulate Plant Room |  | Fri 03/01/20 | Fri 03/01/20 |  | Completed
ICT (Depot) | Air Test Plant Room |  | Sun 05/01/20 | Fri 03/01/20 |  | Completed
ICT (Depot) | Scaffolding |  | Tue 07/01/20 | Fri 03/01/20 |  | Completed
ICT (Depot) | Sheeting up |  | Thu 09/01/20 | Mon 06/01/20 |  | Completed
ICT | MTD - VAT Tax codes into iTrent |  | 2019-12-31 | 2019-12-31 |  | Delayed: not started | 14/01/2020 (KRD): change control possibly required according to Shahzad
ICT | Order and receive BT lines |  | 2020-02-03 | 2019-12-17 |  | Delayed: not started | 20/01/2020 (KRD): ordered but not yet received
ICT | Build hardware of site |  | 2020-02-24 | 2020-01-21 |  | Delayed: not started
ICT | Business applications support |  | 2020-07-09 | 2019-12-17 |  | Delayed: not started | 14/01/2020 (KRD): due to start on 20/01/2020 (change from 17/12/2020) 21/01/2020 (KRD): start date changed to 06/07/2020 (changed from 20/01/2020)
ICT | Business world support |  | 2020-07-09 | 2019-12-17 |  | Delayed: not started | 14/01/2020 (KRD): due to start on 20/01/2020 (change from 17/12/2020) 21/01/2020 (KRD): start date changed to 06/07/2020 (changed from 20/01/2020)
ICT | Hardware support |  | 2020-04-23 | 2019-12-17 |  | Delayed: not started | 14/01/2020 (KRD): due to start on 30/01/2020 (change from 17/12/2020) 21/01/2020 (KRD): start date changed to 24/02/2020 from 30/01/2020
ICT | HOTS sign-off |  | 2020-06-25 | 2019-12-17 |  | Delayed: not started
Procurement | Confirmation of Fleet Delivery time line | John Arnold/Sarah Hadland | 2020-02-28 | 2020-01-09 | 2019-12-19 | in progress | May be a delay with certain vehicles, however, the contingency is to use manufacturers demo vehicles and/or have an arrangement with Hitachi or TPPL/GoPlant can provide short term hire (minimum 2 months). Meeting end of January; if not comfortable with position - approach hire vehicle companies and/or potentially novate Amey rubbish vehicles.
Procurement | Award Maintenance contract once Tender has finished | John Arnold/Sarah Hadland/ Kevin O'Leary/ Vincent Hunt/ Chuhr Nijjar | 2020-03-31 | 2019-11-01 | 2019-11-01 | in progress | Tender has been issued and is due back 17/02.
Procurement | Award Bunkered Fuel Contract | John Arnold/Sarah Hadland | 2020-02-28 | 2020-01-06 | 2020-01-06 | in progress | Mini-competition for bunker fuel has been issued via the LASER Fuel framework w/c 06/01; for return on 20/01. Fuel card requirements need to be confirmed to Commercial Hub. Comp needs to be re run to provide correct fuel type for Acton.
Procurement | Finish Spec for Occupational Health Contract | John Arnold/Sarah Hadland | 2020-01-31 | 2020-01-06 | 2019-12-06 | in progress | Currently in final stages there are a couple of things to address such as Ill health retirement
Procurement | Confirm Jewson can supply required tools | John Arnold/Sarah Hadland | 2020-02-28 | 2020-01-31 | 2020-01-10 | in progress | Tool list created and ready to be sent to Jewson Sarah has meeting Friday 24.01.20 to confirm rates etc.
Procurement | Place final order for small plant with supplier | John Arnold/Sarah Hadland/ Chirs Welsh | 2020-03-31 | 2020-03-01 | 2020-01-10 | in progress | List has been created, they have offered a demo before placing order which we will be taking advantage of.
Procurement | finalise P.P.E list | John Arnold/Sarah Hadland | 2020-01-31 | 2020-01-06 | 2019-12-06 | in progress | Amey have supplied PPE information we are waiting for size confirmation before committing to volumes etc. to attach as part of the Tender
Procurement | Agency contract award | John Arnold/Sarah Hadland | 2020-02-29 | 2020-01-06 | 2019-12-06 | in progress | Meeting arranged with Pertemps in January 2020 to gather info on current staffing requirements. Potential risk of challenge re: using MSTAR Framework due to LATCOs not being named as permissible users - way forward on this has been agreed by GA. Sarah will review the pricing etc. 24.01.20
Procurement | finalise H&S system contract (Alcumus) | John Arnold/Sarah Hadland/ Chuhr Nijjar | 2020-01-31 | 2020-01-06 | 2019-12-06 | in progress | Legal have reviewed the Alcumus contract. Comments/proposed amendments have been sent back to IEX (supplier). Have received the revised contract back need to review with Chuhr
Procurement | Finalise Financing Company | John Arnold/Sarah Hadland | 2020-02-29 | 2020-01-06 | 2019-12-06 | in progress | List has been finalised by John. The competition for electric vehicles can start January 2020 via Link.
HR | Arrange employers Liability insurance | Ewan re Ins/ Chris | 2020-04-01 | 2019-10-01 | 2019-10-01 | in progress | 1/12 Being done by April 2020 by Ewan as part of new Insurance contract for council
HR | Arrange scheme - require PAYE and bank account | Chris re bank / Payroll re PAYE then |  | 2019-10-01 | 2019-10-01 | in progress | 14/1/2020 expect bank account this week, and SUN for payroll the following, as all details provided to bank. Do not need PAYE registration to start till 6wks before start paying PAYE. 6/1/20 Chris requested Simon to get updated Director Alison Reynolds, to bank, as they requested. 1/12/19 started getting bank account hoping earliest in Dec
HR | Request early version of all Employee Liability Information documents | Sharon Brown |  | 2020-02-28 | 2019-12-16 | in progress | 28/11/2019: When will the employer liability information be received as per the exit agreement? Will it include ID checks and driver information?
HR | Review GEL's company structure and reporting lines | Sharon Brown | 2020-02-28 |  |  | in progress
HR | Develop recruitment process for posts | Sharon Brown | 2020-02-28 |  |  | in progress | 16/12 Interim Director already in place, Council Director to make decision about this pending Board being set up
HR | Develop pay, benefits, and T&Cs for each post | Sharon Brown/ Gel Mgmt team/KO'L | 2020-02-28 |  |  | in progress | Using ACAS T&C's for new posts
HR | Develop a specimen contract of employment | Sharon Brown | 2020-02-28 |  |  | in progress | Using ACAS T&C's for new posts
HR | Work with Procurement to ensure an agency supplier is in place for temp staff | HR/John Arnold | 2020-02-28 | 2020-01-16 | 2020-01-16 | in progress | Pertemps identified by Mstar framework. John and Sarah in discussions with them and all on target. Pertemps currently providing Hillingdon so will replica.
HR | Review existing AMEY policies and procedures, amending to fit GEL (NEW STARTERS) | HR/KO'L | 28/2/20 | 2020-06-01 |  | in progress
HR | Redundancy benefits policy | GEL HR Manager |  | 2019-07-01 |  | in progress | 16/12 Need to discuss the policy element in more detail, decide what we want the policies to look like i.e. use ACAS. John & SB reviewing current drafts
HR | Job evaluation procedure | GEL HR Manager |  | 2019-07-01 |  | in progress
HR | Pay policy (base pay; overtime; bonuses; shift and other allowances) | GEL HR Manager |  | 2019-07-01 |  | in progress
HR | Performance management | GEL HR Manager |  | 2019-07-01 |  | in progress
HR | Sickness absence | GEL HR Manager |  | 2019-07-01 |  | in progress
HR | Holiday policy and booking process | GEL HR Manager |  | 2019-07-01 |  | in progress
HR | Overtime recording process | GEL HR Manager |  | 2019-07-01 |  | in progress
HR | Signing in, signing out procedure | GEL HR Manager |  | 2019-07-01 |  | in progress
HR | Other absences (paid; unpaid; procedure; entitlement) | GEL HR Manager |  | 2019-07-01 |  | in progress
HR | Sick pay policy | GEL HR Manager |  | 2019-07-01 |  | in progress
HR | Maternity/paternity/adoption/parental leave | GEL HR Manager |  | 2019-07-01 |  | in progress
HR | Working Time Regulations/limits/opting out policy | GEL HR Manager |  | 2019-07-01 |  | in progress
HR | Working week/working patterns/rest breaks/toil/overtime | GEL HR Manager |  | 2019-07-01 |  | in progress
HR | Disciplinary procedure | GEL HR Manager |  | 2019-07-01 |  | in progress
HR | Grievance procedure | GEL HR Manager |  | 2019-07-01 |  | in progress
HR | Equal opportunities | GEL HR Manager |  | 2019-07-01 |  | in progress
HR | Health and safety | GEL HR Manager |  | 2019-07-01 |  | in progress
HR | Smoking at work | GEL HR Manager |  | 2019-07-01 |  | in progress
HR | Harassment policy | GEL HR Manager |  | 2019-07-01 |  | in progress
HR | Personal records and data protection | GEL HR Manager |  | 2019-07-01 |  | in progress
HR | Handling organisational change policy | GEL HR Manager |  | 2019-07-01 |  | in progress
HR | References policy | GEL HR Manager |  | 2019-07-01 |  | in progress
HR | Handbook (reference to Modern Slavery Act 2015 Regs/Anti corruption policy/Bribery Act 2010). Company property (care, reporting damage, returning, storing, handover, keep it safe) | GEL HR Manager |  | 2019-07-01 |  | in progress
HR | Email/internet policy | GEL HR Manager |  | 2019-07-01 |  | in progress
HR | Mobile phone policy | GEL HR Manager |  | 2019-07-01 |  | in progress
HR | Expenses policy | GEL HR Manager |  | 2019-07-01 |  | in progress
HR | Review scope and content of any Amey recognition/ collective agreements | Sharon Brown/Amey HR | 2019-07-29 | 2019-07-01 | 28/11/20 | in progress | 1/12 SB: Not sure if this complete. We've had first offical meeting with the TU's, not seen any recognition/collective agreements.
HR | Develop any changes/protocols for LATCo and trade union facilities | Sharon Brown/Amey HR | 2020-06-07 | 2020-11-28 |  | in progress
Finance | Interest rate determination on loan for state aid purposes | Chris Neale | 2020-02-28 | 2019-11-27 | 2019-10-01 | in progress | 17/1/2020 Meeting requested in Finance for Mon 27/1 re Lease Finance accounting at which will agree next steps for this. 10/1/2020 LINK agreed re lease finance to ensure quotes requested for funding LATCO direct also, so that covered. (Chris separately to look at documenting confirmation that interest rates on any council loans correct to avoid being state aid). 10/12/2019 Chris requested Tim and Sarah re the timing of this, following up request of 11/11, where requested that the quotes include leasing via the Council and also direct to LATCO to show the difference to be charged by Council to avoid providing state aid. 10/12/2019 Chris also followed with Peterborough LATCO re 10/11 request re the calculation of the state aid compliant interest on loans from the council KRD 27/11/2019 - What is involved to get this figure
Finance | Agree payment mechanism for LBE /GEL contract and arrangement between GEL and LBE | Chris Neale/ Shabana Kausar / Simon Peet | 2020-01-31 | 2019-11-27 | 2019-10-01 | in progress | 6/1/2020 timescale of Jan not likely, however not absolutely nec till later 1/12/2019 Awaits SLA being further developed, to then progress
Finance | Accounts Payable SLA deliverable and volumes and KPIs | Georgia Hoare | 2020-01-31 | 2019-11-27 | 2019-10-01 | in progress | 13/1/2020 Georgia Hoare provided draft to John A, Chris and John P to confirm. 13/1/2020 Georgia Hoare confirmed would complete in next few days what possible now, conferring with John Parmenter where needed, and ensure note of what awaits further decisions, for her successor Liz. 7/1/2020 Georgia Hoare proposed would attend to Wed 8/1/2020 so completed this week. 6/1/2020 reminded Georgia Hoare. 10/12/2019 reminded Georgia Hoare re proforma given 27/11 to her so has info to complete
Finance | Vehicle lease quotes | Chris and Sarah | 2020-02-02 | 2019-11-27 | 2019-05-01 | in progress | 10/1/2020 Meeting held by Tim with LINK to ensure handover to his successor and that LINK aware of what needed next. 7/1/2020 Chris noted meeting planned with Link 10/1/2020 10/12/2019 Chris requested Tim and Sarah provide their outline planned timetable
Finance | Insurance | Chris Neale and Sarah Hadland & Ewan | 2020-07-01 | 2020-07-01 | 2020-07-01 | in progress | 8/1/2020 Mary confirmed for Kevin and John that insurance of new fleet subleased to Amey would need be via Amey's insurer. Rest of insurance procurement on track, for earlier awred 9/3/2020. 7/1/2020 Chris organised meeting of John and Kevin with Mary 8/1/20. 22/7/2019 Cabinet report authorised procurement, with 30/8/2019 Draft Tender Document, with 6/9/2019 Agree finalised tender specification, with 20/11/2019 Tenders back, with 21/2/2020 Final decision, 9/3/2020 Award Contract
Finance | Making tax digital | John Parmenter | 2020-03-05 | Requested clarification meeting 14/1 | Requested clarification meeting 14/1 | in progress | 14/1/2020 confirmed on track, with main item required from HR Payroll, due in few weeks, and no items needed from Finance, next update planned for Wed 26/2. 8/1/2020 requested clarification meeting Tues 14/1/2020, James Pugh 9/1 noted main deliverable is from HR Payroll (not Finance) and the project manager that would invite to 14/1/2020 meeting 7/1/2020 John requested meeting including Georgia, John wishing to attend also 6/1/2020 Chris noted the request to John Parmenter 10/12/2019 Chris asked John P to confirm following note here 27/11/2019 - KRD asked Chris please specify dates
Finance | Register for VAT | Chris Neale | 31/04/2020 | 2020-01-15 |  | in progress | 14/1/2020 agreed not likely to be before April 2020 need. 7/1/2020 agreed to discuss further with John Parmenter at 14/1/2020 making tax digital meeting. 10/12/2019- Chris requested dates from John Pamenter following up request of 23/10/2019 KRD 27/11/2019 - Chris please can you specify dates for this task
Finance | London Living Wage to calculate impact of 20p increase | Chris Neale | 2020-01-31 | 2020-12-16 |  | in progress | Seeking to start last week Jan 2020
ICT | HR |  | 2020-04-01 | 2019-11-08 |  | in progress
ICT | Business World GEL |  | 2020-07-07 | 2019-12-19 |  | in progress
ICT | GEL BW Client Build |  | 2020-04-06 | 2019-12-19 |  | in progress
ICT | Accounts payable |  | 2020-02-04 | 2020-01-15 |  | in progress
ICT | GEL Business Applications |  | 2020-06-02 | 2019-09-25 |  | in progress
ICT | CRM integration |  | 2020-02-27 | 2019-11-04 |  | in progress
ICT | Contender integrations - proposal |  | 2019-11-28 | 2019-11-04 |  | in progress
ICT | Contender integration development and testing |  | 2020-02-27 | 2019-12-02 |  | in progress
ICT | Support ICT |  | 2020-07-09 | 2019-11-27 |  | in progress
Legal | SLA support services (Support Services Agreement) | Chuhr Nijjar | 20.2.20 | 1.2.20 |  | in progress | 09/12/2019: CNi has written to colleagues on ICT, FM, HR and Finance to ascertain which contracts will need to progress specs for the support services agreement.
Legal | obtain details from Finance | Chuhr Nijjar | 20.2.20 | 1.2.20 | 2020-10-01 | in progress | 13/1/2020 Georgia confirmed working on SLA re payments for this week. 6/1/2020 reminded Georgia and John 27/11/2019 Georgia Hoare (& John Parmenter) have Accounts Payable KPIs and deliverables and have been requested to shape to propose to John Arnold, for incorporation into legal agreement
Legal | obtain details from ICT | Chuhr Nijjar | 20.2.20 | 1.2.20 |  | in progress
Legal | obtain details from FM | Chuhr Nijjar | 20.2.20 | 1.2.20 |  | in progress
Legal | obtain details from Payroll | Chuhr Nijjar | 20.2.20 | 1.2.20 |  | in progress
Legal | obtain details fromPensions Administration | Chuhr Nijjar | 20.2.20 | 1.2.20 |  | in progress
Legal | obtain details from Procurement Services | Chuhr Nijjar | 20.2.20 | 1.2.20 |  | in progress
Legal | Novation of existing contracts | Chuhr Nijjar | 2020-05-02 | 1.1.20 | 2020-01-20 | in progress | 09/12/2019: Any Amey or LBE contracts to novate to GE. CNi to liasing with colleagues.
Legal | Identify Amey contracts to Novate |  | 1.7.20 | 20.1.20 | 20.1.20 | in progress | 20/01/20 JA to identify the contracts
Legal | Loan agreement/funding facility agreement | Chuhr Nijjar | 1.3.20 | 1.1.20 | 1899-12-31 02:53 | in progress | 09/12/2019: CNi to liaise with Finance and client officers, including re interest rate
Legal | Draft Loan Agreement to KL |  | 1.3.20 | 1.1.20 | 1.1.20 | in progress | 20/01/2020 (KRD): Chuhr emailing Chris
Legal | Novation of procured contracts | Chuhr Nijjar | 2020-03-02 | ? |  | in progress | 09/12/2019: CNi working with procurement stream.
Legal | Identify other Contracts to Novate |  | 1.7.20 | 20.1.20 | 20.1.20 | in progress | 20/01/20 CNi to identify the contracts with colleagues
Legal | TUPE information to insert into Services Agreement | Chuhr Nijjar | 1.7.20 | 2019-12-16 | 2019-12-16 | in progress
Legal | Procurements | Chuhr Nijjar | 2020-03-02 | 1.1.20 |  | in progress | 09/12/2019: Numerous procurements which will need to be completed before GE commences services provision.
Legal | Vehicle procurement - approve & finalise agreements | Chuhr Nijjar | 2020-03-02 | 1.1.20 |  | in progress | 20/01/2020 Check status with SH on 23/1
Legal | Agreement with Amey to lease vehicles to Amey |  | 2020-03-02 | 1.1.20 |  | in progress
Legal | Vehicle Finance Lease | Chuhr Nijjar | 2020-03-02 | 1.1.20 |  | in progress | 20/01/2020 Check status with CNe
Legal | Vehicle maintenance procurement - approve & finalise agreements | Chuhr Nijjar | 2020-03-02 | 1.1.20 |  | in progress | 20/01/20 Tender out, updated documents out today. Tender return in February
Legal | Hire vehicles procurement - approve & finalise agreements | Chuhr Nijjar | 2020-03-02 | 1.1.20 |  | in progress
Legal | Staffing agencies procurement - approve & finalise agreements | Chuhr Nijjar | 2020-03-02 | 1.1.20 |  | in progress
Legal | Equipment procurement -approve & finalise agreements | Chuhr Nijjar | 2020-03-02 | 1.1.20 |  | in progress
Legal | Other products and services procurement -approve & finalise agreements | Chuhr Nijjar | 2020-03-02 | 1.1.20 |  | in progress
Legal | Insurance procurement approve & finalise agreements | Chuhr Nijjar (TLT) | 2020-03-02 | 1.1.20 |  | in progress | 09/12/2019 Ewan Taylor in Insurance will be instructing contracts team on the procurement
Legal | Property Leases & Licences | Jackie Adams | 1.7.20 | 1.1.20 | 1.1.20 | in progress
Legal | Heads of terms from LSH | Jackie Adams | 1.3.20 | 1.1.20 | 1.1.20 | in progress | 20/1/20 EM to instruct LSH for heads of terms
Legal | Lease or Licence Draft | Jackie Adams | 6.3.20 | 1.1.20 |  | in progress | 09/12/2019 CNi keeping a watching brief.
ICT (Depot) | Workshops\Garages |  | Thu 23/01/20 | Thu 02/01/20 |  | in progress
ICT (Depot) | Asbestos work |  | Thu 23/01/20 | Thu 02/01/20 |  | in progress
ICT (Depot) | Phase 1 Asbestos Removal Plant Room |  | Sun 05/01/20 | Thu 02/01/20 |  | in progress
ICT (Depot) | Phase 2 Asbestos Removal Bus Garages |  | Thu 23/01/20 | Fri 03/01/20 |  | in progress
GEL Tasks | Waste carriers licence | John Arnold/ Kevin Oleary | 2020-03-01 | 2020-01-06 | 2020-01-06 | in progress | Awaiting for all GEL directors to be added to companies house (X3 directors)
GEL Tasks | Ascertain if there are any Amey vehicles LBE would like to buy | John Arnold/ Earl McKenzie/ Kevin O'Leary | 2020-03-01 | 2020-01-06 | 2019-12-16 | In Progress | We have requested an updated fleet list with costs so we can make an informed decision
Finance | GEL Bank account set up | Simon Peet / Chris Neale | 2020-01-15 | 2020-11-01 | 2020-11-01 | In progress: delayed | Monday 13/1/2020 Lloyds confirmed had everything for bank account to be opened, hopefully this week, and had SUN indirect submitter form re payroll (sent original in post that day also) that might be completed the following week. 9/1/2020 SUN Indirect Submitter form drafted and given to Lara and to Kayleigh (of Lloyds bank) for final points to be concluded so then when sorted then can be put to Alison to sign, for SUN aspect to be sorted thereafter. Regarding separate (non SUN) point of bank account being set up, Bank have all other information for setting up bank account which can hopefully be set up by 17/1/2020, as bank 6/1/2020 said this can be done in a few days. 9/1/2020 SUN Indirect Submitter form drafted and provided to Karmveer to complete based on Ealing Pension Fund form he completed. 9/1/2020 Deborah confirmed sent in remaining details requested by bank and with which provided for sending in Nov 2019. 7/1/2020 KAP confirmed sent in, and Deborah to provide details of email so Chris can also be in contact with them. 6/1/2020 Chris requested Simon to submit Key Account information for new director Alison to bank, Alison confirmed had left Key Accout information for Simon on 20/12 when Simon on leave, following 6/12/2019 Chris chasing Simon for whether sent as Alison Key information signed left with Simon 20/12 on leave till 6/1.
ICT | Payroll file from HR to be received by BW team |  | 2019-01-22 | 2019-11-11 |  | In progress: delayed | 14/01/2020 (KRD): delayed by one week, update from HR on 22/01
ICT | SUN (Service User) numbers for bank account provided to HR |  | 2019-12-31 | 2019-12-31 |  | In progress: delayed | 14/01/2020 (KRD): delayed, hope to have by end of January. No impact as of yet
ICT | Whitespace Contract (Gcloud) sign-off |  | 2020-11-29 | 2019-10-22 |  | In progress: delayed
ICT | Sign-off |  | 2019-11-29 | 2019-11-29 |  | In progress: delayed | 21/01/2020 (KRD): still needs to be signed. Meeting arranged for 27/01/2020 to progress. Completion date moved from 29/11/2019 to 31/01/2020.
ICT | Data gathering |  | 2019-11-29 | 2019-10-03 |  | In progress: delayed
ICT | Internal testing |  | 2019-01-10 | 2019-01-06 |  | In progress: delayed | 21/01/2020 (KRD): more testing to be done
ICT | Order and receive kit |  | 2020-01-20 | 2019-12-17 |  | In progress: delayed | 20/01/2020 (KRD): cannot happen until the PID is signed off
ICT | Commercials - ICT |  | 2020-01-16 | 2019-11-27 |  | In progress: delayed | 14/01/2020 (KRD): due to be finished on 16/01/2020 21/01/2020 (KRD): it has been escalated. It has been sent to Peter Greenham
Legal | Variation of articles to be approved by Cabinet | Helen Harris | 2020-03-17 | 17.3.2020 |  | In progress: delayed | 09/12/2019: Articles - wrong version attached to the October Cabinet Report. Will need to go back to February Cabinet to amend the articles. 20/01/2020: will now go to March Cabinet, delayed from Feb Cabinet
Legal | New director to appoint to replace Tim Smith and obtain authority to indemnify new director | Helen Harris | 2020-02-28 |  | 2020-01-07 | In progress: delayed | 09/12/2019: HH & Ross to decide who to appoint as director to replace TS. HH has delegated authority to appoint directors and to give indemnities to directors. 20/01/2020 (KRD): approval required from Alison and Ross to indemnify Kieran Read. This task has been delayed from a completion date of 10/01/2020 to end of Feb.
Legal | Ealing Side Gel Governance - Directors Training | Helen Harris | 15.1.20 |  |  | In progress: delayed
Legal | Arranging training with TLT | Helen Harris | 2020-02-13 |  |  | In progress: delayed | 20/01/2020 (KRD): still in process of setting date of training itself, in liaison with TLT lawyers. Delaying required completion date from 10/01 to mid-Feb
Legal | Service Provision Agree - GEL and LBE | Chuhr Nijjar | 2020-01-10 | 1.10.19 |  | In progress: delayed
Legal | Agreement for the provision of services from GEL to LBE to KL | Chuhr Nijjar | 2020-01-17 |  |  | In progress: delayed | 09/12/2019 Ongoing - meeting every 2 weeks. Colleagues are updating specs, default provisions and KPIs. Aim to complete draft by Xmas and send to Kevin O'Leary early new year. HH suggestion for GE to meet with client departments to agree prices and other important issues. CNi to raise with Clients at meeting on Tuesday. 20/01/2020 (KRD): Chuhr said the agreement will be written by 24/01
ICT (Depot) | Strip A.I.B. Ceiling Soffit |  | Mon 13/01/20 | Fri 10/01/20 |  | In progress: delayed
ICT (Depot) | Fine Clean Enclosure |  | Sun 12/01/20 | Fri 10/01/20 |  | In progress: delayed
Procurement | Approach hire vehicle companies and/or potentially novate Amey vehicles if not comfortable with position | John Arnold/Sarah Hadland | 2020-02-28 |  |  | Not started | JA is creating a list of Amey contracts we need to novate where the total is under OJEU (£189K)
Procurement | Award Occupational Health Contract | John Arnold/Sarah Hadland | 2020-03-31 |  |  | Not started
Procurement | Award P.P.E supplier contract & place order | John Arnold/Sarah Hadland | 2020-02-28 |  |  | Not started
Procurement | Storage - find storage for fleet if required | John Arnold/Sarah Hadland | 2020-02-29 |  |  | Not started | Need to find enough storage for the fleet if we cannot do a staggered delivery
HR | Set up a workplace pension | Lara Balogun | 2020-06-06 | 2020-06-05 | 2020-06-07 | Not started
HR | Register with HMRC | Lara Balogun | 2020-05-06 |  |  | Not started | 1/12 to register with HMRC re PAYE once ready to have payroll
HR | HMRC to issue Company with Scheme Number | Lara Balogun | 2020-06-06 |  |  | Not started
HR | Register Company with NEST | Lara Balogun | 2020-06-06 |  |  | Not started | 1/12 Company registered Oct 19 with Companies House, to register re Pension once registered for PAYE
HR | Broadly equivalent LGPS or Admitted Body Status scheme for ex Ealing employees (up to 17) | Jenny Connett/Chuhr | 2020-06-07 | 2020-05-06 |  | Not started | Needs two months lead in to complete tasks
HR | Obtain confirmation of the names and details (that are available) of the staff that are to be included in the admitted body. | Sharon Brown | 2020-06-07 | 2020-05-06 |  | Not started | Need Amey to confirm TUPE data and names that need to be put into LGPS
HR | The application form and first tab of the new employer data request spreadsheet needs to be completed and returned and provided to pensions. The first few columns of the second tab can be completed with the names and basic information. | Chuhr | 2020-06-07 | 2020-05-06 |  | Not started
HR | Pensions to check with the actuaries to see if they need details of deferred benefits held with Ealing (or if the will extract this from the valuation data they already hold) | Jenny Connett | 2020-06-07 | 2020-05-06 |  | Not started
HR | Once received the above documents will be sent to the scheme actuaries to access the employers contributions rate (plus any possible deficit payments) and if a bond is required. | Jenny Connett | 2020-06-07 | 2020-05-06 |  | Not started
HR | The actuaries will then issue an admission summary paper (this might take 6 – 8 weeks, but hopefully will be sooner) | Jenny Connett | 2020-06-07 | 2020-05-06 |  | Not started
HR | A report will need to go to the Pensions Fund Panel (this will need to be submitted two weeks before the meeting date. I am not sure of the exact date it will be in June / July 2020) | Jenny Connett | 2020-06-07 | 2020-05-06 |  | Not started | report written and fully signed off by 15/6/2020. PFP meeting confirmed as 02/07/2020
HR | Develop a TUPE transfer process and ensure smooth transition of Amey staff to the LATCO | Sharon Brown | 2020-06-01 | 2020-01-31 |  | Not started | Need to take into account Amey's Mobilation Plan/current non contact wth Amey HR rep
HR | Complete due diligence/gap analysis of ELI | Sharon Brown |  | 2020-02-28 |  | Not started | 28/11/2019: What LATCo provisions are envisaged, as formulating them is a task in itself? SB: need to have productive dialogue with Amey HR re completion of TUPE spreadsheet. Amey mobilition plan states information to be provided 22/6/20!
HR | Identify and agree which roles/who should transfer | HR/ GEL Mgmt Team | 2020-06-01 | 2020-04-29 |  | Not started | 16/12 SB: Can't do this until Amey have provided TUPE list
HR | Develop proposals for any measures, including negotation on any new contractual provisions. | HR/ GEL Mgmt Team | 2020-06-01 | 2020-04-29 |  | Not started | 03/12/2019: need discussion with TU - need to jointly agreed and send measures letter re any proposed changes
HR | Develop staff consultation plan | HR/ GEL Mgmt Team | 2020-06-01 | 2020-04-29 |  | Not started | 03/12/2019: consultation plan needs to be devised in January 2020. Amey's mobilation plan suggests agreeing timetable for consultation in April, 18/5/20-19/6/20 to carry out consulation meetings and issuing letters to staff
HR | Agree consultation plan with trade unions | HR/KO'L | 2020-06-01 | 2020-04-29 |  | Not started
HR | Develop the staff consultation information, and consult | Sharon Brown | 2020-06-01 | 2020-04-29 |  | Not started
HR | Manage the staff transfer process | Sharon Brown | 2020-06-07 | 2020-06-06 |  | Not started | 28/11/2019: LBE's HR Shared Service Centre can be mobilised as a virtual team to support the TUPE document checking process for eligibility to work docs/checks
HR | Ensure payroll provider has TUPE transfer payroll data for payroll | Ealing/Amey Payroll contacts | 2020-06-07 | 2020-06-06 |  | Not started | Need to facilitate introduction of Ealing and Amey payroll contact
HR | Staff induction | Sharon Brown/ Gel Mgmt team/KO'L | 2020-07-06 | 2020-01-03 |  | Not started | Depends on what induction /training is being requested and provided by whom
HR | Review existing AMEY policies and procedures, amending to fit GEL (TUPE EMPLOYEES) | Sharon Brown | 2020-07-30 | 2020-06-30 |  | Not started | 16/12 Awaiting these being supplied. This can be done post transfer, as will need to consult on any changes proposed with staff group and the TU's.
HR | Redundancy benefits policy | GEL HR Manager | TBA | TBA |  | Not started
HR | Job evaluation procedure | GEL HR Manager | TBA | TBA |  | Not started
HR | Pay policy (base pay; overtime; bonuses; shift and other allowances) | GEL HR Manager | TBA | TBA |  | Not started
HR | Performance management | GEL HR Manager | TBA | TBA |  | Not started
HR | Sickness absence | GEL HR Manager | TBA | TBA |  | Not started
HR | Holiday policy and booking process | GEL HR Manager | TBA | TBA |  | Not started
HR | Overtime recording process | GEL HR Manager | TBA | TBA |  | Not started
HR | Signing in, signing out procedure | GEL HR Manager | TBA | TBA |  | Not started
HR | Other absences (paid; unpaid; procedure; entitlement) | GEL HR Manager | TBA | TBA |  | Not started
HR | Sick pay policy | GEL HR Manager | TBA | TBA |  | Not started
HR | Maternity/paternity/adoption/parental leave | GEL HR Manager | TBA | TBA |  | Not started
HR | Working Time Regulations/limits/opting out policy | GEL HR Manager | TBA | TBA |  | Not started
HR | Working week/working patterns/rest breaks/toil/overtime | GEL HR Manager | TBA | TBA |  | Not started
HR | Disciplinary procedure | GEL HR Manager | TBA | TBA |  | Not started
HR | Grievance procedure | GEL HR Manager | TBA | TBA |  | Not started
HR | Equal opportunities | GEL HR Manager | TBA | TBA |  | Not started
HR | Health and safety | GEL HR Manager | TBA | TBA |  | Not started
HR | Smoking at work | GEL HR Manager | TBA | TBA |  | Not started
HR | Harassment policy | GEL HR Manager | TBA | TBA |  | Not started
HR | Personal records and data protection | GEL HR Manager | TBA | TBA |  | Not started
HR | Handling organisational change policy | GEL HR Manager | TBA | TBA |  | Not started
HR | References policy | GEL HR Manager | TBA | TBA |  | Not started
HR | Handbook (reference to Modern Slavery Act 2015 Regs/Anti corruption policy/Bribery Act 2010). Company property (care, reporting damage, returning, storing, handover, keep it safe) | GEL HR Manager | TBA | TBA |  | Not started
HR | Email/internet policy | GEL HR Manager | TBA | TBA |  | Not started
HR | Mobile phone policy | GEL HR Manager | TBA | TBA |  | Not started
HR | Expenses policy | GEL HR Manager | TBA | TBA |  | Not started
HR | Identify local reps/shop stewards and what the consultative requirements are | Sharon Brown/Amey HR | 2020-07-06 | 2020-06-06 |  | Not started | Could discuss with Dean Gilligan at next TU meeting
HR | Payroll/HR provider | Andrew Scully/ Lara Balogun | 2020-06-01 |  |  | Not started
HR | Training & Development Plan | GEL HR |  |  |  | Not started
HR | Apprenticeship Programme | GEL HR |  |  |  | Not started
HR | Employment links with local employers and schools | GEL HR |  |  |  | Not started
H&S | Agree approach to the develop of route risk assessments | Health and safety consultant | TBC (h&s consultant conducting gap analysis) |  |  | Not started | have Amey's Risk Assessments which we can use as a start point
H&S | Understand COSHH requirements across the service | Health and safety consultant | TBC (h&s consultant conducting gap analysis) |  |  | Not started | have Amey's COSHH Assessments which we can use as a start point
H&S | Health and Safety | Health and safety consultant | TBC (h&s consultant conducting gap analysis) |  |  | Not started | Need to develop a H&S Policy have a draft one for GEL from the HSE website
H&S | Environment | Health and safety consultant | TBC (h&s consultant conducting gap analysis) |  |  | Not started | Need to develop a Policy
H&S | Develop risk assessments for all operations | Health and safety consultant | TBC (h&s consultant conducting gap analysis) |  |  | Not started | have Amey's Risk Assessments which we can use as a start point
H&S | Develop Safe Systems of Work for waste operations | Health and safety consultant | TBC (h&s consultant conducting gap analysis) |  |  | Not started | Have Amey's SSOW can be used as a start point
H&S | Identify training requirements for day one and on an ongoing basis | Health and safety consultant | TBC (h&s consultant conducting gap analysis) |  |  | Not started | Ask Amey for their training matrix and highlight the training they actually carry out
H&S | Approval of risk assessments | Health and safety consultant | TBC (h&s consultant conducting gap analysis) |  |  | Not started | Need to speak to LBE H&S for support RE. using Amey's Risk Assessments as a start point of the contract and review as we go during the 1st 6 months of GEL
H&S | Undertake route risk assessments | Health and safety consultant | TBC (h&s consultant conducting gap analysis) |  |  | Not started | Have Amey's RRRA
H&S | Approval of Safe Systems of Work | Health and safety consultant | TBC (h&s consultant conducting gap analysis) |  |  | Not started | Need to speak to LBE H&S for support RE. using Amey's SSOW as a start point of the contract and review as we go during the 1st 6 months of GEL
H&S | Undertake Fire Risk Assessment on the new depot area | Health and safety consultant | TBC (h&s consultant conducting gap analysis) |  |  | Not started | Should be pre existing as LBE depot
H&S | Develop evacuation plan for depot | Health and safety consultant | TBC (h&s consultant conducting gap analysis) |  |  | Not started | Should be pre existing as LBE depot
H&S | Approval of route risk assessments | Health and safety consultant | TBC (h&s consultant conducting gap analysis) |  |  | Not started | Need to speak to LBE H&S for support RE. using Amey's RRRA as a start point of the contract and review as we go during the 1st 6 months of GEL
H&S | Training and dissemination of risk assessments | Health and safety consultant | TBC (h&s consultant conducting gap analysis) |  |  | Not started | Training will be carried out as part of the induction (induction plan to still be drafted)
H&S | Training and dissemination of route risk assessments | Health and safety consultant | TBC (h&s consultant conducting gap analysis) |  |  | Not started | Training will be carried out as part of the induction (induction plan to still be drafted)
H&S | Training and dissemination of Safe Systems of Work | Health and safety consultant | TBC (h&s consultant conducting gap analysis) |  |  | Not started | Finance will need to be involved in this as there will be a cost element I.E overtime paid to amey to train the staff before go live date
Finance | PAYE registering | Chris Neale | 2020-05-04 | 2020-01-31 |  | Not started | 10/12/2019 Chris noted update, provided 23/10.2019, that should not start to register payroll until 4 week before have staff on payroll if do on the phone (max 8 weeks before have staff on payroll, if online), to avoid having payroll fines of £100-£400. KRD 27/11/2019 - Chris please can you specify dates for this task
Finance | Handover information for GEL New Finance Manager | Chris Neale | 2020-03-15 | 2020-02-01 | 2020-02-01 | Not started
Finance | Sort out appointment of auditor | Chris Neale / Simon Peet | 2020-02-28 | 2020-02-01 | 2020-01-06 | Not started | 10/1/2020 Simon checking with Deloitte. 7/1/2020 Chris asked Simon to ask Deloitte how wished formalised. 6/1/2019 Chris got info from Simon Peet re Deloittes auditors, and asked Simon how to progress, and from Simon re PwC tax advisor.
ICT | HR BACS file updated |  | 2020-04-01 | 2020-04-01 |  | Not started
ICT | Accounts receivable |  | 2020-02-19 | 2020-02-05 |  | Not started
ICT | Integration |  | 2020-03-05 | 2020-02-20 |  | Not started
ICT | Making tax digital installation of BW module and client |  | 2020-03-05 | 2020-02-20 |  | Not started
ICT | Systems test and fix |  | 2020-03-19 | 2020-03-06 |  | Not started
ICT | Set up balance tables, planner revenue, capital, logistics, actuals data |  | 2020-03-24 | 2020-03-20 |  | Not started
ICT | Set up basic reporting, AP, AR, trial balance |  | 2020-03-30 | 2020-03-24 |  | Not started
ICT | Banking set up facility for manual upload of statement into BW |  | 2020-04-02 | 2020-03-31 |  | Not started
ICT | BW Development and system testing complete |  | 2020-04-06 | 2020-04-03 |  | Not started
ICT | GEL UAT Post Build Test and Train |  | 2020-07-07 | 2020-04-07 |  | Not started
ICT | BW UAT |  | 2020-04-27 | 2020-04-07 |  | Not started
ICT | BW Training |  | 2020-05-04 | 2020-04-21 |  | Not started
ICT | BW - data input |  | 2020-05-08 | 2020-05-05 |  | Not started
ICT | Testing, ready for go-live |  | 2020-07-02 | 2020-05-11 |  | Not started
ICT | Go live/no go-live decision |  | 2020-07-03 | 2020-07-03 |  | Not started
ICT | Go live |  | 2020-07-07 | 2020-07-07 |  | Not started
ICT | vehicle kit out |  | 2020-02-14 | 2020-02-03 |  | Not started | 14/01/2020 (KRD): do not know when vehicles will be devlivered and cannot therefore have start and finish date
ICT | Training |  | 2020-02-20 | 2020-01-27 |  | Not started
ICT | UAT |  | 2020-04-06 | 2020-03-10 |  | Not started
ICT | Ready for go-live - parallel running |  | 2020-04-14 | 2020-04-14 |  | Not started
ICT | Analytics delivery |  | 2020-05-27 | 2020-04-15 |  | Not started
ICT | Complete go-live by turning off parallel running |  | 2020-06-02 | 2020-06-02 |  | Not started
ICT | GEL ICT Infrastructure and Hardware |  | 2020-04-06 | 2019-10-01 |  | Not started
ICT | Network/wifi implement |  | 2020-02-24 | 2020-02-04 |  | Not started
ICT | Desktop hardware - implement |  | 2020-03-02 | 2020-02-25 |  | Not started
ICT | Telephony - implement |  | 2020-03-09 | 2020-02-25 |  | Not started
ICT | Printers - implement |  | 2020-03-09 | 2020-02-25 |  | Not started
ICT | Implement furniture |  | 2020-02-17 | 2020-01-21 |  | Not started
ICT | Test and completion |  | 2020-04-06 | 2020-03-10 |  | Not started
ICT | Network support |  | 2020-07-09 | 2019-02-25 |  | Not started | 14/01/2020 (KRD): due to start on 30/03/2020 (change from 25/02/2020)
Legal | Completion of Agreement - executed by both parties |  | 1.7.20 |  |  | Not started
Legal | Draft SLA to KL covering heads listed below |  | 20.2.20 | 1.2.20 |  | Not started
Legal | Completion of SLA |  | 1.7.20 | 1.2.20 |  | Not started
Legal | obtain details from HR | Chuhr Nijjar | 20.2.20 | 1.2.20 |  | Not started
Legal | obtain details fromLegal Services | Chuhr Nijjar | 20.2.20 | 1.2.20 |  | Not started
Legal | Completion of Loan Agreement |  | 1.7.20 | 1.7.20 |  | Not started
Legal | Pensions | Chuhr Nijjar | 2.5.2020 |  |  | Not started | 09/12/2019: Meeting with HR who are progressing these arrangements and have been advised to obtain pension panel authority for admission agreement.
Legal | NEST for new staff | Shahzad Ayub | 2020-06-06 |  |  | Not started
Legal | Authority to enter into Admission Agreement from Pension Panel |  | 2020-05-02 |  |  | Not started
Legal | LGPS - Admission Agreement draft to KL | Chuhr Nijjar | 2020-03-02 |  |  | Not started
Legal | Completion of Lease or Licence |  | 1.7.20 |  |  | Not started
Legal | Sub Lease to Vehicle Maintenance operator |  | 1.7.20 |  | 13.1.20 | Not started
ICT (Depot) | Phase 3 Roof Works |  |  |  |  | Not started
ICT (Depot) | External Cladding |  | Wed 29/01/20 | Thu 23/01/20 |  | Not started
ICT (Depot) | Bird netting |  | Fri 31/01/20 | Thu 30/01/20 |  | Not started
ICT (Depot) | Scaffolding/ roof set up |  | Thu 30/01/20 | Wed 29/01/20 |  | Not started
ICT (Depot) | Roof Coatings/ Roof lights |  | Sat 22/02/20 | Thu 30/01/20 |  | Not started
ICT (Depot) | Finalise |  | Mon 24/02/20 | Sun 23/02/20 |  | Not started
ICT (Depot) | Clear Site |  | Thu 27/02/20 | Thu 27/02/20 |  | Not started
ICT (Depot) | Completion |  | Fri 28/02/20 | Fri 28/02/20 |  | Not started
ICT (Depot) | Heating works |  | Fri 27/03/20 | Mon 02/03/20 |  | Not started
ICT (Depot) | Re-instating heating at workshops\garages |  | Fri 27/03/20 | Mon 02/03/20 |  | Not started
ICT (Depot) | Parking |  | Mon 02/03/20 | Mon 02/03/20 |  | Not started
ICT (Depot) | Parking area for 150 vehicles |  |  | TBD |  | Not started
ICT (Depot) | 20 Electric Charge points |  |  | TBD |  | Not started
ICT (Depot) | All other requirements |  | Tue 10/03/20 | Mon 02/03/20 |  | Not started
ICT (Depot) | Facilities currently in use by AMEY to be provided to GEL |  | Tue 10/03/20 | Mon 02/03/20 |  | Not started
GEL Tasks | Negotiate deal with Amey | John Arnold/ Earl McKenzie/ Kevin O'Leary | 2020-04-01 | 2020-02-01 |  | Not Started | We have a fleet consultant who will assist the project in the O Licence application and check that our plans keep us compliant
GEL Tasks | Work Out who COTC Holder Is | John Arnold/ Earl McKenzie/ Kevin O'Leary | 2020-07-01 | 2020-02-01 |  | Not Started | We have a fleet consultant who will assist the project in the O Licence application and check that our plans keep us compliant
GEL Tasks | Apply for O Licence | John Arnold/Kevin O'Leary + Consultant | 2020-07-01 | 2020-02-01 |  | Not Started | We have a fleet consultant who will assist the project in the O Licence application and check that our plans keep us compliant
GEL Tasks | Transport Manager CPC holder(Green Recruitment time) | John Arnold/Kevin O'Leary + Consultant | 2020-07-01 | 2020-02-01 |  | Not Started | We have a fleet consultant who will assist the project in the O Licence application and check that our plans keep us compliant
GEL Tasks | O Licence Granted | John Arnold/Kevin O'Leary + Consultant | 2020-07-01 | 2020-02-01 |  | Not Started | We have a fleet consultant who will assist the project in the O Licence application and check that our plans keep us compliant
GEL Tasks | V5s handed over | John Arnold/Kevin O'Leary + Consultant | 2020-07-01 | 2020-02-01 |  | Not Started | We have a fleet consultant who will assist the project in the O Licence application and check that our plans keep us compliant
GEL Tasks | Keys and spares handed over | John Arnold/Kevin O'Leary + Consultant | 2020-07-01 | 2020-02-01 |  | Not Started | We have a fleet consultant who will assist the project in the O Licence application and check that our plans keep us compliant
GEL Tasks | Maintenance records handed over | John Arnold/Kevin O'Leary + Consultant | 2020-07-01 | 2020-02-01 |  | Not Started | We have a fleet consultant who will assist the project in the O Licence application and check that our plans keep us compliant
GEL Tasks | MOT records handed over | John Arnold/Kevin O'Leary + Consultant | 2020-07-01 | 2020-02-01 |  | Not Started | We have a fleet consultant who will assist the project in the O Licence application and check that our plans keep us compliant
GEL Tasks | LOLER records handed over | John Arnold/Kevin O'Leary + Consultant | 2020-07-01 | 2020-02-01 |  | Not Started | We have a fleet consultant who will assist the project in the O Licence application and check that our plans keep us compliant
GEL Tasks | Understand current defect process | John Arnold/Kevin O'Leary + Consultant | 2020-07-01 | 2020-02-01 |  | Not Started | We have a fleet consultant who will assist the project in the O Licence application and check that our plans keep us compliant
GEL Tasks | Make sure each round/beat has a map and a road list of each day | John Arnold/Kevin O'Leary | 2020-07-01 | 2020-05-01 |  | Not Started
GEL Tasks | Highlight assisted and ensured collections on each round | John Arnold/Kevin O'Leary | 2020-07-01 | 2020-05-01 |  | Not Started
Legal | Provision of training to Ealing Directors | Helen Harris | 2020-02-28 |  |  | Not started: delayed | 9/12/2019 HH to arrange training via TLT and include all relevant officers 20/01/2020 (KRD): delayed as training hasn't been fully arranged yet
ICT (Depot) | Air Test Enclosure |  | Sun 19/01/20 | Sat 18/01/20 |  | Not started: delayed
ICT (Depot) | Strip down Enclosure |  | Mon 13/01/20 | Fri 10/01/20 |  | Not started: delayed
ICT (Depot) | Dismantle Scaffolding |  | Thu 23/01/20 | Wed 22/01/20 |  | Not started: delayed
ICT (Depot) | Roof Works |  | Fri 28/02/20 | Thu 02/01/20 |  | Not started: delayed
ICT (Depot) | Inspections |  | Thu 02/01/20 | Thu 02/01/20 |  | Not started: delayed
ICT (Depot) | Pre-Start Meeting |  | Mon 13/01/20 | Mon 13/01/20 |  | Not started: delayed
ICT (Depot) | Site Set Up |  | Wed 22/01/20 | Mon 20/01/20 |  | Not started: delayed
ICT (Depot) | Clearing of rubbish at the site |  | Fri 10/01/20 | Wed 18/12/19 |  | Not started: delayed
ICT (Depot) | Clearing of rubbish at the site for lanscaping |  | Fri 10/01/20 | Wed 18/12/19 |  | Not started: delayed
GEL Tasks | ABP Permit (free) |  | POST GO LIVE
Note on B161: John Arnold: Tasks to complete Milestone
Note on B177: Killian Rosato-Dooey: We need to specify what tasks are involved to achieve this deliverable