## Title Page
Project Name: | Transfer of Environmental Services
Version: | 0.1
Contact: | Gillian Marston
Email: | MarstonG@ealing.gov.uk
Phone:
Summary of Project and Risks
RISK REGISTER

## Scoring Matrix
DO NOT DELETE OR EDIT
Scoring
|  |  | High | 15 - 25 |  |  | = High Priority
|  |  | Medium | 5_ 14 |  |  | = Medium Priority
|  |  | Low | 0 - 4 |  |  | = Low Priority | PICK LIST
Overspend
Spending too much time
|  |  | Scoring Matrix |  |  |  |  | Legal
IMPACT | H | 5 | 5 | 15 | 25 |  |  | Technical
| M | 3 | 3 | 9 | 15 |  |  | Reputation
| L | 1 | 1 | 3 | 5 |  |  | Financial
|  |  | 1 | 3 | 5 |  |  | Environmental
|  |  | L | M | H
Probability
DO NOT DELETE OR EDIT
Probability Score | [5 empty] | Impact (£ m = million)
Up to 10% equals Low (1 - 3) | [5 empty] | 0 - 10 M = Low (1 - 3)
From 11% to 60% equal Medium (5 - 9) | [5 empty] | 10 M - 100 M = Medium (5 - 9)
From 61% up to 100% equals High (15 - 25) | [5 empty] | 100 M + = High (15 - 25)

## PMO Support
Workstream
Finance | Up-to-date as of 11/12/2019 (weekly monitoring from January 2020 to update risks and consider mitigations)
Procurement | Up-to-date as of 06/12/2019 (weekly monitoring from January 2020 to update risks and consider mitigations)
ICT | In progress - weekly monitoring meetings from January 2020 to update and consider mitigations
HR | Risk Register updated as of 02/12/2019. A further update will need to take place once updated workstream plan has been achieved (in addition to weekly monitoring from January 2020).
*Health and Safety | Risks to be updated once workstream plan has been updated. Killian and John meeting Health and Safety W/C 16/12/2019. A work package lead will have to be assigned in order for weekly monitoring to take place from January 2020.
*Communications
*Legal | In progress - weekly monitoring meetings from January 2020 to update and consider mitigations
Additionally - Column C of the Risk Register (Sheet) requires addressing. Will greatly enhance efficiency of weekly monitoring from Janaury. Risks can be easily identified, updated, and closed if necessary. Also, those risks that are no longer live need to be moved into the closed risks Sheet. This could take place in the first weekly monitoring meeting John/Killian have with respective workstream Leads in early-January 2020.

## Risk Register
Project Name | Transfer of Environmental Services
Risk Identification | [9 empty] | Assessment |  |  | Risk Management |  |  |  |  | Residual Risk Assessment |  |  | Contingency Strategy
Risk Number | Date Added | WORKSTREAM | Officer responsible for mitigating action(s) | Risk link | Risk Description* | Risk Owner | Effect | Category (source of risk) | Status | Probability | Impact | Rating (RYG) | Potential Mitigation | Date By | Management Actions Taken | Date Updated | Comments | Probability | Impact | Rating (RYG) | Action undertaken if risk occurs
4 |  |  |  |  | Brexit |  | Labour shortage and costs go up | Financial | Closed | 3 | 5 | 15 | reduce specs on cleansing and GM further to make sure a waste service runs |  | Transitiion period lasts for the whole of 2020 | 2020-06-12 |  | 1 | 5 | 5
5 |  |  |  |  | Brexit |  | Timelines for vehicles & costs of vehicles increase | Financial | Closed | 3 | 5 | 15 | (9/12 JA to update 'Negotiate a fixed price with suppliers before March 2019 (now Oct)') |  |  | 2020-06-12 |  | 1 | 5 | 5
6 |  |  |  |  | Brexit |  | Subcontractor/materials/supplier cost increase | Financial | Closed | 3 | 5 | 15 | (9/12 JA to update 'Negotiate a fixed price with suppliers before March 2019 (now Oct)') |  |  | 2020-06-12 |  | 1 | 5 | 5
7 |  |  |  |  | Brexit |  | Repairs & maintenance costs increase | Financial | Closed | 3 | 5 | 15 | (9/12 JA to update 'Negotiate a fixed price with suppliers before March 2019 (now Oct)') |  |  | 2020-06-12 |  | 1 | 5 | 5
8 |  |  |  |  | Brexit |  | Pressure to produce savings increase | Financial | Closed | 3 | 5 | 15 | (9/12 JA to update 'Negotiate a fixed price with suppliers before March 2019 (now Oct)') |  |  | 2020-06-12 |  | 1 | 5 | 5
9 |  |  |  |  | Brexit |  | Changes to taxation | Financial | Closed | 3 | 5 | 15 | (9/12 JA to update 'Negotiate a fixed price with suppliers before March 2019 (now Oct)') |  |  | 2020-06-12 |  | 1 | 5 | 5
10 |  |  |  |  | Brexit |  | Fuel costs increase | Financial | Closed | 3 | 5 | 15 | (9/12 JA to update 'Negotiate a fixed price with suppliers before March 2019 (now Oct)') |  |  | 2020-06-12 |  | 1 | 5 | 5
11 |  |  |  |  | Brexit |  | Change in pricing | Financial | Closed | 3 | 5 | 15 | (9/12 JA to update 'Negotiate a fixed price with suppliers before March 2019 (now Oct)') |  |  | 2020-06-12 |  | 1 | 5 | 5
12 |  | Procurement | Sarah Hadland/ John Arnold |  | Vehicle costs |  | 10-12% increase in price because of Brexit |  | Closed | 3 | 5 | 15 | confirm prices early Jun 19 be aware there maybe some underlining charge increase. | 31.01.2020 | Prices have been agreed and honered we are liable for increase tarrifs and are working with suppliers to minimise charges I.E shipping a whole vehicle across rather then in parts | 2020-06-12 |  | 1 | 5 | 5
13 |  | GEL HR | Sharon Brown (recruitment process underway) | 1 | Amey providing TUPE data only 28 days before go live (creates pressure as little time to resolve data issues) |  | Outstanding pressure on service resulting in poor start to contract | Reputation | Closed | 5 | 5 | 25 | Request earlier infomration from Amey, have Agency supplier ready for day one to reduce/ fill any gaps. GEL have already begun to recruit senior team for key positions such as HR manager and Finance manager for GEL | 31.01.20 | TUPE information request sent to Amey WC 16.12.2019 | 2020-06-12 |  | 3 | 3 | 9
14 |  | Procurement | Sarah Hadland/ John Arnold | 2 | Vehicles/Plant/equipment |  | Not all ready to go live on day one | Technical | Active | 3 | 5 | 15 | The project team will continue to push suppliers to deliver on time. There are a few ways Ealing can mitigate this by doing the following A) Novate some of Amey fleet across for short term B) Short term hire and charge back to the suppliers (term in vehicle tender contract) | 04.04.2020 - 06.7.2020 | The three choices have been discussed by the programme board, the project team are in constant dialog with the suppliers and meetings have been arranged for 29.01.2020. (A) and (B) have been implemented. | 2020-06-12 |  | 3 | 3 | 9
15 |  | LBE Street Services | Earl McKenzie | 3 | Amey relationship breakdown making mobilisation problematic and service inherited very poor. |  | LAC inherit significant service issues | Technical | Active | 3 | 5 | 15 | LBE team continue engagement with Amey and monitor contract performance | on going | LBE senior team keeping dialog open with Amey to ensure this does not happen | 2020-06-12 |  | 3 | 3 | 9
|  | LBE Street Services/ GEL | Earl McKenzie/ Kevin O'Leary/ John Arnold | 4 | Fleet delivered all at once, i.e. weekend before go live (impacts on all services as vehicle familiarisation training required may not be finished impacts service throughout the rest of the week) |  | LAC inherit significant service issues for day one as mobilisation of 145 vehicles will be difficult | Technical | Closed | 3 | 5 | 15 | Discussion with Amey to use fleet and plant as they are delivered for a short period before go live I.E Apr -Jul Amey will need to insure the fleet and plant etc. for use | on going | Agree in writing Amey will use fleet as delivered based on our delivery timeline they will need to insure | 2020-06-12 |  | 3 | 3 | 9
16 |  | LBE Street Services/ GEL | Earl McKenzie/ Kevin O'Leary | 5 | Non support from Amey during last three months |  | Transistion of services becomes disrupted | Reputation | Active | 3 | 3 | 9 | agree in writing in advance (2019) support requirements from Amey and any cost implications | on going | LBE senior team keeping dialog open with Amey to ensure this does not happen | 2020-06-12 |  | 3 | 3 | 9
17 |  | LBE Street Services/ GEL | Earl McKenzie/ Kevin O'Leary | 5 | storage |  | No storage for fleet and plant if no agreement for Amey to use before GO LIVE | Financial | Closed | 3 | 5 | 15 | Speak to Suppliers to hold fleet/plant until just before Go live/ use any other space to store the fleet and equipment which will cost us more money as need security etc. | 28.02.20 | Discussion with Amey to use fleet and plant as they are delivered for a short period before go live I.E Apr -Jul Amey will need to insure the fleet and plant etc. for use. Agreement reached with suppliers where possible to store fleet and plant through until delivery, and have also got support from Hounslow and Harrow. | 2020-06-12 |  | 3 | 3 | 9
18 |  | All | all | Strat | LAC is not established in time to carry out service |  | Cannot carry out service | Reputation | Closed | 1 | 5 | 5 | Mobilisation resource planning required | on going | project team are working to the timelines to get the project ready for Go live | 2020-06-12 |  | 1 | 5 | 5
19 |  | ICT/HR(ICT) | Shahzad Reyman/ Lara B |  | Tax & VAT |  | The LATC by definition will be subject to Corporation Tax unless it is structured in such a way as to be exempt. There could be significant implications and financial penalties if this or the way the company accounts for VAT are not correct. | Financial | Closed | 3 | 5 | 15 | GEL will have to comply with Making Tax digital this is being reviewed by I-trent and BW development groups | 01.08.2019 | BW & i-Trent currently working to make Tax digtial for GEL the solution will be used for the wider Council as they will also have an obligation to do this in 2020 | 2020-06-12 |  | 1 | 5 | 5
20 |  | GEL/LBE | Kevin O'Leary / Earl McKenzie/ Chris Bunting |  | weed control chemical usage (Glyphosate) |  | Legislation could change banning the use of Glyphosate as has Carcinogenic properties | Environmental | Closed | 3 | 3 | 9 | Can use foam treatment (coconut oil and other natrual treatments costs more) Glyphosate section in Buisness plan where cabinet can choose) | on going | LBE and Gel are intouch with LEDNET who are reviewing the current use of Gyphosate | 2020-06-12 |  | 1 | 5 | 5
21 |  | HR/H&S/GEL | Sharon Brown/ Kevin O'Leary/ Liz |  | LAC do not have the appropriate polices and procedures in place to operate a safe operational service causing injury to staff or members of the public |  | Cannot carry out service | Reputation | Closed | 1 | 5 | 5 | Mobilisation resource planning required | on going | these are being developed ACAS templates will be used | 2020-06-12 |  | 1 | 5 | 5
22 |  | ICT | Shahzad Reyman |  | LAC does not have the appropriate business processes in place to ensure the effective delivery of the service causing a decrease in service standards and impacting on Ealing Council reputation |  | Cannot carry out service | Reputation | Closed | 1 | 5 | 5 | Develop business processes to form part of the ICT service specification | on going | currenttly wokring to the timeline | 2020-06-12 |  | 1 | 5 | 5
24 |  | HR/GEL/LBE | Sharon Brown/ Kevin O'Leary/ Earl McKenzie |  | LAC Staff are not paid on first payroll and therefore service is not delivered |  | Cannot carry out service | Technical | Active | 1 | 5 | 5 | Discuss requirements with payroll as part of plan and ensure all timelines are understood, with support provided at first payroll | on going | back up plan we can up laod the TUPE data into the Ealing I-Trent system to pay the staff. Currently BW and I-Trent teama re working to the timeline to get this completed for GEL | 2020-06-12 |  | 1 | 5 | 5 | BR
25 |  | All | all |  | Transferring staff have not received suitable induction and therefore cannot carry out the service |  | Cannot carry out service | Technical | Active | 1 | 5 | 5 | A training and induction plan can be built into the programme plan | on going | Induction/ training induction being developed part of this depends on Amey discussions I.E vehicle swapping as they are delivered. Carrying out induction on 20th, due to COVID-19 will carry out full induction during first month of operations. | 2020-06-12 |  | 1 | 5 | 5 | br
27 |  | GEL HR | Unknown(recruitment process underway) |  | Unknown claims against staff, Tribunal, injury |  | Council end up with the costs | Financial | Closed | 5 | 5 | 25 | Request all information in advance and keep dialog open with amey up to last day for any outstanding claims | 31.01.20 | Liability information to be requested alongside TUPE information. E-mail sent to Amey WC 16.12.19 | 2020-06-12 |  | 1 | 3 | 3
29 |  | Procurement | Sarah Hadland/ John Arnold |  | Workforce numbers lower than required (sick, Holiday, absent) |  | Full service does not run day one | Technical | Closed | 3 | 5 | 15 | Agency suppliers on board for 1st month | 01.06.2020 | Procurement of Agency contract has already begun, meeting booked for 16.01.2020 to finalise call off from M-Star framework. Agency supplier (Pertmeps) has been finalised. | 2020-06-12 |  | 1 | 3 | 3
30 |  | Procurement | Sarah Hadland/ John Arnold |  | HGV drivers , knowledge transfer GM skills shortage commercial waste knowledge |  | Skills shortage from day one resulting in service disruption | Technical | Closed | 3 | 5 | 15 | Agency suppliers on board for 1st month | 01.06.2020 | Procurement of Agency contract has already begun, meeting booked for 16.01.2020 to finalise call off from M-Star framework | 2020-06-12 |  | 1 | 3 | 3
31 |  | HR/GEL/Legal | Sharon Brown/Kevin O'Leary & Helen Harris |  | O Licence holders |  | Without O Licence no vehicle over 3.5t can leave the depot | Technical | Closed | 3 | 5 | 15 | need a min of 2 for number of fleet, if use Harrow they can supply X2 Transport managers. If we own the vehicles we should recruit in advance for those roles as exsiting staff could be used in other positions. | 01.02.2020 | Currently in dialog with amey to see if the transport manager will be on the TUPE list. If not we have put a budget aside for recruitment of a transport manager for GEL. We also have consultancy support for applying for the O'Licence | 2020-06-12 |  | 1 | 3 | 3
32 |  | Procurement | Sarah Hadland/ John Arnold |  | Management and running of workshops |  | Need to identfy key personal that need to transfer Workshops Nick Wilson currently runs Greenford workshop | Technical | Closed | 3 | 5 | 15 | Negotiate with Amey advance TUPE (6months) for those that wish to come to LATCO Key postions or for split time between Amey and LATCO 50/50 split. If not recruit position 3 months in advance | 30.03.2020 | Workshop maintenance Tender has gone out to suppliers on a framework. Once completed the maintenance provider will be appointed | 2020-06-12 |  | 1 | 3 | 3
33 |  | H&S | Liz/ John Arnold |  | H&S Risk assessments and SSOW not ready for day one. |  | No RRRA or SSOW for day one resulting in unsfae workforce | Technical | Closed | 3 | 5 | 15 | Negotiate with Amey advance TUPE (6months) for those that wish to come to LATCO Key postions or for split time between Amey and LATCO 50/50 split. If not recruit position 3 months in advance. | 30.01.2020 | Amey have provided their SSOW & Risk Assessments, GEL need to review and see if these are fit for purpose if so they can adopt . | 2020-06-12 |  | 1 | 3 | 3
34 |  | GEL/ LBE | Kevin O'Leary/ John Arnold/ Earl McKenzie |  | Check legislation changes |  | Possible changes forcing sort separate collections | Environmental | Closed | 3 | 5 | 15 | Lease some vehicles as changes will affect methodolgy & collection plan to reduce cost implications needs to be under 2 years | 02.04.2019 | No forcasted changes to legislation, If changes happen this will need to be reviewed by GEL, the shareholder and LBE operations as this would not be a small change and would end up as waste service change invloving staff, vehicles etc. | 2020-06-12 |  | 1 | 3 | 3
35 |  | HR | Unknown(recruitment process underway) + Sharon Brown |  | Pensions |  | The LATC will TUPE staff who were transferred to EMS when the contract was originally let as well as staff that have been employed subsequently and new staff once the LATC is operational. There will need to be pension provision in place for all of these staff. The company will need to gain admitted body status and provide a pension option for new staff. | Financial | Closed | 3 | 5 | 15 | Identified 17 staff who will have admitted body status for the LGPS pension the remaining staff will be included in a NEST scheme pension | 17.09.2019 | This is part of the project plan and is being worked on by HR | 2020-06-12 |  | 1 | 3 | 3 |  | 11.6.20 Jenny Connett and William Gilmour (HR Manager; HR Workstream Lead) produced a letter to be sent to those transferring employees not originally anticipated to be joining GEL with a right to join the LGPS (i.e. persons with LBE service prior to 1.4.94 or service with another LGPS employer). Respective employment history will be attached to this letter.
36 |  | HR/GEL | Sharon Brown/ Kevin O'Leary |  | Key members of the Amey operational team did not TUPE transfer leaving a knowledge gap amongst staff |  | Day one operational continuity impacted | Technical | Closed | 3 | 3 | 9 | Contingency plans to be put in place through the use of the mobilisation team to bed in service. | 31.01.2020 | Early discussions witrh Amey RE real TUPE data so GEL have enough time to recruit roles | 2020-06-12 |  | 3 | 1 | 3 |  |  | Need to identfy key personal that need to transfer for H&S Sandra Hewyey is currently OSA (Operational Safety Advisor)
37 |  | ICT | Shahzad Reyman |  | ICT systems are not developed in time for new service causing significant issues in dealing with customer requests |  | Poor service for residents | Technical | Closed | 3 | 3 | 9 | Early engagement with ICT and ICT to form part of Steering Group | 30.04.2020 | If Whitespace is not working on day one GEL will treat all missed collectiions as justifed and will clear until system is up and running | 2020-06-12 |  | 1 | 3 | 3
38 |  | Finance/ GEL | Chris Neale / Kevin O'Leary |  | The cost of LAC mobilisation exceeds budget allowed for in business case |  | Not enough money to mobilise the service | Financial | Closed | 3 | 3 | 9 | Ongoing monitoring of LAC mobilisation budget by PM and Steering group | on going | Budget has been part of the Cabinet report, there could be possible alterations , project team are working to keep this as close to the Cabinet report budget as possible | 2020-06-12 |  | 1 | 3 | 3
40 |  | HR/GEL | Unknown(recruitment process underway) / Kevin O'Leary |  | Change of upheaval |  | Staff morale Low, work not completed to standard | Reputation | Closed | 3 | 3 | 9 | staff consultation in adavance along with Union discussions to reduce possible service disruption | on going | HR & GEL have begun dialog with TU and will begin dialog with Amey in the new year to keep staff informed of the changes | 2020-06-12 |  | 1 | 3 | 3
49 |  | HR/GEL | Unknown(recruitment process underway) / Kevin O'Leary |  | Commercial waste disruptions if we do not collect on time (Economic) |  | Vehicles & staff with knowledge if not available day one will disrupt services | Reputation | Closed | 3 | 3 | 9 | Create commerical waste round, Maps, details etc. in advance have Agency on standby to support with staff requriements have data ready for incab | on going | Early discussions witrh Amey RE real TUPE data so GEL have enough time to recruit roles | 2020-06-12 |  | 1 | 3 | 3
51 |  | Procurement | Sarah Hadland/John Arnold |  | Co2 emissions |  | Effects on climate change, also cost with LEZ | Environmental | Closed | 3 | 3 | 9 | Fleet needs to be either electric, hybrid, bio fuel, or minimum of Euro VI engines (fleet will be a combination of Electric & Euro VI) | 01.08.2019 | All vehicles are Euro 6 and where we could buy electric we have | 2020-06-12 |  | 1 | 3 | 3
53 |  | HR/GEL | Sharon Brown/ Kevin O'Leary |  | Staff choose not to TUPE transfer and the service cannot operate fully on day one |  | Cannot carry out service | Technical | Closed | 1 | 5 | 5 | An agency contingency plan can be built into the programme plan. | 30.04.2019 | Agency currently being sorced via procurement routes we a also in dialog with Amey I.E TUPE request information and have a pre Go live worksheet for Amey to fill in RE pre booked leave for Go live/ LT & ST sickness and absence | 2020-06-12 |  | 1 | 3 | 3
55 |  | Depot | Nishant B |  | Depots not live |  | Cannot use the current depots on day one | Technical | Closed | 1 | 5 | 5 | alternative depot or storage location for vehicles required within Ealing or close to Ealing as possible | on going | There is a depot plan to make sure the roof no longer has broken asbestos/ the heating is fixed. The other areas are in a workable state and can be upgraded over time | 2020-06-12 |  | 1 | 3 | 3
56 |  | GEL | John Arnold |  | Maps route etc in place |  | Round maps, not completed not all scheudled work is carried out to agreed service spec | Technical | Closed | 1 | 5 | 5 | Agree with Amey no changes to rounds for the last 3 month of contract all maps can be produced by the month before go live | 30.06.2020 | GEL have ameys exsiting route data fromApr 20 GEL will work with Amey closely on de- mob including creating round maps to be used as a back up (crew folders) | 2020-06-12 |  | 1 | 3 | 3
59 |  | HR/GEL | Sharon Brown/ Kevin O'Leary |  | WAMITAB holder for HWRC (Derek) |  | Current WAMITAB holder does not come across | Technical | Closed | 1 | 5 | 5 | Speak to WLW see if they can step in temporary or speak to a consultancy firm for temp support | on going | This falls within the TUPE transfer and is being reviewed along side the early request of data | 2020-06-12 |  | 3 | 1 | 3
60 |  | LBE | Ed Axe? |  | Property costs condition surveys |  | Unforseen cost to make sure properties are running in a safe condition | Technical | Closed | 1 | 5 | 5 | condition survey 6 months in advance to calculate any repairs which maybe required. | on going | This falls within the wider Depot plans and project for regen . The GEL requirements have been listed and are being worked on | 2020-06-12 |  | 1 | 3 | 3
61 |  | LBE/GEL | Earl McKenzie / Kevin O'Leary |  | Recycling rates could drop due to disruptions |  | Council may not reach its target of 60% recycling rate by 2022 | Environmental | Active | 1 | 5 | 5 | Vehicle famialirsation training in advance as well as staff inductions within 3 months of go live to reduce impact on service | 30.06.2020 | contamination levels will be closely monitored by GEL & LBE to recude the outcome of disruption . If the service is behind the recycling will still be collected which should nto impact yearly targets | 2020-06-12 |  | 1 | 3 | 3
64 |  | GEL/ Legal | Kevin O'Leary /Helen Harris |  | Waste carriers licence for LATCO |  | No licence the LATCO cannot pick up or transport any waste (no service) | Technical | Closed | 3 | 5 | 15 | Can register online, (6 - 3 months in advance for LATCO) £160 cost, need names and dates of birth of the organisation’s executives, owners, directors or partners details of any environmental offences they’ve committed | 30.1.2020 | 6/1/2020 Helen confirmed Alison Reynolds formally appointed Director and registered with Companies House 3/1/2020, and Ross going to resign this week. Dec 2019 was waiting for Helen Haris Director of Legal to update GEL's company house with relevant director information so we can apply for the waste carriers licence | 2020-06-12 |  | 1 | 1 | 1
65 |  | Procurement | Sarah Hadland/John Arnold |  | Management of H&S |  | The services provided can be dangerous and the Health and Safety regime is critical to ensuring the safety of both staff and the general public; | Technical | Closed | 3 | 5 | 15 | The H&S system used by Ealing council will also be used by the LATCO (alcumas) | 01.10.2019 | Alcumus has been chosen as the H&S system their contract is currently being reviewed by Legal and Procurement once agreed and signed Alcumus will begin building the system for GEL approx time of completion 12 -15 weeks | 2020-06-12 |  | 1 | 1 | 1
66 |  | HR/GEL | Sharon Brown/ Kevin O'Leary |  | non recruitment of HR role for GEL |  | Outstanding set up tasks needs TUPE expert | Technical | Closed | 3 | 5 | 15 | Use LBE support may have to pay for consultancy | 01.12.2019 | recrutiment has begun for this position and other Key positions required expected start date Feb 20 | 2020-06-12 |  | 1 | 1 | 1
67 |  | LBE Street Services/ GEL | Earl McKenzie/ Kevin O'Leary |  | The new operation will require a strong and experienced depot manager with experience of operating these services. The depot is a potential pinchpoint in effective operations |  | Poor service delivery | Technical | Closed | 3 | 3 | 9 | Interim resource could be employed to cover | Post project | Kevin O'Leary and LBE to interview candidates to fill postion when required | 2020-06-12 |  | 1 | 1 | 1
69 |  | GEL/COMMS | Kevin O'Leary/ Keith Leiws |  | Branding wrong smear the LACTO name/ council issues. |  | LATCO looks unprofessional in its approach | Reputation | Closed | 1 | 5 | 5 | Get branding samples 6 months in advance of go live to check. | Post-project | Logo has been chosen, depending on vehicle situation I.E delivery etc. we are likley to stagger the Livery for vehicles over the first month. Staff will have the correct Logo on their PPE | 2020-06-12 |  | 1 | 1 | 1
70 |  | GEL | Kevin O'Leary /John Arnold |  | ABP licence |  | Animal By Product licence (currently free) required for collection of comerical food waste can be used to cover all food rounds | Technical | Closed | 1 | 5 | 5 | Apply in advance ( 6months) for new service, check 1 year in advance Amey current set up for washing food waste vehicles. | Post project | GEL will not be collecting food waste form commercial properties to begin with and can apply for the licence once vehicle washing arrangementshave been agreed. | 2020-06-12 |  | 1 | 1 | 1
71 |  | Procurement | Sarah Hadland/John Arnold |  | Suppliers for materials cleansing sacks, brushes barrows etc. |  | No tools or materials disrupts cleansing & GM services | Technical | Closed | 1 | 5 | 5 | Agree price and have tools brought and delivered 6 months in advance will require storage maybe a lock up in Greenford? | 30.04.2020 | Procureing via frameworks, mini comps will be held to make sure this is fair . Mini comps to start Jan 20 leaving enough time for delivery of required equipment | 2020-06-12 |  | 1 | 1 | 1
72 |  | LBE | Earl McKenzie |  | EA conditonal licence (Environmental Permitting Regulations – Waste Operations for England) |  | Cannot operate the HWRC sites within Ealing | Environmental | Closed | 1 | 5 | 5 | EP3896NF/V002 (Greenford 2011 Permit) EP3996NZ/A001 (Acton 1994 permit) |  | already with Ealing | 2020-06-12 |  | 1 | 1 | 1
73 |  | LBE | Earl McKenzie |  | CA site licence depot to carry out HWRC services and to park vehicles |  | Required to carry out HWRC services (this currently is with the council) | Technical | Closed | 1 | 1 | 1 | Keep with Council |  | already with Ealing | 2020-06-12 |  | 1 | 1 | 1
75 |  | Depot | Gauri Thakur |  | Project work could be delayed or stopped due to issues relating to the Corona virus and availability of Project Resources |  | There could be possible delay in deliverables | Environmental | Active | 3 | 3 | 9 | Daily meetings and announcements are in place to advise onnext steps, possible WFH measures introduced. GEL will be informed in case any planned activities gets impacted due to this |  | Close tracking of the situation and regular announcement | 2020-06-12 |  | 3 | 3 | 9 | br
76 | [11 empty] | 0 | [7 empty] | 0
77 | [11 empty] | 0 | [7 empty] | 0
78 | [11 empty] | 0 | [7 empty] | 0
79 | [11 empty] | 0 | [7 empty] | 0
80 | [11 empty] | 0 | [7 empty] | 0
81 | [11 empty] | 0 | [7 empty] | 0
82 | [11 empty] | 0 | [7 empty] | 0
83 | [11 empty] | 0 | [7 empty] | 0
84 | [11 empty] | 0 | [7 empty] | 0
85 | [11 empty] | 0 | [7 empty] | 0
86 | [11 empty] | 0 | [7 empty] | 0
87 |  |  |  |  | s | [6 empty] | 0 | [7 empty] | 0
88 | [11 empty] | 0 | [7 empty] | 0
89 | [11 empty] | 0 | [7 empty] | 0
90 | [11 empty] | 0 | [7 empty] | 0
91 | [11 empty] | 0 | [7 empty] | 0
92 | [11 empty] | 0 | [7 empty] | 0
93 | [11 empty] | 0 | [7 empty] | 0
94 | [11 empty] | 0 | [7 empty] | 0
95 | [11 empty] | 0 | [7 empty] | 0
96 | [11 empty] | 0 | [7 empty] | 0
97 | [11 empty] | 0 | [7 empty] | 0
98 | [11 empty] | 0 | [7 empty] | 0
99 | [11 empty] | 0 | [7 empty] | 0
100 | [11 empty] | 0 | [7 empty] | 0
101 | [11 empty] | 0 | [7 empty] | 0
102 | [11 empty] | 0 | [7 empty] | 0
103 | [11 empty] | 0 | [7 empty] | 0
104 | [11 empty] | 0 | [7 empty] | 0
105 | [11 empty] | 0 | [7 empty] | 0
106 | [11 empty] | 0 | [7 empty] | 0
107 | [11 empty] | 0 | [7 empty] | 0
108 | [11 empty] | 0 | [7 empty] | 0
109 | [11 empty] | 0 | [7 empty] | 0
110 | [11 empty] | 0 | [7 empty] | 0
111 | [11 empty] | 0 | [7 empty] | 0
112 | [11 empty] | 0 | [7 empty] | 0
113 | [11 empty] | 0 | [7 empty] | 0
114 | [11 empty] | 0 | [7 empty] | 0
115 | [11 empty] | 0 | [7 empty] | 0
116 | [11 empty] | 0 | [7 empty] | 0
117 | [11 empty] | 0 | [7 empty] | 0
118 | [11 empty] | 0 | [7 empty] | 0
119 | [11 empty] | 0 | [7 empty] | 0
120 | [11 empty] | 0 | [7 empty] | 0
121 | [11 empty] | 0 | [7 empty] | 0
122 | [11 empty] | 0 | [7 empty] | 0
123 | [11 empty] | 0 | [7 empty] | 0
124 | [11 empty] | 0 | [7 empty] | 0
125 | [11 empty] | 0 | [7 empty] | 0
126 | [11 empty] | 0 | [7 empty] | 0
127 | [11 empty] | 0 | [7 empty] | 0
128 | [11 empty] | 0 | [7 empty] | 0
129 | [11 empty] | 0 | [7 empty] | 0
130 | [11 empty] | 0 | [7 empty] | 0
131 | [11 empty] | 0 | [7 empty] | 0
132 | [11 empty] | 0 | [7 empty] | 0
133 | [11 empty] | 0 | [7 empty] | 0
134 | [11 empty] | 0 | [7 empty] | 0
135 | [11 empty] | 0 | [7 empty] | 0
136 | [11 empty] | 0 | [7 empty] | 0
137 | [11 empty] | 0 | [7 empty] | 0
138 | [11 empty] | 0 | [7 empty] | 0
139 | [11 empty] | 0 | [7 empty] | 0
140 | [11 empty] | 0 | [7 empty] | 0
141 | [11 empty] | 0 | [7 empty] | 0
142 | [11 empty] | 0 | [7 empty] | 0
143 | [11 empty] | 0 | [7 empty] | 0
144 | [11 empty] | 0 | [7 empty] | 0
145 | [11 empty] | 0 | [7 empty] | 0
146 | [11 empty] | 0 | [7 empty] | 0
147 | [11 empty] | 0 | [7 empty] | 0
148 | [11 empty] | 0 | [7 empty] | 0
149 | [11 empty] | 0 | [7 empty] | 0
150 | [11 empty] | 0 | [7 empty] | 0
151 | [11 empty] | 0 | [7 empty] | 0
*Need to identify whether risks apply to options assessment process or option implementation.

## Closed risks
Project Name | Transfer of Environmental Services
Risk Identification | [7 empty] | Assessment |  |  | Risk Management |  |  |  |  | Residual Risk Assessment |  |  | Contingency Strategy
Risk Number | Date Added | WORKSTREAM | Risk Description* | Risk Owner | Effect | Category (source of risk) | Status | Probability | Impact | Rating (RYG) | Potential Mitigation | Date By | Management Actions Taken | Date Updated | Comments | Probability | Impact | Rating (RYG) | Action undertaken if risk occurs
3 |  | Finance | Chris Neale | Skill set required business world build |  | Finance require dedicated resource to develop the end to end solution from the financial delivery alone, to meet the necessary timescales. Ability to define the process and solution in the absence of the business doing it themselves to timescales crucial.Chart of Accounts and associated reporting, structures and rules will take 6 weeks minimum for the right skill set. This is only part of the Financial solution for LATCO. For this skill Finance do have Margaret Donaldson and Shabana Kausar, in addition to John Parmenter, but crucially not with their current work load. | Financial | Closed | 5 | 5 | 25 | (9/12 request JA update 'Need a dedicated resource to assist with BW design John Parmenter was going to be that resource but reuqires a new contract ASAP his contract runs out 01.08.2019 if John Parmenter is given a contract the project timeline and costs from ICT are likley to be the same as forcasted') | 01.08.2019 | Contract issued by finance to John Parmenter who will continue working on the project | 01.08.2019 |  | 1 | 1 | 1
127 | [9 empty] | 0 | [7 empty] | 0
128 | [9 empty] | 0 | [7 empty] | 0
129 | [9 empty] | 0 | [7 empty] | 0
130 | [9 empty] | 0 | [7 empty] | 0
131 | [9 empty] | 0 | [7 empty] | 0
132 | [9 empty] | 0 | [7 empty] | 0
133 | [9 empty] | 0 | [7 empty] | 0
134 | [9 empty] | 0 | [7 empty] | 0
135 | [9 empty] | 0 | [7 empty] | 0
136 | [9 empty] | 0 | [7 empty] | 0
137 | [9 empty] | 0 | [7 empty] | 0
138 | [9 empty] | 0 | [7 empty] | 0
139 | [9 empty] | 0 | [7 empty] | 0
140 | [9 empty] | 0 | [7 empty] | 0
141 | [9 empty] | 0 | [7 empty] | 0
142 | [9 empty] | 0 | [7 empty] | 0
143 | [9 empty] | 0 | [7 empty] | 0
144 | [9 empty] | 0 | [7 empty] | 0
145 | [9 empty] | 0 | [7 empty] | 0
146 | [9 empty] | 0 | [7 empty] | 0
147 | [9 empty] | 0 | [7 empty] | 0
148 | [9 empty] | 0 | [7 empty] | 0
149 | [9 empty] | 0 | [7 empty] | 0
150 | [9 empty] | 0 | [7 empty] | 0
151 | [9 empty] | 0 | [7 empty] | 0
*Need to identify whether risks apply to options assessment process or option implementation.

## Procurement risks (hidden)
Project Name | Transfer of Environmental Services
Risk Identification | [6 empty] | Assessment |  |  | Risk Management |  |  |  |  | Residual Risk Assessment |  |  | Contingency Strategy
Risk Number | Date Added | Risk Description* | Risk Owner | Effect | Category (source of risk) | Status | Probability | Impact | Rating (RYG) | Potential Mitigation | Date By | Management Actions Taken | Date Updated | Comments | Probability | Impact | Rating (RYG) | Action undertaken if risk occurs
1 |  | LAC is not established in time to carry out service |  | Cannot carry out service | Reputation |  | 1 | 5 | 5 | Mobilisation resource planning required |  |  |  |  | 1 | 5 | 5
3 |  | LAC do not have the appropriate polices and procedures in place to operate a safe operational service causing injury to staff or members of the public |  | Cannot carry out service | Reputation |  | 1 | 5 | 5 | Mobilisation resource planning required |  |  |  |  | 1 | 5 | 5
4 |  | LAC does not have the appropriate business processes in place to ensure the effective delivery of the service causing a decrease in service standards and impacting on Ealing Council reputation |  | Cannot carry out service | Reputation |  | 1 | 5 | 5 | Develop business processes to form part of the ICT service specification |  |  |  |  | 1 | 5 | 5
5 |  | LAC Staff are not paid on first payroll and therefore service is not delivered |  | Cannot carry out service | Technical |  | 1 | 5 | 5 | Discuss requirements with payroll as part of plan and ensure all timelines are understood, with support provided at first payroll |  |  |  |  | 1 | 5 | 5
6 |  | Key members of the Amey operational team did not TUPE transfer leaving a knowledge gap amongst staff |  | Day one operational continuity impacted | Technical |  | 3 | 3 | 9 | Contingency plans to be put in place through the use of the mobilisation team to bed in service. |  |  |  |  | 3 | 1 | 3
7 |  | Transferring staff have not received suitable induction and therefore cannot carry out the service |  | Cannot carry out service | Technical |  | 1 | 5 | 5 | A training and induction plan can be built into the programme plan |  |  |  |  | 1 | 5 | 5
8 |  | Staff choose not to TUPE transfer and the service cannot operate fully on day one |  | Cannot carry out service | Technical |  | 1 | 5 | 5 | An agency contingency plan can be built into the programme plan. |  |  |  |  | 1 | 5 | 5
9 |  | ICT systems are not developed in time for new service causing significant issues in dealing with customer requests |  | Poor service for residents | Technical |  | 3 | 3 | 9 | Early engagement with ICT and ICT to form part of Steering Group |  |  |  |  | 1 | 3 | 3
10 |  | Amey relationship breakdown making mobilisation problematic and service inherited very poor. |  | LAC inherit significant service issues | Technical |  | 3 | 3 | 9 | LBE team continue engagement with Amey and monitor contract performance |  |  |  |  | 1 | 3 | 3
11 |  | The new operation will require a strong and experienced depot manager with experience of operating these services. The depot is a potential pinchpoint in effective operations |  | Poor service delivery | Technical |  | 3 | 3 | 9 | Interim resource could be employed to cover |  |  |  |  | 1 | 3 | 3
12 |  | The cost of LAC mobilisation exceeds budget allowed for in business case |  | Not enough money to mobilise the service | Financial |  | 3 | 3 | 9 | Ongoing monitoring of LAC mobilisation budget by PM and Steering group |  |  |  |  | 1 | 3 | 3
13 |  | The cost of LAC exceeds business case due to unforeseen costs |  | Financial business case for change undermined | Financial |  | 1 | 5 | 5 | Ongoing review of business case by Steering Group with contact with DoF |  |  |  |  | 1 | 5 | 5
14 |  | Brexit |  | labour shortage and costs go up | Financial |  | 3 | 5 | 15 | reduce specs on cleansing and GM further to make sure a waste service runs |  |  |  |  | 1 | 5 | 5
15 |  | Brexit |  | Timelines for vehicles & costs of vehicles increase | Financial |  | 3 | 5 | 15 | negotiate a fixed price with suppliers before March 2019 (now Jan 2020) |  |  |  |  | 1 | 5 | 5
16 |  | Brexit |  | Subcontractor/materials/supplier cost increase | Financial |  | 3 | 5 | 15 | negotiate a fixed price with suppliers before March 2019 (now Jan 2020). Use existing LBE contracts which have fixed prices for materials where possible. |  |  |  |  | 1 | 5 | 5
17 |  | Brexit |  | Repairs & maintenance costs increase | Financial |  | 3 | 5 | 15 | negotiate a fixed price with suppliers before March 2019 (now Jan 2020) through competitive procurement process with fixed inflationary increases. |  |  |  |  | 1 | 5 | 5
18 |  | Brexit |  | Pressure to produce savings increase | Financial |  | 3 | 5 | 15 | negotiate a fixed price with suppliers before March 2019 (now Jan 2020) |  |  |  |  | 1 | 5 | 5
19 |  | Brexit |  | Changes to taxation | Financial |  | 3 | 5 | 15 | negotiate a fixed price with suppliers before March 2019 (now Jan 2020) |  |  |  |  | 1 | 5 | 5
20 |  | Brexit |  | Fuel costs increase | Financial |  | 3 | 5 | 15 | negotiate a fixed price with suppliers before March 2019 (now Jan 2020) |  |  |  |  | 1 | 5 | 5
21 |  | Brexit |  | Change in pricing | Financial |  | 3 | 5 | 15 | negotiate a fixed price with suppliers before March 2019 (now Jan 2020) |  |  |  |  | 1 | 5 | 5
22 |  | No financial system in place for day one |  | Staff not paid = stike action & reputaional damage | Financial |  | 1 | 5 | 5 | Have a back up payment method (Itrent) for first 3 months payments with all LATCO info while LATCO financial system is agreed |  |  |  |  | 1 | 1 | 1
24 |  | Change of upheaval |  | Staff morale Low, work not completed to standard | Reputation |  | 3 | 3 | 9 | staff consultation in adavance along with Union discussions to reduce possible service disruption |  |  |  |  | 1 | 3 | 3
25 |  | Branding wrong smear the LACTO name/ council issues. |  | LATCO looks unprofessional in its approach | Reputation |  | 1 | 5 | 5 | Get branding samples 6 months in advance of go live to check. Ensure branding is provided to PPE/uniform supplier well in advance of required 'drop dead' date for uniform and PPE orders. |  |  |  |  | 1 | 1 | 1
26 |  | Workforce numbers lower than required (sick, Holiday, absent) |  | full service does not run day one | Technical |  | 3 | 5 | 15 | Agency suppliers on board for 1st month. Agency suppliers to have recruirment plans in place. |  |  |  |  | 1 | 5 | 5
27 |  | Vehicles/Plant/equipment |  | Not all ready to go live on day one | Technical |  | 3 | 5 | 15 | Have an agreement ready with hire company for go live procurment of hire contract curerntly in progress |  |  |  |  | 1 | 5 | 5
|  | Vehicle costs |  | 10-12% increase in price because of Brexit | Financial |  | 3 | 5 | 15 | Place orders as soon as possible to fix prices. Hold contingency for potential price increases if UK leaves EU with no deal (WTO tarrif increases) |  |  |  |  | 1 | 5 | 5
28 |  | ICT |  | ICT software not not up and running day one | Technical |  | 1 | 5 | 5 | back up system? Can Contender be used as temp? |  |  |  |  | 1 | 5 | 5
29 |  | Depots not live |  | cannot use the current depots on day one | Technical |  | 1 | 5 | 5 | alternative depot or storage location for vehicles required within Ealing or close to Ealing as possible |  |  |  |  | 1 | 3 | 3
30 |  | Maps route etc in place |  | round maps, not completed not all scheudled work is carried out to agreed service spec | Technical |  | 1 | 5 | 5 | Agree with Amey no changes to rounds for the last 3 month of contract all maps can be produced by the month before go live |  |  |  |  | 1 | 3 | 3
31 |  | HGV drivers , knowledge transfer GM skills shortage commercial waste knowledge |  | skills shortage from day one resulting in service disruption | Technical |  | 3 | 5 | 15 | Agency suppliers on board for 1st month |  |  |  |  | 1 | 5 | 5
32 |  | WAMITAB holder for HWRC (Derek) |  | current WAMITAB holder does not come across | Technical |  | 1 | 5 | 5 | Speak to WLW see if they can step in temporary or speak to a consultancy firm for temp support |  |  |  |  | 3 | 1 | 3
33 |  | O Licence holders |  | without O Licence no vehicle over 3.5t can leave the depot | Technical |  | 3 | 5 | 15 | need a min of 2 for number of fleet, if use Harrow they can supply X2 Transport managers. If we own the vehicles we should recruit in advance for those roles as exsiting staff could be used in other positions. |  |  |  |  | 1 | 5 | 5
34 |  | ABP licence |  | Animal By Product licence (currently free) required for collection of comerical food waste can be used to cover all food rounds | Technical |  | 1 | 5 | 5 | Apply in advance ( 6months) for new service, check 1 year in advance Amey current set up for washing food waste vehicles. |  |  |  |  | 1 | 1 | 1
35 |  | Management and running of workshops |  | Need to identfy key personal that need to transfer Workshops Nick Wilson currently runs Greenford workshop | Technical |  | 3 | 5 | 15 | Negotiate with Amey advance TUPE (6months) for those that wish to come to LATCO Key postions or for split time between Amey and LATCO 50/50 split. If not recruit position 3 months in advance |  |  |  |  | 1 | 5 | 5
36 |  | H&S Risk assessments and SSOW not ready for day one. |  | No RRRA or SSOW for day one resulting in unsfae workforce | Technical |  | 3 | 5 | 15 | Negotiate with Amey advance TUPE (6months) for those that wish to come to LATCO Key postions or for split time between Amey and LATCO 50/50 split. If not recruit position 3 months in advance |  |  |  |  | 1 | 5 | 5 |  | Need to identfy key personal that need to transfer for H&S Sandra Hewyey is currently OSA (Operational Safety Advisor)
37 |  | Waste carriers licence for LATCO |  | No licence the LATCO cannot pick up or transport any waste (no service) | Technical |  | 3 | 5 | 15 | Can register online, (6 - 3 months in advance for LATCO) £160 cost, need names and dates of birth of the organisation’s executives, owners, directors or partners details of any environmental offences they’ve committed |  |  |  |  | 1 | 1 | 1
38 |  | CA site licence depot to carry out HWRC services and to park vehicles |  | required to carry out HWRC services (this currently is with the council) | Technical |  | 1 | 1 | 1 | Keep with Council |  |  |  |  | 1 | 1 | 1
40 |  | Suppliers for materials cleansing sacks, brushes barrows etc. |  | No tools or materials disrupts cleansing & GM services | Technical |  | 1 | 5 | 5 | agree price and have tools brought and delivered 6 months in advance will require storage maybe a lock up in Greenford? |  |  |  |  | 1 | 1 | 1
49 |  | Commercial waste disruptions if we do not collect on time (Economic) |  | vehicles & staff with knowledge if not available day one will disrupt services | Reputation |  | 3 | 3 | 9 | Create commerical waste round, Maps, details etc. in advance have Agency on standby to support with staff requriements have data ready for incab |  |  |  |  | 1 | 3 | 3
51 |  | Property costs condition surveys |  | unforseen cost to make sure properties are running in a safe condition | Technical |  | 1 | 5 | 5 | condition survey 6 months in advance to calculate any repairs which maybe required. |  |  |  |  | 1 | 3 | 3
53 |  | Co2 emissions |  | effects on climate change, also cost with LEZ | Environmental |  | 3 | 3 | 9 | fleet needs to be either electric, hybrid, bio fuel, or minimum of Euro VI engines (fleet will be a combination of Electric & Euro VI) |  |  |  |  | 1 | 3 | 3
54 |  | weed control chemical usage (Glyphosate) |  | Legislation could change banning the use of Glyphosate as has Carcinogenic properties | Environmental |  | 3 | 3 | 9 | Can use foam treatment (coconut oil and other natrual treatments costs more) Glyphosate section in Buisness plan where cabinet can choose) |  |  |  |  | 1 | 5 | 5
55 |  | Recycling rates could drop due to disruptions |  | the council may not reach its target of 60% recycling rate by 2022 | Environmental |  | 1 | 5 | 5 | Vehicle famialirsation training in advance as well as staff inductions within 3 months of go live to reduce impact on service |  |  |  |  | 1 | 3 | 3
56 |  | Climate change snow and ice… |  | disruption of services | Environmental |  | 5 | 5 | 25 | increase recycling rate & lower carbon emmisons |  |  |  |  | 1 | 1 | 1
57 |  | Check legislation changes |  | Possible changes forcing sort separate collections | Environmental |  | 3 | 5 | 15 | Lease some vehicles as changes will affect methodolgy & collection plan to reduce cost implications needs to be under 2 years |  |  |  |  | 3 | 3 | 9
59 |  | EA conditonal licence (Environmental Permitting Regulations – Waste Operations for England) |  | Cannot operate the HWRC sites within Ealing | Environmental |  | 1 | 5 | 5 | EP3896NF/V002 (Greenford 2011 Permit) EP3996NZ/A001 (Acton 1994 permit) |  |  |  |  | 1 | 1 | 1
60 |  | Non support from Amey during last three months |  | transistion of services becomes disrupted | Reputation |  | 3 | 3 | 9 | agree in writing in advance (2019) support requirements from Amey and any cost implications |  |  |  |  | 1 | 3 | 3
61 |  | Skill set required business world build |  | Finance require dedicated resource to develop the end to end solution from the financial delivery alone, to meet the necessary timescales. Ability to define the process and solution in the absence of the business doing it themselves to timescales crucial.Chart of Accounts and associated reporting, structures and rules will take 6 weeks minimum for the right skill set. This is only part of the Financial solution for LATCO. For this skill Finance do have Margaret Donaldson and Shabana Kausar, in addition to John Parmenter, but crucially not with their current work load. | Financial |  | 5 | 5 | 25 | Need a dedicated resource to assist with BW design John Parmenter was going to be that resource but reuqires a new contract ASAP his contract runs out 01.08.2019 if John Parmenter is given a contract the project timeline and costs from ICT are likley to be the same as forcasted |  |  |  |  | 3 | 1 | 3
64 |  | Tax & VAT |  | The LATC by definition will be subject to Corporation Tax unless it is structured in such a way as to be exempt. There could be significant implications and financial penalties if this or the way the company accounts for VAT are not correct. | Financial |  | 3 | 5 | 15 | GEL will have to comply with Making Tax digital this is being reviewed by I-trent and BW development groups |  |  |  |  | 1 | 5 | 5
65 |  | Pensions |  | The LATC will TUPE staff who were transferred to EMS when the contract was originally let as well as staff that have been employed subsequently and new staff once the LATC is operational. There will need to be pension provision in place for all of these staff. The company will need to gain admitted body status and provide a pension option for new staff. | Financial |  | 3 | 5 | 15 | Identified 17 staff who will have admitted body status for the LGPS pension the remaining staff will be included in a NEST scheme pension |  |  |  |  | 1 | 3 | 3
66 |  | Licences |  | There are a significant number of licences that need to be in place before the LATC can operate the services. | Legal |  | 3 | 5 | 15 | Licences required, Waste carriers licence, O licence, ABP licence |  |  |  |  | 1 | 1 | 1
67 |  | Management of H&S |  | The services provided can be dangerous and the Health and Safety regime is critical to ensuring the safety of both staff and the general public; | Technical |  | 3 | 5 | 15 | The H&S system used by Ealing council will also be used by the LATCO (alcumas) |  |  |  |  | 1 | 1 | 1
68 |  | H&S Risk assessments and SSOW not ready for day one. |  | No RRRA or SSOW for day one resulting in unsfae workforce | Technical |  | 3 | 5 | 15 | We have collated the exsiting H&S information from Amey and are reviewing to see if fit for purpose we aim to work alongside the H&S manager from Amey who will TUPE across as well as Ealing Council's H&S team to have these in place for day one. | [6 empty] | 0
69 |  | Not having the information from Amey (Due ) |  | People not paid on day one | Financial |  | 3 | 5 | 15 | Have dialog with Amey up to last day to make sure information is correct |  |  |  |  | 1 | 3 | 3
70 |  | Unknown claims against staff, Tribuneral, injury |  | we end up with the costs | Financial |  | 5 | 5 | 25 | Request all information in advance and keep dialog open with amey up to last day for any outstanding claims |  |  |  |  | 1 | 3 | 3
71 |  | non recruitment of HR role for GEL |  | outstanding set up tasks needs TUPE expert | Technical |  | 3 | 5 | 15 | Use LBE support may have to pay for consultancy |  |  |  |  | 1 | 3 | 3
72 | [8 empty] | 0 | [7 empty] | 0
73 | [8 empty] | 0 | [7 empty] | 0
74 | [8 empty] | 0 | [7 empty] | 0
75 | [8 empty] | 0 | [7 empty] | 0
76 | [8 empty] | 0 | [7 empty] | 0
77 | [8 empty] | 0 | [7 empty] | 0
78 | [8 empty] | 0 | [7 empty] | 0
79 | [8 empty] | 0 | [7 empty] | 0
80 | [8 empty] | 0 | [7 empty] | 0
81 | [8 empty] | 0 | [7 empty] | 0
82 | [8 empty] | 0 | [7 empty] | 0
83 | [8 empty] | 0 | [7 empty] | 0
84 | [8 empty] | 0 | [7 empty] | 0
85 | [8 empty] | 0 | [7 empty] | 0
86 | [8 empty] | 0 | [7 empty] | 0
87 |  | s | [6 empty] | 0 | [7 empty] | 0
88 | [8 empty] | 0 | [7 empty] | 0
89 | [8 empty] | 0 | [7 empty] | 0
90 | [8 empty] | 0 | [7 empty] | 0
91 | [8 empty] | 0 | [7 empty] | 0
92 | [8 empty] | 0 | [7 empty] | 0
93 | [8 empty] | 0 | [7 empty] | 0
94 | [8 empty] | 0 | [7 empty] | 0
95 | [8 empty] | 0 | [7 empty] | 0
96 | [8 empty] | 0 | [7 empty] | 0
97 | [8 empty] | 0 | [7 empty] | 0
98 | [8 empty] | 0 | [7 empty] | 0
99 | [8 empty] | 0 | [7 empty] | 0
100 | [8 empty] | 0 | [7 empty] | 0
101 | [8 empty] | 0 | [7 empty] | 0
102 | [8 empty] | 0 | [7 empty] | 0
103 | [8 empty] | 0 | [7 empty] | 0
104 | [8 empty] | 0 | [7 empty] | 0
105 | [8 empty] | 0 | [7 empty] | 0
106 | [8 empty] | 0 | [7 empty] | 0
107 | [8 empty] | 0 | [7 empty] | 0
108 | [8 empty] | 0 | [7 empty] | 0
109 | [8 empty] | 0 | [7 empty] | 0
110 | [8 empty] | 0 | [7 empty] | 0
111 | [8 empty] | 0 | [7 empty] | 0
112 | [8 empty] | 0 | [7 empty] | 0
113 | [8 empty] | 0 | [7 empty] | 0
114 | [8 empty] | 0 | [7 empty] | 0
115 | [8 empty] | 0 | [7 empty] | 0
116 | [8 empty] | 0 | [7 empty] | 0
117 | [8 empty] | 0 | [7 empty] | 0
118 | [8 empty] | 0 | [7 empty] | 0
119 | [8 empty] | 0 | [7 empty] | 0
120 | [8 empty] | 0 | [7 empty] | 0
121 | [8 empty] | 0 | [7 empty] | 0
122 | [8 empty] | 0 | [7 empty] | 0
123 | [8 empty] | 0 | [7 empty] | 0
124 | [8 empty] | 0 | [7 empty] | 0
125 | [8 empty] | 0 | [7 empty] | 0
126 | [8 empty] | 0 | [7 empty] | 0
127 | [8 empty] | 0 | [7 empty] | 0
128 | [8 empty] | 0 | [7 empty] | 0
129 | [8 empty] | 0 | [7 empty] | 0
130 | [8 empty] | 0 | [7 empty] | 0
131 | [8 empty] | 0 | [7 empty] | 0
132 | [8 empty] | 0 | [7 empty] | 0
133 | [8 empty] | 0 | [7 empty] | 0
134 | [8 empty] | 0 | [7 empty] | 0
135 | [8 empty] | 0 | [7 empty] | 0
136 | [8 empty] | 0 | [7 empty] | 0
137 | [8 empty] | 0 | [7 empty] | 0
138 | [8 empty] | 0 | [7 empty] | 0
139 | [8 empty] | 0 | [7 empty] | 0
140 | [8 empty] | 0 | [7 empty] | 0
141 | [8 empty] | 0 | [7 empty] | 0
142 | [8 empty] | 0 | [7 empty] | 0
143 | [8 empty] | 0 | [7 empty] | 0
144 | [8 empty] | 0 | [7 empty] | 0
145 | [8 empty] | 0 | [7 empty] | 0
146 | [8 empty] | 0 | [7 empty] | 0
147 | [8 empty] | 0 | [7 empty] | 0
148 | [8 empty] | 0 | [7 empty] | 0
149 | [8 empty] | 0 | [7 empty] | 0
150 | [8 empty] | 0 | [7 empty] | 0
151 | [8 empty] | 0 | [7 empty] | 0
*Need to identify whether risks apply to options assessment process or option implementation.