## MASTER (UPDATE weekly)
Workstream | Task/Milestone | Task owner | Planned start date | Required completion date | Actual start date | Status | Comments
Communications | Stakeholder survey | Verity | 2020-03-16 | 2020-05-01 | 2020-03-07 | Not started: delayed | 24/03/2020 (KRD): with senior management pre-occupied with the coronavirus response, it is not possible to set a required completion date.
Communications | Staff survey | Verity | 2020-03-17 | 2020-06-01 | 2020-03-17 | Not started: delayed | 14/04/20 (JA) Non Urgent due to COVID -19
Communications | Summary of the programme and what it acheievd | Verity | 2020-04-15 | 2020-07-31 | 2020-04-15 | in Progress
Communications | Non-executive directors depot tour | Verity |  |  |  | Not started: delayed | 14/04/20 (JA) Non Urgent due to COVID -19
Communications | Non-executive route tour | Verity |  |  |  | Not started: delayed | 14/04/20 (JA) Non Urgent due to COVID -19
Communications | Press briefings (external) | Vertiy | 2020-07-06 | 2020-07-10 |  | Not Started
Communications | Photo opps for vehicle deliveries | Vertiy | 2020-07-06 | 2020-07-10 |  | Not Started
Communications | Celebration event | Vertiy |  |  |  | Not started: delayed | 14/04/20 (JA) Non Urgent due to COVID -19
Communications | Signage | Vertiy | 2020-07-06 | 2020-07-31 | 2020-04-15 | in Progress | Need to deceide is it full signage or cover up. Discussions started
Communications | Brand guidelines | Vertiy | 2020-03-17 | 2020-04-30 | 2020-03-17 | in Progress | Print out are discussing with desginer
Communications | Develop specification | Vertiy |  |  |  | Not Started | If required subject to Row 325
Communications | Go out for tender | Verity |  |  |  | Not Started | If required subject to Row 325
Communications | stationery order | Verity | 2020-04-06 | 2020-04-30 | 2020-04-06 | in progress | With Print Out team and designers
Communications | livery designs | Verity | 2020-03-05 | 2020-05-29 | 2020-03-03 | in progress | Conversations had with Roadvert and Spectrum Signs
Communications | newsletter | Verity | 2020-04-21 | 2020-05-29 | 2020-04-21 | in progress | Decision on items for 1st edition to be made - 2 sided -emailed? Depends on info from tupe.
Communications | Around Ealing | Verity |  |  |  | Not Started | To Check the deadlines for AE
Communications | Receive approval from AMEY to conduct survey | Verity |  |  |  | Not started: delayed | 14/04/20 (JA) Non Urgent due to COVID -19
Communications | Establishing staff focus groups | Verity |  |  |  | Not started: delayed | 14/04/20 (JA) Non Urgent due to COVID -19
Finance | Interest rate determination on loan for state aid purposes | Chris Neale | 2019-11-27 | 2020-03-15 | 2019-10-01 | In progress: delayed | 9/4/2020 Chuhr wrote letter to TLT (as prior advisors re LATCO, not Gowling) requesting confirmation of legal advice re state aid not applying to main company and would only to a trading subsidiary if trading set up in future. 12/3/2020 Legal (Chuhr) confirmed they would send letter of instruction to Gowling in following week commencing 16/3/2020, to confirm not an issue re state aid for GEL as long as any future trading in subsidiary. 28/2/2020 Legal confirmed do not believe need comply with State Aid in GEL as trading can be done in subsidiary and in w/c 2/3 will instruct Gowlings to confirm, so this means may not need do lending at commercial rates. 27/2/20120 C confirmed should be able to do by same arrangement as Amey, with standard fixed amount invoiced at start of month, for payment within 2 weeks, before payroll, and non standard items the start of the following item. Legal (Jackie & Chuhr) 27/2/2020 confirmed that seemed fair risk share if needed to confirm a commercial arrangement. 24/2/2020 C sent requrest to Legal re questions and with quantification of issues, requesting meeting this week. Changed required completion date from 28/2 to 15/3/2020 18/2 C saw legal requesting they get advice since PwC not, nor Treasury's advisors LINK able to fullly cover 17/2 Bridget got 11% rate if no collateral 11/2 Await Bridget Uku getting state aid compliant interest rate 27/1/2020 Meeting of Corporate Finance deferred to 30/1 to discuss accounting treatment that might include this 17/1/2020 Meeting requested in Finance for Mon 27/1 re Lease Finance accounting at which will agree next steps for this. 10/1/2020 LINK agreed re lease finance to ensure quotes requested for funding LATCO direct also, so that covered. (Chris separately to look at documenting confirmation that interest rates on any council loans correct to avoid being state aid). 10/12/2019 Chris requested Tim and Sarah re the timing of this, following up request of 11/11, where requested that the quotes include leasing via the Council and also direct to LATCO to show the difference to be charged by Council to avoid providing state aid. 10/12/2019 Chris also followed with Peterborough LATCO re 10/11 request re the calculation of the state aid compliant interest on loans from the council KRD 27/11/2019 - What is involved to get this figure
Finance | Agree payment mechanism for LBE /GEL contract and arrangement between GEL and LBE | Chris Neale/ Shabana Kausar / Simon Peet | 2019-11-27 | 2020-03-15 | 2019-10-01 | Completed | 12/3/2020 Legal (Chuhr) confirmed they would send letter of instruction to Gowling in following week commencing 16/3/2020, to confirm not an issue re state aid for GEL as long as any future trading in subsidiary 28/2/2020 Legal confirmed do not believe need comply with State Aid in GEL as trading can be done in subsidiary and in w/c 2/3 will instruct Gowlings, and so payment can be as wished. So 24/2/2020 C confirmed that expected payment to be mid month, after invoice at start of month re standard costs for that month, and invoice at start of next month for any non regular items, as per Amey contract. 24/2/2020 C put written request again to Legal to get specialist advice on this, re payment at start of quarter, asking for meeting this week. Changed required delivery date from 15/2/2020 to 15/3/2020 17/2 Simon confirmed PwC unlikely to assist 11/2 Await still PwC replying on this. 27/1/2020 Meeting of Corporate Finance deferred to 30/1 to discuss accounting treatment that might include this 23/1/2020 Noted to Simon Peet that await answer and requested he get answer in next meeting with PwC. 6/1/2020 timescale of Jan not likely, however not absolutely nec till later 1/12/2019 Awaits SLA being further developed, to then progress
Finance | Accounts Payable SLA deliverable and volumes and KPIs | Liz Lyons | 2019-11-27 | 2020-01-31 | 2019-10-01 | Completed | 2/3/2020 John confirmed content re AP. 24/2/2020 changed Procurement lead from Georgia Hoare to Liz Lyons 28/1/2020 John A sending comments on agreement to Georgia and Liz re outstanding points in draft agreement provided. 13/1/2020 Georgia Hoare provided draft to John A, Chris and John P to confirm. 13/1/2020 Georgia Hoare confirmed would complete in next few days what possible now, conferring with John Parmenter where needed, and ensure note of what awaits further decisions, for her successor Liz. 7/1/2020 Georgia Hoare proposed would attend to Wed 8/1/2020 so completed this week. 6/1/2020 reminded Georgia Hoare. 10/12/2019 reminded Georgia Hoare re proforma given 27/11 to her so has info to complete 28/01/2020 (KRD): updated status to 'in progress: delayed'
Finance | Vehicle lease quotes | Chris and Sarah and Henry | 27/11/2019 | 30/4/2020 | 2020-02-11 | In progress | 8/04/2020 LINK has been advised to go ahead with issuing a tender 7/4/2020 C confirmed needing to check outstanding queries of LINK or Legal. 31/3/2020 have gone out to tender and various contractual issues being checked by legal 2/3/2020 John confirmed Robyn would revert with timings, this week, now having prior week given her the expected dates for delivery from April. 24/2/2020 John has prior week provided new delivery dates to LINK to start procuring lease finance. C asked LINK 24/2 to confirm when would have finance in place for first ones, and for note re pros and cons of council paying first for the leases, that 19/2 they said they would provide w/c 24/2. Changed required completion to 7/3/2020 from 28/2/2020 11/2 Still await update from Procurement and from Link, also have noted to John and Kevin that if need finance for vehicle delivery in April then Link and Procurement need know. 28/1/2020 Chris to ask Henry and Sarah for update on this, expect quotes later than 2/2/2020 as need to be close to delivery which is cMay-June. 10/1/2020 Meeting held by Tim with LINK to ensure handover to his successor and that LINK aware of what needed next. 7/1/2020 Chris noted meeting planned with Link 10/1/2020 10/12/2019 Chris requested Tim and Sarah provide their outline planned timetable
Finance | Insurance | Ewan Taylor | 2020-07-01 | 2020-07-01 | 2020-07-01 | In progress | 14/04/20 (JA) Ewan has stated he he will receive feedback from the tender WC 13.04.20 JA will ask for an update on Friday 31/3/2020 Insurance Cabinet report on agenda for May, included by Euan. 27/03/2020 (KRD) John Arnold waiting to hear back from Ewan Taylor on what is required on 30/03 4/3/2020 C asked John Arnold to update this if not Ewan, as they both the closest to this. 3/3/2020 C asked Darren provide update re getting new quotes for Greener Ealing as not provided within Council request for quote. 25/2/20 Ewan confirmed that 22/1/2020 did not receive any insurance bids that were viable and were going back to tenderers for separate quotes for Greener Ealing, and C asked Ewan and Killian to ensure way for more updates on this here. 25/2/2020 Requested update of Ewan re Council insurance contract. 11/2/2020 Still with John. 28/1/2020 the insurance of vehicles if used by Amey before GE is yet to be discussed with Amey. 8/1/2020 Mary confirmed for Kevin and John that insurance of new fleet subleased to Amey would need be via Amey's insurer. Rest of insurance procurement on track, for earlier awred 9/3/2020. 7/1/2020 Chris organised meeting of John and Kevin with Mary 8/1/20. 22/7/2019 Cabinet report authorised procurement, with 30/8/2019 Draft Tender Document, with 6/9/2019 Agree finalised tender specification, with 20/11/2019 Tenders back, with 21/2/2020 Final decision, 9/3/2020 Award Contract
Finance | Making Tax Digital | John Parmenter | 2020-02-26 | 2020-03-05 |  | Completed | 31/3/2020 Finance believe have provided all information required so green for Finance and deliverable is in ICT. 12/3/2020 C registered company for Corporation Tax and gave details to John Parmenter. 11/2/2020 Still with PwC. 29/1/2020 C seeking confirmation from PwC whether should be earlier.14/1/2020 confirmed on track, with main item required from HR Payroll, due in few weeks, and no items needed from Finance, next update planned for Wed 26/2. 8/1/2020 requested clarification meeting Tues 14/1/2020, James Pugh 9/1 noted main deliverable is from HR Payroll (not Finance) and the project manager that would invite to 14/1/2020 meeting 7/1/2020 John requested meeting including Georgia, John wishing to attend also 6/1/2020 Chris noted the request to John Parmenter 10/12/2019 Chris asked John P to confirm following note here 27/11/2019 - KRD asked Chris please specify dates
Finance | Register for VAT | Chris Neale | 2020-01-04 | 30/04/2020 | 2020-01-04 | In progress | 09/04/2020 GEL application for VAT registration submitted; registration number to be generated within 1-2 weeks 6/4/2020 Katarina registered 6/4 on HMRC website and preparing application to register for VAT. Trying to sort out registration details with Simon Peet and IT and PwC, and also from a Director to complete form. 31/3/2020 Shahzad asked for VAT returns by end April also, for testing MTD VAT software, will factor in that request into VAT registration request seeking to do this week. 12/3/2020 Greener Ealing registered for Corporation Tax, meaning some steps done making it easier for then re VAT. 24/2/2020 Simon seeking find another PwC advisor. 11/2 Still await from Simon. 30/1/2020 requested Simon request PwC for new advisor if Catherine cannot respond 23/1/2020 Chris requested Simon request PwC advice when seeing Mon 27/1 14/1/2020 agreed not likely to be before April 2020 need. 9/1/2020 C sent briefing to PwC requesting confirm if any other points on what council currently planning. 7/1/2020 agreed to discuss further with John Parmenter at 14/1/2020 making tax digital meeting. 10/12/2019- Chris requested dates from John Pamenter following up request of 23/10/2019 KRD 27/11/2019 - Chris please can you specify dates for this task 28/01/2020 (KRD): start date changed from 15/01/2020 to 01/04/2020
Finance | Finalise budget allocation per service | Chris Neale | 2019-12-02 | 2020-01-31 | 2019-12-02 | Completed | 28/1/2020 Chris shared file with Kevin and John, incl update re LLW from £10.55 to £10.75/hr 9/1/2020 Completed, though pre any refinement by service or further change re LLW. Chris to share file (copy viewable without links) 29/1/2020. JA 04/12/2019 -JA & CNe met 02/12/2019 and split remaining costs, Chris now to input to complete by mid Jan
Finance | PAYE registering | Chris Neale | 15/4/2020 | 2020-04-05 |  | Not started | 12/3/2020 GEL set up for Corporation Tax, meaning some steps done with HMRC to help re PAYE registration, when to be done. 29/1/2019 Changed planned start date 31/1/2019 to 15/4/2019 . 10/12/2019 Chris noted update, provided 23/10.2019, that should not start to register payroll until 4 week before have staff on payroll if do on the phone (max 8 weeks before have staff on payroll, if online), to avoid having payroll fines of £100-£400. KRD 27/11/2019 - Chris please can you specify dates for this task
Finance | GEL Bank account set up | Simon Peet / Chris Neale | 2020-11-01 | 2020-01-27 | 2020-11-01 | Completed | 17/2/2020 Confirmed set up. Monday 11/2 Lloyds confirmed that have forms signed by directors and are in final stages of Know your Client compliance and hope within a week. Monday 27/1/20 Lloyds confirmed (Hayleigh) that had been told (Gabriel) that should be done by Friday 24/1 and would chase to find out why not and when would. Monday 13/1/2020 Lloyds confirmed had everything for bank account to be opened, hopefully this week, and had SUN indirect submitter form re payroll (sent original in post that day also) that might be completed the following week. 9/1/2020 SUN Indirect Submitter form drafted and given to Lara and to Kayleigh (of Lloyds bank) for final points to be concluded so then when sorted then can be put to Alison to sign, for SUN aspect to be sorted thereafter. Regarding separate (non SUN) point of bank account being set up, Bank have all other information for setting up bank account which can hopefully be set up by 17/1/2020, as bank 6/1/2020 said this can be done in a few days. 9/1/2020 SUN Indirect Submitter form drafted and provided to Karmveer to complete based on Ealing Pension Fund form he completed. 9/1/2020 Deborah confirmed sent in remaining details requested by bank and with which provided for sending in Nov 2019. 7/1/2020 KAP confirmed sent in, and Deborah to provide details of email so Chris can also be in contact with them. 6/1/2020 Chris requested Simon to submit Key Account information for new director Alison to bank, Alison confirmed had left Key Accout information for Simon on 20/12 when Simon on leave, following 6/12/2019 Chris chasing Simon for whether sent as Alison Key information signed left with Simon 20/12 on leave till 6/1. 28/01/2020 (KRD): Chris chasing bank
Finance | London Living Wage to calculate impact of 20p increase | Chris Neale | 2020-12-16 | 2020-01-31 |  | Completed | 28/1/2020 completed and shared file with Kevin & John for meeting 29/1/2020 6/1/2020 Seeking to start last week Jan 2020, seem likely to Feb
Finance | Handover information for GEL New Finance Manager | Chris Neale | 2020-02-01 | 2020-04-30 | 2020-02-01 | In progress | 30/3/2020 started process 26/2/2020 Kevin confirmed would be 1/4/2020. 24/2/2020 John confirmed think Caterina starting c1/2/2020. C requested know when confirmed, so email account set up for her and diary. 17/2/2020 confirmed Caterina may be earlier, C asked Sharon and Kevin confirm and put on email. 10/2 Confirmed Caterina may start end in 2m so 10/4.
Finance | Sort out appointment of auditor | Chris Neale / Simon Peet | 2020-02-01 | 2020-04-15 | 2020-01-06 | In progress | 6/4/2020 Auditor confirmed they would send draft letter of engagement, and listed things required for the audit. 6/4/2020 Chris emailed chaser to Deloitte auditor. 31/3/2020 CN to chase Deloitte re letter of engagement. 9/3/2020 C with Kevin met Deloitte auditor and requested letter of engagement and requirements and agreed some work may be May-June where documentation and then would do audit from September 2020. 3/3/2020 C requested auditor meeting by 10/3/2020 now internal Council finance clearance that auditor available. 18/2/2020 confirmed to Jo that not going to appoint till after March Board meeting, and that 1st accounting reference date to be June 2020, then March 2021. Changed required date for auditor till 15/4/20, from 28/2/20, to allow time for discussions of their service levels with them for the fee they have quoted. 10/2 Deloitte gave £15k quote for 2019/20, and Chris checking with Simon re conditions that Greener Ealing would like. 27/1/2020 Chris asked Deloitte again for response this week, also are seeking clarification re whether the Accounting Reference Period should change to 30th June for 19/20 and then 31st March for 20/21 and thereafter, to ease accounting for Council and for company 10/1/2020 Simon checking with Deloitte. 7/1/2020 Chris asked Simon to ask Deloitte how wished formalised. 7/1/2020 Chris to contact Deloitte re how to appoint. 6/1/2019 Chris got info from Simon Peet re Deloittes auditors, and asked Simon how to progress, and from Simon re PwC tax advisor.
Finance | Sort out if tax advisor required | Chris Neale / Simon Peet | 2020-02-01 | 2020-01-06 | 2020-01-06 | Completed | 17/2/2020 Simon confirmed not likely to hear from PwC for several weeks. 24/1/2020 Chris asked Simon for when PwC might revert. 9/1/2020 Chris contacted PwC outlining main points on which may seek advice. 6/1/2020 Chris got info from Simon Peet re PwC tax advisor.
Finance | Register for Corpporation Tax | Chris Neale / John Parmenter | 2020-02-25 | 2020-03-16 | 2020-02-25 | Completed | 13/3/2020 C registered Greener Ealing for CT and sent details to John P. 25/2/2020 John clarified that thought Greener Ealing registered for Tax (when in fact Legal only got registered with Companies House August 2019), and would wish Greener Ealing registered to allow access for Finance system set up, so access sought, HMRC confirmed will get back within 2 weeks
Finance | Transfer budget files so can be accessed by consultants | Chris Neale | 2020-03-02 | 2020-03-13 | 2020-03-02 | Completed | 11/3/2020 C transferred all files to OneDrive, and explained via email to John P how could be relinked on new folder if wished, and how could help someone doing. 2/3/2020 C resurfaced IT request of 28/2/2020 to escalate with IT
GEL Tasks | Waste carriers licence | John Arnold/ Kevin Oleary | 2020-01-06 | 2020-03-01 | 2020-01-06 | Completed | Awaiting for all GEL directors to be added to companies house (X3 directors) 28.01.20 -registered
GEL Tasks | Ascertain if there are any Amey vehicles LBE would like to buy | John Arnold/ Earl McKenzie/ Kevin O'Leary | 2020-01-06 | 2020-03-01 | 2019-12-16 | In Progress | We have requested an updated fleet list with costs so we can make an informed decision
GEL Tasks | Negotiate deal with Amey | John Arnold/ Earl McKenzie/ Kevin O'Leary | 2020-02-01 | 2020-04-01 |  | Not Started | We have a fleet consultant who will assist the project in the O Licence application and check that our plans keep us compliant
GEL Tasks | Work Out who COTC Holder Is | John Arnold/ Earl McKenzie/ Kevin O'Leary | 2020-02-01 | 2020-07-01 | 2020-04-01 | in progress | Plan B support have highlighted this we are awaiting confirmation from Amey
GEL Tasks | Apply for O Licence | John Arnold/Kevin O'Leary + Consultant | 2020-02-01 | 2020-07-01 | 2020-02-01 | in progress | Application has been submitted along with payment of £350K to GEL bank account awaiting final award to Vehicle Maintenance supplier so updated can be given to Traffic Commisoner
GEL Tasks | Transport Manager CPC holder(Green Recruitment time) | John Arnold/Kevin O'Leary + Consultant | 2020-02-01 | 2020-07-01 | 2020-02-20 | in progress | Mick Aherne & Masoud Inayat to TUPE across both have been named on GEL's O Licence application as CPC holders
GEL Tasks | O Licence Granted | John Arnold/Kevin O'Leary + Consultant | 2020-02-01 | 2020-07-01 |  | Not Started
GEL Tasks | V5s handed over | John Arnold/Kevin O'Leary + Consultant | 2020-06-01 | 2020-07-01 |  | Not Started | Not required until Amey fleet is novated across to GEL (Spares)
GEL Tasks | Keys and spares handed over | John Arnold/Kevin O'Leary + Consultant | 2020-06-01 | 2020-07-01 |  | Not Started | Not required until Amey fleet is novated across to GEL (Spares)
GEL Tasks | Maintenance records handed over | John Arnold/Kevin O'Leary + Consultant | 2020-06-01 | 2020-07-01 |  | Not Started | Not required until Amey fleet is novated across to GEL (Spares)
GEL Tasks | MOT records handed over | John Arnold/Kevin O'Leary + Consultant | 2020-06-01 | 2020-07-01 |  | Not Started | Not required until Amey fleet is novated across to GEL (Spares)
GEL Tasks | LOLER records handed over | John Arnold/Kevin O'Leary + Consultant | 2020-06-01 | 2020-07-01 |  | Not Started | Not required until Amey fleet is novated across to GEL (Spares)
GEL Tasks | Understand current defect process | John Arnold/Kevin O'Leary + Consultant | 2020-02-01 | 2020-07-01 | 2020-02-02 | in progress | We understand the current defect report process and have deceided to carry this on but using a different application provider GEL will use Fleetcheck while Amey currently us Checked safe
GEL Tasks | Make sure each round/beat has a map and a road list of each day | John Arnold/Kevin O'Leary | 2020-05-01 | 2020-07-01 | 2020-04-15 | in progress | Request made to amey for lates round data for all services so maps can be created
GEL Tasks | Highlight assisted and ensured collections on each round | John Arnold/Kevin O'Leary | 2020-05-01 | 2020-07-01 |  | Not Started
GEL Tasks | ABP Permit (free) |  |  | POST GO LIVE
H&S | Recruitment of a health and safety consultant to deliver workplan | John Arnold and Somayya Yaqub | 2020-01-06 | 2020-01-27 |  | Completed
H&S | Secure requisite approval and funding | John Arnold | 2020-01-06 | 2020-01-07 |  | Completed
H&S | Appoint candidate to start W/C 27/01/2020 | Health and safety consultant | 2020-01-14 | 2020-01-27 |  | Completed | 23/01/2020 (KRD): H&S consultant met with on 21/01/2020, to begin conducitng gap analsysis. After which, project plan can be created
H&S | Production of H&S Management System Documents | Plan B Management Solutions | 2020-04-13 | 2020-07-06 |  | In progress | 16/04/2020 (KRD): Kevin to request a schedule for when each document will be produced
H&S | Gap analysis | Plan B Management Solutions | 2020-08-03 | 2020-11-03 |  | Not started | 16/04/2020 (KRD): firmer start and completion dates to be agreed with supplier.
H&S | Culture change project | Plan B Management Solutions | 2020-11-04 | 2021-02-04 |  | Not started | 16/04/2020 (KRD): firmer start and completion dates to be agreed with supplier.
HR | Develop a TUPE transfer process and ensure smooth transition of Amey staff to the LATCO | Bill Gilmour | 2020-01-31 | 2020-06-08 |  | In progress | Need to take into account Amey's Mobilation Plan/current non contact wth Amey HR rep Bill to write to Amey on 06/04 as this is three months before go-live
HR | Request early version of all Employee Liability Information documents | Bill Gilmour | 2020-02-28 | N/A | 2019-12-16 | Completed | 28/11/2019: When will the employer liability information be received as per the exit agreement? Will it include ID checks and driver information?
HR | Complete due diligence/gap analysis of ELI | Bill Gilmour | 2020-04-01 | 2020-06-08 |  | In progress | 28/11/2019: What LATCo provisions are envisaged, as formulating them is a task in itself? SB: need to have productive dialogue with Amey HR re completion of TUPE spreadsheet. Amey mobilition plan states information to be provided 22/6/20! 06/04/2020 (KRD): taking place at the moment with anonymous data, and will continue to be reviewed once in receipt of full ELI data
HR | Identify and agree which roles/who should transfer | Bill Gilmour | 2020-04-01 | 2020-06-08 |  | Not started | 16/12 SB: Can't do this until Amey have provided TUPE list
HR | Develop proposals for any measures, including negotation on any new contractual provisions. | Bill Gilmour | 2020-04-06 | 2020-06-08 |  | In progress | 03/12/2019: need discussion with TU - need to jointly agreed and send measures letter re any proposed changes 06/04/2020 (KRD): initial measures letter will be created by 10/04/2020 (BG)
HR | Develop staff consultation plan in liaison with unions | Bill Gilmour | 2020-04-29 | 2020-06-01 |  | Not started | 03/12/2019: consultation plan needs to be devised in January 2020. Amey's mobilation plan suggests agreeing timetable for consultation in April, 18/5/20-19/6/20 to carry out consulation meetings and issuing letters to staff
HR | Manage the staff transfer process | Bill Gilmour | 2020-01-31 | 2020-06-08 |  | In progress | 28/11/2019: LBE's HR Shared Service Centre can be mobilised as a virtual team to support the TUPE document checking process for eligibility to work docs/checks
HR | Liaise with Lara on payroll | Bill Gilmour | 2020-06-08 | 2020-06-12 |  | Not started | Need to facilitate introduction of Ealing and Amey payroll contact
HR | Design staff induction (ICT TRAINING ELEMENT) | Bill Gilmour | 2020-04-06 | 2020-07-06 | 2020-04-06 | In progress | Depends on what induction /training is being requested and provided by whom 23/03/2020 (KRD): Samantha/HR designing new virtual induction, hopefully by next week 16/04/2020 (KRD): workshop to finalise process. JA to check-up with Bill and Sharon to confirm this is being arranged by HR/Samantha Whittick.
HR | Design staff induction (general staff induction, ALL STAFF) | Bill Gilmour | 2020-04-06 | 2020-07-06 | 2020-04-06 | In progress
HR | Review GEL's company structure and reporting lines | Sharon Brown |  | 2020-02-28 |  | Completed
HR | Develop recruitment process for posts | Sharon Brown |  | 2020-02-28 |  | Completed | 16/12 Interim Director already in place, Council Director to make decision about this pending Board being set up
HR | Develop JDs and person specs | Sharon Brown/ Gel Mgmt team/KO'L |  | 2020-02-28 |  | Completed | 16/12 Hays Recruitment Agency commissioned to recruit to HR and Finance roles
HR | Develop pay, benefits, and T&Cs for each post | Sharon Brown/ Gel Mgmt team/KO'L |  | 2020-02-28 |  | Completed | Using ACAS T&C's for new posts
HR | Policies and procedures required | Bill | 2020-02-28 | 2020-06-01 |  | in progress | 06/04/2020 (KRD): Amey policies being reviewed but these are non-contractual and we will introduce a set of HR policies to fit GEL
HR | Develop a specimen contract of employment | Sharon |  | 2020-06-01 |  | in progress | Using ACAS T&C's for new posts
HR | Pay policy (base pay; overtime; bonuses; shift and other allowances) | Bill Gilmour | TBC | TBC |  | Not started | 06/04/2020 (KRD): will review on receipt of sepcific pay policy documentation from Amey
HR | Performance management | Bill Gilmour | 2020-04-13 | 2020-04-20 |  | In progress
HR | Sickness absence and sick pay | Bill Gilmour | 2020-04-06 | 2020-04-10 |  | In progress
HR | Holiday policy and booking process | Bill Gilmour | TBC | TBC |  | Not started
HR | Overtime recording process | Bill Gilmour | TBC | TBC |  | Not started
HR | Signing in, signing out procedure | Bill Gilmour | TBC | TBC |  | Not started
HR | Other absences (paid; unpaid; procedure; entitlement) | Bill Gilmour | TBC | TBC |  | Not started
HR | Maternity/paternity/adoption/parental leave | Bill Gilmour | TBC | TBC |  | Not started
HR | Working Time Regulations/limits/opting out policy | Bill Gilmour | TBC | TBC |  | Not started
HR | Working week/working patterns/rest breaks/toil/overtime | Bill Gilmour | TBC | TBC |  | Not started
HR | Disciplinary procedure | Bill Gilmour | 2020-04-03 | 2020-04-06 |  | in progress
HR | Grievance procedure | Bill Gilmour | 2020-04-02 | 2020-04-03 |  | completed | 06/04/2020 (krd): draft completed and sent to SB for review
HR | Equal opportunities | Bill Gilmour | 2020-04-07 | 2020-04-10 |  | In progress
HR | Smoking at work | Bill Gilmour | TBC | TBC |  | Not started
HR | Harassment policy | Bill Gilmour | TBC | TBC |  | Not started
HR | Personal records and data protection | Bill Gilmour | TBC | TBC |  | Not started
HR | Handling organisational change policy | Bill Gilmour | TBC | TBC |  | Not started
HR | References policy | Bill Gilmour | TBC | TBC |  | Not started
HR | Handbook (reference to Modern Slavery Act 2015 Regs/Anti corruption policy/Bribery Act 2010). Company property (care, reporting damage, returning, storing, handover, keep it safe) | Bill Gilmour | TBC | TBC |  | Not started
HR | Email/internet policy | Bill Gilmour | TBC | TBC |  | Not started
HR | Mobile phone policy | Bill Gilmour | TBC | TBC |  | Not started
HR | Expenses policy | Bill Gilmour | TBC | TBC |  | Not started
HR | Review scope and content of any Amey recognition/ collective agreements | Bill Gilmour | 2020-06-08 | 2020-07-06 |  | in progress | 1/12 SB: Not sure if this complete. We've had first offical meeting with the TU's, not seen any recognition/collective agreements. 06/04/2020 (KRD): discussed with unions and are awaiting confirmation of any formal recognition agreements. Will also pick up with Amey HR now that we are in 3 month de-mob period
HR | Identify local reps/shop stewards and what the consultative requirements are | Bill Gilmour | 2020-03-16 | 2020-07-06 |  | In progress | Could discuss with Dean Gilligan at next TU meeting 23/03/2020 (KRD): agreed with union that they would meet with shop stewards, but Amey did not want any visits before the 3 months 06/04/2020 (KRD): local reps Dean Gilligan provided names of reps currently at Amey. Awaiting confirmation of their details and credentials
HR | Develop any changes/protocols for LATCo and trade union facilities | Bill Gilmour | 2020-06-06 | 2020-06-07 |  | Not started | 06/04/2020 (KRD): we will seek to develop these with the GMB and others following receipt of any information, as to current arrangements.
HR | Post go-live | Bill Gilmour | N/A | N/A |  | Not started
HR | Training & Development Plan | GEL HR | N/A | N/A |  | Not started
HR | Apprenticeship Programme | GEL HR | N/A | N/A |  | Not started | 06/04/2020 (KRD): BG liaised with Jas to discuss way forward
HR | Employment links with local employers and schools | GEL HR | N/A | N/A |  | Not started
HR | Staff induction (WIDER INDUCTION) | William Gilmour/GEL |  |  |  | Not Started
HR (pensions) | Determine pension scheme type | Kevin O'Leary |  |  |  | Completed | 28/11/2019: Option to adopt the Government 'Nest' (National Employment Savings Trust) scheme for Amey staff & new recruits who were never part of the previous Ealing TUPE transfer group. Decided June 2019.
HR (pensions) | HMRC registration | Lara Balogun | 2020-05-06 | 2020-05-06 |  | Not started | 1/12 to register with HMRC re PAYE once ready to have payroll
HR (pensions) | HMRC to issue Company with Scheme Number | Lara Balogun | 2020-05-06 | 2020-05-06 |  | Not started
HR (pensions) | Register Company with NEST | Lara Balogun | 2020-06-06 | 2020-06-06 |  | Not started | 1/12 Company registered Oct 19 with Companies House, to register re Pension once registered for PAYE
HR (pensions) | Arrange employers Liability insurance | Ewan re Ins/ Chris | 2019-10-01 | 2020-04-01 | 2019-10-01 | in progress | 1/12 Being done by April 2020 by Ewan as part of new Insurance contract for council
HR (pensions) | Arrange scheme - require PAYE and bank account | Chris re bank / Payroll re PAYE then | 2019-10-01 | 2020-02-20 | 2019-10-01 | Completed | 20/2/2020 SUN set up 17/2/2020 Bank account set up 14/1/2020 expect bank account this week, and SUN for payroll the following, as all details provided to bank. Do not need PAYE registration to start till 6wks before start paying PAYE. 6/1/20 Chris requested Simon to get updated Director Alison Reynolds, to bank, as they requested. 1/12/19 started getting bank account hoping earliest in Dec
HR (pensions) | Agree contribution levels | Kevin O'Leary |  | 2019-11-28 |  | Completed | 28/11/2019: 5% minimum contribution level was agreed.
HR (pensions) | Decide main contact for Nest/ other scheme who makes decisions about the scheme | Kevin O'Leary |  | 2019-11-28 |  | Completed | 28/11/2019: it has been agreed that the GEL MD and the Company Board will hold this decision making authority.
HR (pensions) | Names of delegates / internal and external (Finance, Payroll provider) | Lara Balogun/ Chris Neale |  |  |  | Completed
HR (pensions) | Specify pay period/frequency | Lara Balogun |  | 2020-12-20 |  | Completed | Monthly - 26th of each month or nearest working day i.e. if 26th falls on Saturday will pay on Friday.
HR (pensions) | Broadly equivalent LGPS or Admitted Body Status scheme for ex Ealing employees (up to 17) | Jenny Connett | 2020-03-10 | 2020-06-07 |  | Not started | Needs two months lead in to complete tasks
HR (pensions) | Obtain dates of birth | John Arnold | 1900-01-09 | 2020-03-13 |  | Completed | 06/04/2020 (KRD): JC has these DOBs
HR (pensions) | Researching legal requirements for the report | Chuhr Nijjar | 2020-03-10 | 2020-04-10 |  | Completed
HR (pensions) | Obtain confirmation of the names and details (that are available) of the staff that are to be included in the admitted body. | Bill Gilmour | 2020-06-08 | 2020-06-08 |  | Not started | Need Amey to confirm TUPE data and names that need to be put into LGPS
HR (pensions) | The application form and first tab of the new employer data request spreadsheet needs to be completed and returned and provided to pensions. The first few columns of the second tab can be completed with the names and basic information. | Bill Gilmour | 2020-06-08 | 2020-06-08 |  | Not started
HR (pensions) | Pensions to check with the actuaries to see if they need details of deferred benefits held with Ealing (or if the will extract this from the valuation data they already hold) | Jenny Connett | 2020-05-06 | 2020-06-08 |  | Not started
HR (pensions) | Once received the above documents will be sent to the scheme actuaries to access the employers contributions rate (plus any possible deficit payments) and if a bond is required. | Bill Gilmour | 2020-06-09 | 2020-06-09 |  | Not started
HR (pensions) | The actuaries will then issue an admission summary paper (this might take 6 – 8 weeks, but hopefully will be sooner) | Jenny Connett | 2020-05-06 | 2020-06-07 |  | Not started
HR (pensions) | A report will need to go to the Pensions Fund Panel (this will need to be submitted two weeks before the meeting date. I am not sure of the exact date it will be in June / July 2020) | Jenny Connett | 2020-05-06 | 2020-06-18 |  | Not started | report written and fully signed off by 15/6/2020. PFP meeting confirmed as 02/07/2020
HR (pensions) | Drafting and agreeing Admissions agreement | Chuhr | 2020-04-10 | 2020-07-09 |  | Not started | THIS WILL NOT IMPACT ON THE SERVICE IN ANY WAY
HR (pensions) | Finalising | Chuhr | 2020-07-02 | TBC |  | Not started
ICT | HR |  | 2019-11-08 | 2020-04-01 |  | In progress: delayed
ICT | Send payroll info to HR |  | 2019-11-08 | 2019-11-08 |  | Completed
ICT | Payroll file from HR to be received by BW team |  | 2019-11-11 | 2019-01-22 |  | Completed | 14/01/2020 (KRD): delayed by one week, update from HR on 22/01
ICT | HR BACS file updated |  | 2020-04-01 | 2020-04-01 |  | Not started: delayed | 16/04/2020 (KRD): Killian to arrange meeting between IT and Finance to clarify what IT require from Finance.
ICT | MTD - VAT Tax codes into iTrent |  | 2019-12-31 | second week March |  | in progress: delayed | 14/01/2020 (KRD): change control possibly required according to Shahzad James is doing this, informally, may not need change control. Status needs to be confirmed 19/03/2020 (KRD): delayed as HR need to supply, issue with SMART cards, software MTD needs to go in for testing 31/03/2020 (KRD): VAT return needs to be sent to James. The VAT file (HR) also needs to be received. 16/04/2020 (KRD): escalated to Andrew Scully for completion.
ICT | SUN (Service User) numbers for bank account provided to HR |  | 2019-12-31 | 2019-12-31 |  | Completed | 20/2/2020 SUN 189918 provided to IT 14/01/2020 (KRD): delayed, hope to have by end of January. No impact as of yet 11/02/2020 (SR): scheduled for completion next week
ICT | Business World GEL |  | 2019-12-19 | 2020-07-07 |  | in progress
ICT | GEL BW Client Build |  | 2019-12-19 | 2020-04-06 |  | in progress
ICT | Design |  | 2019-12-19 | 2019-12-30 |  | Completed
ICT | System set up |  | 2020-01-01 | 2020-01-14 |  | Completed
ICT | Accounts payable |  | 2020-01-15 | 2020-02-04 |  | Completed
ICT | Accounts receivable |  | 2020-02-05 | 2020-02-19 |  | Completed | 25/02/2020 (KRD): cannot be completed until TUPEE names and details are provided
ICT | Integration |  | 2020-03-05 | 2020-03-21 |  | Completed | 19/03/2020 (KRD): one week behind 31/03/2020 (KRD): one week behind (from 28/03/2020)
ICT | Making tax digital installation of BW module and client |  | 2020-02-20 | 2020-03-05 |  | In progress | 19/03/2020 (KRD): one week behind 31/03/2020 (KRD): one week behind (from 12/03/2020) 16/04/2020 (KRD): testing underway
ICT | Systems test and fix |  | 2020-03-06 | 2020-03-19 |  | Completed | 19/03/2020 (KRD): one week behind 31/03/2020 (KRD): one week behind (from 26/03/2020)
ICT | Set up balance tables, planner revenue, capital, logistics, actuals data |  | 2020-03-20 | 2020-03-24 |  | Completed | 19/03/2020 (KRD): one week behind 31/03/2020 (KRD): one week behind
ICT | Set up basic reporting, AP, AR, trial balance |  | 2020-03-24 | 2020-03-30 |  | Completed | 19/03/2020 (KRD): one week behind 31/03/2020 (KRD): one week behind
ICT | Banking set up facility for manual upload of statement into BW |  | 2020-03-31 | 2020-04-02 |  | Completed | 19/03/2020 (KRD): one week behind 31/03/2020 (KRD): one week behind
ICT | BW Development and system testing complete |  | 2020-04-03 | 2020-04-10 |  | in progress | 19/03/2020 (KRD): one week behind 31/03/2020 (KRD): one week behind
ICT | GEL UAT Post Build Test and Train |  | 2020-04-07 | 2020-07-07 |  | Not started | 16/04/2020 (KRD): Not started due to COVID-19
ICT | BW UAT |  | 2020-04-07 | 2020-04-27 |  | Not started
ICT | BW Training |  | 2020-04-21 | 2020-05-04 |  | Not started | 16/04/2020 (KRD): JA to liaise with Amey on staff for training
ICT | BW - data input |  | 2020-05-05 | 2020-05-08 |  | Not started
ICT | Testing, ready for go-live |  | 2020-05-11 | 2020-07-02 |  | Not started
ICT | Go live/no go-live decision |  | 2020-07-03 | 2020-07-03 |  | Not started
ICT | Go live |  | 2020-07-07 | 2020-07-07 |  | Not started
ICT | GEL Business Applications |  | 2019-09-25 | 2020-06-02 |  | in progress
ICT | Initiation |  | 2019-09-25 | 2020-11-14 |  | Completed
ICT | ICT technical standards and FOI |  | 2019-11-07 | 2019-11-18 |  | Completed
ICT | Gcloud ICT requirements and plan |  | 2019-10-22 | 2019-11-28 |  | Completed
ICT | Procurement elements |  | 2019-10-22 | 2019-11-28 |  | Completed
ICT | Sign-off Whitespace Contract |  | 2019-11-29 | 2020-03-27 |  | In progress: delayed | 21/01/2020 (KRD): still needs to be signed. Meeting arranged for 27/01/2020 to progress. Completion date moved from 29/11/2019 to 31/01/2020. 11/02/2020 (SR): to be signed off by Head of ICT on 11/02/2020 25/02/2020 (KRD): another week 19/03/2020 (KRD): has to be re-signed 16/04/2020 (KRD): to be signed off once Alec gives the go-ahead
ICT | Data gathering |  | 2019-10-03 | 2019-11-29 |  | Completed
ICT | Prepare LLPG data |  | 2019-10-14 | 2019-10-31 |  | Completed
ICT | Prepare FTP |  | 2019-10-14 | 2019-11-08 |  | Completed
ICT | FTP LLPG data to WS |  | 2019-11-11 | 2019-11-12 |  | Completed
ICT | Whitespace data gather |  | 2019-11-13 | 2019-11-28 |  | Completed
ICT | COU process in place |  | 2019-11-29 | 2019-11-29 |  | Completed
ICT | Whitespace configuration |  | 2019-11-29 | 2019-01-02 |  | Completed
ICT | Whitespace mobile configuration |  | 2019-11-25 | 2019-11-27 |  | Completed
ICT | Whitespace workshop |  | 2019-12-06 | 2019-12-06 |  | Completed
ICT | Internal testing |  | 2019-01-06 | 2020-06-22 |  | In progress | 21/01/2020 (KRD): more testing to be done 20/03/2020 (KRD): will continue until go-live
ICT | vehicle kit out |  | 2020-02-03 | POST GO LIVE |  | Not started | 14/01/2020 (KRD): do not know when vehicles will be devlivered and cannot therefore have start and finish date 20/03/2020 (KRD): will now happen post go-live
ICT | CRM integration |  | 2019-11-04 | 2020-02-27 |  | in progress: delayed | 16/04/2020 (KRD): still working on integration as due to greater complexity than first anticipated.
ICT | Contender integrations - proposal |  | 2019-11-04 | 2019-11-28 |  | Completed
ICT | Requirement - initial meet with Contender |  | 2019-11-04 | 2019-11-04 |  | Completed
ICT | Receive quote from Contender |  | 2019-11-05 | 2019-11-11 |  | Completed
ICT | Confirm Contender quote as acceptable |  | 2019-11-12 | 2019-11-25 |  | Completed
ICT | Generate PO and send to Contender |  | 2019-11-26 | 2019-11-28 |  | Completed
ICT | Contender integration specification |  | 2019-11-29 | 2019-11-29 |  | Completed
ICT | Contender integration development and testing |  | 2019-12-02 | 2020-04-06 |  | in progress: delayed | 20/03/2020 (KRD): moved finish date to second week in April 16/04/2020 (KRD): still working on integration due to greater complexity than first anticipated.
ICT | Training |  | 2020-04-07 | 2020-04-09 |  | Not started
ICT | UAT |  | 2020-04-10 | 2020-06-22 |  | Not started
ICT | Ready for go-live - parallel running |  | 2020-04-14 | 2020-04-14 |  | Not started | need to speak to Amey
ICT | Analytics delivery |  | 2020-04-15 | 2020-05-27 |  | Not started
ICT | Complete go-live by turning off parallel running |  | 2020-06-02 | 2020-06-02 |  | Not started
ICT | GEL ICT Infrastructure and Hardware |  | 2019-10-01 | 2020-04-06 |  | In progress
ICT | Requirements |  | 2019-10-01 | 2019-10-01 |  | Completed
ICT | Domain names |  | 2019-10-01 | 2019-10-07 |  | Completed
ICT | Site surveys |  | 2019-10-22 | 2019-10-22 |  | Completed
ICT | Order and receive kit |  | 2020-03-27 | 2020-04-04 |  | In progress | 20/01/2020 (KRD): cannot happen until the PID is signed off 11/02/2020 (SR): PID to be signed off by GEL on 11/02/2020, kit to be ordered following day 19/03/2020 (KRD): start and finish dates changed 20/03/2020 (KRD): issue with procurement on ordering. Shahzad will order next week 31/03/2020 (KRD): 16/04/2020 (KRD): slight delay due to COVID-19.
ICT | Order and receive BT lines |  | 2019-12-17 | 2020-02-03 |  | Completed | 20/01/2020 (KRD): ordered but not yet received
ICT | Network/wifi implement |  | 2020-02-04 | 2020-02-24 |  | In progress | 20/03/2020 (KRD): issue with procurement on ordering. Shahzad will order next week 16/04/2020 (KRD): due to COVID-19 slight delay with switch config installation due to be finished April-end
ICT | Build hardware of site |  | 2020-01-21 | 2020-02-24 |  | In progress | 20/03/2020 (KRD): issue with procurement on ordering. Shahzad will order next week 16/04/2020 (KRD): due to COVID-19 slight delay with switch config installation due to be finished April-end
ICT | Desktop hardware - implement |  | 2020-02-25 | 2020-03-02 |  | In progress | 20/03/2020 (KRD): issue with procurement on ordering. Shahzad will order next week 16/04/2020 (KRD): due to COVID-19 slight delay with switch config installation due to be finished April-end
ICT | Telephony - implement |  | 2020-02-25 | 2020-03-09 |  | In progress | 20/03/2020 (KRD): issue with procurement on ordering. Shahzad will order next week 16/04/2020 (KRD): due to COVID-19 slight delay with switch config installation due to be finished April-end
ICT | Printers - implement |  | 2020-02-25 | 2020-03-09 |  | In progress | 20/03/2020 (KRD): issue with procurement on ordering. Shahzad will order next week 16/04/2020 (KRD): due to COVID-19 slight delay with switch config installation due to be finished April-end
ICT | Implement furniture |  | 2020-01-21 | 2020-02-17 |  | In progress | 20/03/2020 (KRD): issue with procurement on ordering. Shahzad will order next week 16/04/2020 (KRD): due to COVID-19 slight delay with switch config installation due to be finished April-end
ICT | Test and completion |  | 2020-03-10 | 2020-04-06 |  | Delayed: not started | 20/03/2020 (KRD): issue with procurement on ordering. Shahzad will order next week
ICT | Support ICT |  | 2019-11-27 | 2020-07-09 |  | in progress
ICT | Commercials - ICT |  | 2019-11-27 | 2020-01-16 |  | Completed | 14/01/2020 (KRD): due to be finished on 16/01/2020 21/01/2020 (KRD): it has been escalated. It has been sent to Peter Greenham
ICT | Business applications support |  | 2019-12-17 | 2020-07-09 |  | In progress | 14/01/2020 (KRD): due to start on 20/01/2020 (change from 17/12/2020) 21/01/2020 (KRD): start date changed to 06/07/2020 (changed from 20/01/2020) 16/04/2020 (KRD): completed but Chuhr will require version to approve
ICT | Business world support |  | 2019-12-17 | 2020-07-09 |  | In progress | 14/01/2020 (KRD): due to start on 20/01/2020 (change from 17/12/2020) 21/01/2020 (KRD): start date changed to 06/07/2020 (changed from 20/01/2020) 16/04/2020 (KRD): completed but Chuhr will require version to approve
ICT | Network support |  | 2019-02-25 | 2020-07-09 |  | Not started | 14/01/2020 (KRD): due to start on 30/03/2020 (change from 25/02/2020)
ICT | Hardware support |  | 2019-12-17 | 2020-04-23 |  | In progress | 14/01/2020 (KRD): due to start on 30/01/2020 (change from 17/12/2020) 21/01/2020 (KRD): start date changed to 24/02/2020 from 30/01/2020
ICT | HOTS sign-off |  | 2019-12-17 | 2020-06-25 |  | Not started
ICT (Depot) | Workshops\Garages |  | Thu 02/01/20 | Thu 23/01/20 |  | completed
ICT (Depot) | Asbestos work |  | Thu 02/01/20 | Thu 23/01/20 |  | completed
ICT (Depot) | Phase 1 Asbestos Removal Plant Room |  | Thu 02/01/20 | Sun 05/01/20 |  | Completed
ICT (Depot) | Mobilize on site |  | Thu 02/01/20 | Thu 02/01/20 |  | Completed
ICT (Depot) | Sheet up Plant Room |  | Thu 02/01/20 | Thu 02/01/20 |  | Completed
ICT (Depot) | Scaffold in Plant Room |  | Thu 02/01/20 | Thu 02/01/20 |  | Completed
ICT (Depot) | Encapsulate Plant Room |  | Fri 03/01/20 | Fri 03/01/20 |  | Completed
ICT (Depot) | Air Test Plant Room |  | Fri 03/01/20 | Sun 05/01/20 |  | Completed
ICT (Depot) | Phase 2 Asbestos Removal Bus Garages |  | Fri 03/01/20 | Thu 23/01/20 |  | Completed
ICT (Depot) | Scaffolding |  | Fri 03/01/20 | Tue 07/01/20 |  | Completed
ICT (Depot) | Sheeting up |  | Mon 06/01/20 | Thu 09/01/20 |  | Completed
ICT (Depot) | Strip A.I.B. Ceiling Soffit |  | Fri 10/01/20 | Mon 13/01/20 |  | Completed
ICT (Depot) | Fine Clean Enclosure |  | Fri 10/01/20 | Sun 12/01/20 |  | Completed
ICT (Depot) | Air Test Enclosure |  | Sat 18/01/20 | Sun 19/01/20 |  | Completed
ICT (Depot) | Strip down Enclosure |  | Fri 10/01/20 | Mon 13/01/20 |  | Completed
ICT (Depot) | Dismantle Scaffolding |  | Wed 22/01/20 | Thu 23/01/20 |  | Completed
ICT (Depot) | Phase 3 Roof Works |  | 2020-01-02 | 2020-03-31 |  | in progress
ICT (Depot) | Inspections |  | 2020-01-02 | 2020-01-02 |  | Completed
ICT (Depot) | Pre-Start Meeting |  | 2020-01-13 | 2020-01-13 |  | Completed
ICT (Depot) | Internal asbestos removal Garages |  | 2020-01-20 | 2020-01-22 | 27.02.20 | Completed
ICT (Depot) | Internal Cladding Garages |  | 2020-01-23 | 2020-02-28 |  | Completed | Updated the start and end date, activity is arked complete
ICT (Depot) | Bird netting |  | 2020-03-31 | TBA |  | Not started | Expected to start in Jan, still deciding when to complete. Pending on contractor survey
ICT (Depot) | Moving scaffolding set up (continuous activity) |  | N/A | N/A |  | in progress | Internal scaffolding removed
ICT (Depot) | Roof Coatings/ Roof lights(Sky lights) |  | 2020-02-03 | 2020-03-25 |  | Completed | The recoating of the roofing over GEL section ofthe building is complete, the skylights will take a while before there will beany remarkable difference in the light penetration
ICT (Depot) | ICT Sign Off on roof works |  | 2020-03-25 | 2020-03-30 |  | Completed
ICT (Depot) | Heating works |  | 2020-03-23 | 2020-04-24 |  | In progress | 16/04/2020 (KRD): slight delay due to COVID-19.
ICT (Depot) | Engage with required providers for heating reinstatement |  | 2020-04-01 | 2020-04-03 |  | In progress
ICT (Depot) | Re-instating heating at workshops\garages |  | 2020-04-04 | 2020-04-24 |  | In progress
ICT (Depot) | Project PID Approval |  | 2020-03-23 | 2020-04-15 |  | in progress: delayed | 16/04/2020 (KRD): JA to email Gauri to confirm that PID is being circulated for approval
ICT (Depot) | Project PID documentations |  | 2020-03-01 | 2020-03-23 |  | Completed
ICT (Depot) | Project PID submission nd eview |  | 2020-03-23 | 2020-03-23 |  | Completed
ICT (Depot) | PID sign off by internal stakeholders |  | 2020-03-26 | 2020-04-02 |  | in progress: delayed
ICT (Depot) | PID circulation to Place for Sign off & Sign Off |  | 2020-04-03 | 2020-04-15 |  | Not started: delayed
ICT (Depot) | Clearing of rubbish at the site |  | NA | NA |  | Ongoing | Tenant to ensure that housekeeping is done regularly and site manager to ensure they do
ICT (Depot) | Parking & Charging Points |  | 2020-04-10 | 2020-06-26 |  | Not started
ICT (Depot) | Parking area identification for vehicles andsign off |  | 2020-02-15 | 2020-03-25 |  | Completed | Originally GEL asked for 150 vehicles, GF Depot can accomodate 112
ICT (Depot) | Relining GEL parking area |  | 2020-04-20 | 2020-05-27 |  | Not started | 112 - provisioned the remaining will continue to be taken home. Plans provided by Highways are accaptable
ICT (Depot) | Electrical Connection to the agreed location or charging points |  | 2020-04-22 | 2020-05-27 | 28.02.20 | Not started | Started to review costs for 6 double charge points in the depot
ICT (Depot) | 12 Electric Charge points provisioning |  | 2020-05-13 | 2020-06-26 | 28.02.20 | Not started | Started to review costs for 6 double charge points in the depot
ICT (Depot) | Facilities currently in use by AMEY to be provided to GEL |  | 2020-06-29 | 2020-07-06 |  | Not started
ICT (Depot) | Facilities handover to GEL |  | 2020-06-29 | 2020-07-03 |  | Not started
ICT (Depot) | GEL Go Live |  | 2020-07-06 | 2020-07-06
Legal | Variation of articles to be approved by Cabinet | Helen Harris | 17.3.2020 | 2020-03-17 |  | Completed | 09/12/2019: Articles - wrong version attached to the October Cabinet Report. Will need to go back to February Cabinet to amend the articles. 20/01/2020: will now go to March Cabinet, delayed from Feb Cabinet
Legal | Shareholder representative appointment | Helen Harris |  | 10.01.20 |  | Completed | 09/12/2019: Gary Alderson appointed at October 2019 Cabinet
Legal | New director to appoint to replace Tim Smith and obtain authority to indemnify new director | Helen Harris |  | 2020-02-28 | 2020-01-07 | Completed | 09/12/2019: HH & Ross to decide who to appoint as director to replace TS. HH has delegated authority to appoint directors and to give indemnities to directors. 20/01/2020 (KRD): approval required from Alison and Ross to indemnify Kieran Read. This task has been delayed from a completion date of 10/01/2020 to end of Feb.
Legal | Ealing Side Gel Governance - Directors Training | Helen Harris | 2020-03-24 | 2020-03-24 |  | In progress: delayed | 9/12/2019 HH to arrange training via TLT and include all relevant officers 20/01/2020 (KRD): delayed as training hasn't been fully arranged yet 18/03/2020 (KRD): informed by Chuhr Nijar that the training has been cancelled due to COVID-19 concerns. An alternative date has not yet been agreed.
Legal | Company secretarial services | Kevin O'Leary |  | 2020-01-03 |  | Completed
Legal | Broadway Living to be approached | Kevin O'Leary |  | 24.12.2019 |  | Completed | Maxine Sawford to set bridgehouse up as a supplier for GEL to use.
Legal | Provision of company secretarial services to GEL | Kevin O'Leary |  | 2020-01-03 |  | Completed | 09/12/2019: KL to speak to BL - Phillip Brown on secretarial services pending
Legal | Service Provision Agreement - GEL and LBE | Chuhr Nijjar | 1.10.19 | 2020-07-01 |  | In progress | 27/01/2020 (KRD): Chuhr sent the Agreement to Kevin for approval on 24/01/2020
Legal | Agreement for the provision of services from GEL to LBE to KL | Chuhr Nijjar |  | 2020-07-01 |  | In progress | 09/12/2019 Ongoing - meeting every 2 weeks. Colleagues are updating specs, default provisions and KPIs. Aim to complete draft by Xmas and send to Kevin O'Leary early new year. HH suggestion for GE to meet with client departments to agree prices and other important issues. CNi to raise with Clients at meeting on Tuesday. 20/01/2020 (KRD): Chuhr said the agreement will be written by 24/01 10/02/2020 (KRD): still being reviewed by Kevin 30/03/2020 Meeting on services agreement. KL to talk to CB and EM on operational matters. CN to update agreement. GEL to provide default mechanism for Council to review
Legal | KL to revert on Services Agreement with comments |  | 2020-01-17 | 2020-06-01 |  | In progress | 07/04/2020 (CNi): Parties have met with regard to agreement terms and spec. Ongoing work from both sides.
Legal | Completion of Agreement - executed by both parties |  | 1.7.20 | 1.7.20 |  | Not started
Legal | SLA support services (Support Services Agreement) | Chuhr Nijjar | 1.2.20 | 1.7.20 |  | in progress | 13/2/2020 Georgia provided info re P2P, that John A subsequently agreeed. 17/1/2020 Georgia Hoare proposed changes re P2P SLA, agreed subsequently by John Arnold. 09/12/2019: CNi has written to colleagues on ICT, FM, HR and Finance to ascertain which contracts will need to progress specs for the support services agreement.
Legal | Draft SLA to KL covering heads listed below | Chuhr Nijjar | 1.2.20 | 31.04.20 |  | Not started | JA - CNi to start WC 02/03/20
Legal | Completion of SLA | Chuhr Nijjar | 1.2.20 | 1.7.20 |  | Not started
Legal | obtain details from HR | Chuhr Nijjar | 1.2.20 | 31.04.20 |  | Not started
Legal | obtain details from Legal Services | Chuhr Nijjar | 1.2.20 | 31.04.20 |  | Not started
Legal | obtain details from Finance | Chuhr Nijjar | 1.2.20 | 31.04.20 | 2020-10-01 | Completed | 13/2/2020 Georgia provided info re Finance, that John A subsequently agreed. 13/1/2020 Georgia confirmed working on SLA re payments for this week. 6/1/2020 reminded Georgia and John 27/11/2019 Georgia Hoare (& John Parmenter) have Accounts Payable KPIs and deliverables and have been requested to shape to propose to John Arnold, for incorporation into legal agreement
Legal | obtain details from ICT | Chuhr Nijjar | 1.2.20 | 31.04.20 |  | in progress
Legal | obtain details from FM | Chuhr Nijjar | 1.2.20 | 31.04.20 |  | in progress
Legal | obtain details from Payroll | Chuhr Nijjar | 1.2.20 | 31.04.20 |  | in progress
Legal | obtain details fromPensions Administration | Chuhr Nijjar | 1.2.20 | 31.04.20 |  | in progress
Legal | obtain details from Procurement Services | Chuhr Nijjar | 1.2.20 | 31.04.20 |  | in progress
Legal | Novation of existing contracts | Chuhr Nijjar | 1.1.20 | 1.7.20 | 2020-01-20 | in progress | 09/12/2019: Any Amey or LBE contracts to novate to GE. CNi to liasing with colleagues.
Legal | Identify Amey contracts to Novate |  | 20.1.20 | 1.7.20 | 20.1.20 | in progress | 20/01/20 JA to identify the contracts 18/03/20 JA meeting with Amey on novation of contracts 23/03/20 Amey consider most contracts are national but JA obtaining details of local contracts. List being obtained of local providers. 07/04/2020 (CN): May be a novation of the Hitachi vehicle lease and further contract with Hitachi for additional leases.
Legal | Loan agreement/funding facility agreement | Chuhr Nijjar | 1.1.20 | 1.7.20 | 2020-01-01 | in progress | 1/4/2020 Finance issued short term £0.350m loan at relevant interest rate for 6m to cover OTC proof of funding for HGV licence. 25/02/2020 CNi agreed to request Gowling confirm that no state aid issue. 09/12/2019: CNi to liaise with Finance and client officers, including re interest rate 17/03/20 Issue re state aid requires advice. CNi to obtain advice from external solicitors
Legal | Draft Loan Agreement to KL |  | 1.1.20 | 31.04.20 | 1.1.20 | in progress | 1/4/2020 Finance issued short term £0.350m loan at relevant interest rate for 6m to cover OTC proof of funding for HGV operator licence. 25/2/2020 Chris provided details of payment per Amey contract for mid month, and 28/2/2020 legal confirmed believed no State Aid issue, as long as trading in Subsidiary, and 12/3/2020 said w/e 20/3/2020 would request confirmation from Gowling solicitors 20/01/2020 (KRD): Chuhr emailing Chris. 02/03/20 (JA) Chuhr needs infomration from Chris around State aid, Advice being procured by Chuhr 14/04/2020 TLT instructed on 9.4.20 for state aid advice.
Legal | Completion of Loan Agreement |  | 1.7.20 | 1.7.20 |  | Not started | 1/4/2020 Council finance issued short term £0.350m loan at relevant interest rate for 6m to Greener Ealing
Legal | Variation/Novation of procured contracts | Chuhr Nijjar |  | 2020-07-01 |  | in progress | 09/12/2019: CNi working with procurement stream.
Legal | Identify other Contracts to Novate |  | 20.1.20 | 1.7.20 | 20.1.20 | in progress | 20/01/20 CNi to identify the contracts with colleagues 17/03/2020 OH - JA to check whether this can be procured on behalf of GE Business World - no contract in place - Need to formalise terms and to vary to allow GE to use 07/04/2020 (CN): Fleet Maintenance, Pertemps and Fuel and Business World to be novated.
Legal | TUPE information to insert into Services Agreement | Chuhr Nijjar | 2019-12-16 | 1.7.20 | 2019-12-16 | Not started | 17/03/2020 KRD JA's view at this stage is that 28 days before to receive information is now most likely
Legal | Pensions | Chuhr Nijjar |  | 2020-06-25 |  | Not started | 09/12/2019: Meeting with HR who are progressing these arrangements and have been advised to obtain pension panel authority for admission agreement.
Legal | NEST for new staff | Shahzad Ayub |  | 2020-06-06 |  | Not started | 17/03/2020 KRD Chuhr unsure at this stage what his involvement requires. KRD to check with SB
Legal | Authority to enter into Admission Agreement from Pension Panel |  |  | 10.06.2020 |  | Not started
Legal | LGPS - Admission Agreement draft to KL | Chuhr Nijjar |  | 25.06.2020 |  | Not started
Legal | Procurements | Chuhr Nijjar | 1.1.20 | 2020-04-30 |  | in progress | 09/12/2019: Numerous procurements which will need to be completed before GE commences services provision.
Legal | Vehicle procurement - approve & finalise agreements | Chuhr Nijjar | 1.1.20 | 2020-04-30 |  | in progress | 20/01/2020 Check status with SH on 23/1 09/03/20 Urgent decsion being progressed. 17/03/20 Agreement not required as purchase will be covered by the Finance Lease. 16/04/2020 (KRD): letter of intent given to winner (16/04). Final letter of approval from Cabinet expected on 21/04/2020.
Legal | Vehicle Finance Lease | Chuhr Nijjar | 1.1.20 | 2020-04-25 |  | in progress | 20/01/2020 Check status with CNe 17/03/20 Finance leases being procured (changed required date from 2/3 to 25/04) 07/04/2020 (KRD): CNi to respond on finance lease amendment
Legal | Whitespace software CRM | Chuhr Nijjar |  | 2020-03-31 |  | Completed | 17/03/20 Gary to sign to complete the contract. Waiting for the officer decision. 23/03/23 ICT now accept the procurement - contract to be prepared subject to CN to check the financial information. 14/04/2020. CNi to check if contract executed.
Legal | Whitespace Hardware for CRM | Chuhr Nijjar |  | 2020-03-31 |  | In progress: delayed | 17/03/20 Exception comments required from legal 19/03/20 CN to confirm no legal comments required 23/03/20 OD agreed. TCs for the hardware contract awaited. 30/3/20 - Exception awaited 07/04/2020 (CN): SR to obtain Alec Joynson consent to progress
Legal | Alcumus Health & Safety software | Chuhr Nijjar |  |  |  | Completed
Legal | Vehicle maintenance procurement - approve & finalise agreements | Chuhr Nijjar | 1.1.20 | 2020-04-30 |  | In progress | 20/01/20 Tender out, updated documents out today. Tender return in February 17/03/20 - Finalise position on abnormally low tender and then contract with successful bidder. Decision going to April Cabinet. Completion date moved from 02/03 to 31/03 23/03/20 - SFS to be advised their tender to be rejected. Letter of Intent to be sent to Go Plant. KOD to be finalised. 14/04/2020. Letter to SFS on 9.4.20 re- challenge. KOD on 21.4.20. Then enter into contracts, novate and issue any letters of intent ( subject to SFS response on fleet maintenance
Legal | Hire vehicles procurement - approve & finalise agreements | Chuhr Nijjar | 1.1.20 | 2020-04-30 |  | In progress | 17/03/20 - Direct of framework t & c s to be checked and agreement to be entered into with GE . Value is below £500k OD required.
Legal | Staffing agencies procurement - approve & finalise agreements | Chuhr Nijjar | 1.1.20 | 2020-03-02 |  | in progress: delayed | 17/03/20 Call off made from Mstar to finalise. Letter of Intent to be agreed and completed. 23/03/20 Letter of Intent issued to Pertemps. KOD in April.
Legal | Equipment procurement -approve & finalise agreements | Chuhr Nijjar | 1.1.20 | 2020-03-02 |  | Completed | 17/03/2020 - Jewson contract to be varied. Ask Sarah on who owns the contract. 14/04/20 NO need to vary the Materials contract. GE can use contract as drafted
Legal | Other products and services procurement -approve & finalise agreements | Chuhr Nijjar | 1.1.20 | 2020-03-02 |  | in progress: delayed | 17/03/2020 - Variation to Staples Contract. Ask Sarah on who owns the contract.
Legal | Insurance procurement approve & finalise agreements | Chuhr Nijjar (TLT) | 1.1.20 | 2020-03-02 |  | in progress: delayed | 9/03/2020 John A and Ewan progressing reprocurement as procurement within council contract not achieved. 09/12/2019 Ewan Taylor in Insurance will be instructing contracts team on the procurement 17/03/2020 KRD insurance tender now out 14/04/20 Tender response expected this week
Legal | Property Leases & Licences | Jackie Adams | 1.1.20 | 1.7.20 | 1.1.20 | in progress
Legal | Heads of terms from LSH | Jackie Adams | 1.1.20 | 1.3.20 | 1.1.20 | in progress: delayed | 20/1/20 EM to instruct LSH for heads of terms 10/02/2020 (CN): still with Jessica 17/03/2020 (KRD): Gary needs to ask Jessica to get heads of terms from LSH 23/03/20 Awaiting to hear back from GA on heads of terms.
Legal | Lease or Licence Draft | Jackie Adams | 1.1.20 | 6.3.20 |  | Not started: delayed | 09/12/2019 CNi keeping a watching brief.
Legal | Completion of Lease or Licence | Jackie Adams |  | 1.7.20 |  | in progress
Legal | Sub Lease to Vehicle Maintenance operator | Chuhr Nijjar |  | 1.7.20 | 13.1.20 | in progress
Legal | State Aid Advice | Chuhr Nijjar | 21.03.20 | 2020-04-30 |  | in progress | 12/3/2020 Chuhr said would send in w/e 20/3/2020 letter to Gowling solicitors requesting their advice, re internal legal view of 24/2/2020
Legal | Obtain state aid advice | Chuhr Nijjar | 21.03.20 | 2020-04-30 |  | in progress | 12/3/2020 Chuhr said would send in w/e 20/3/2020 letter to Gowling solicitors requesting their advice, re internal legal view of 24/2/2020 14/04/20 TLT instructed for advice on 9.2.20
Procurement | Confirmation of Fleet Delivery time line | John Arnold | 2020-01-09 | 2020-07-06 | 2019-12-19 | in progress | May be a delay with certain vehicles, however, the contingency is to use manufacturers demo vehicles and/or have an arrangement with Hitachi or TPPL/GoPlant can provide short term hire (minimum 2 months). Meeting end of January; if not comfortable with position - approach hire vehicle companies and/or potentially novate Amey rubbish vehicles. 06/02/2020 (KRD): we have the timeline, will have 13 vehicles before go live (likely to have more). Vehicles for novation identified and this list has been sent to AMEY for review 13/02/2020 (SH): ESPO Framework for Hire Vehicles identified as route for contingency hire vehicles. Meeting arranged with best VfM supplier on framework to discuss back-up arrangements. Suppleirs reviewing arrangements due to COVID -19 21/02/2020 - Conference call with CTS RE vehicle requirements and an follow up e-mail sent meeting to be arranged for W/C 02.03.20 05/03/20 JA - face to face meeting 12/03/20 to finalise Short Term Hire arrangements 26/03/20 JA due to COVID - 19 we are reviewing the delivery situation daily and creating mitigations where possible 02/04/2020 (KRD): JA submitted report to SRO (GA) on best case and worst case in terms of vehicle delivery schedule, if impacted by coronavirus 09/04/2020 (KRD): from next week we will communicate to supplier that we need firm confirmation. Where there are gaps we can go out on the YPO to satisfy. Will by 14/04 know what vehicles can be short term hired. 16/04/2020 (KRD): we have info back from suppliers today, meeting next Monday with suppliers. Monday will show initial gaps. End of April confirmation on full-picture.
Procurement | Award Maintenance contract once Tender has finished | John Arnold/Sarah Hadland/ Kevin O'Leary/ Vincent Hunt/ Chuhr Nijjar | 2019-11-01 | 2020-03-31 | 2019-11-01 | in progress: delayed | Tender has been issued and is due back 17/02. Evaluations being carried out 03/03/20 05/03/20 - JA furhter questions to be sent to suppliers before final award can be made 20/03/20 - Unsuccessful supplier being advised 20/03 of exclusion of their tender. Letter of Intent and Officer Decision being drafted for GoPlant. Formal sign-off will follow Cabinet decision in April - standstill letters will be issued, then contract. 02/04/2020 (KRD): awaiting Chuhr's sign-off. Chuhr to be reminded 02/04/2020. Potential for challenge requires risk management 09/04/2020 (KRD): SH and JA meeting with Chuhr Nijar 09/04/2020 to confirm status. 16/04/2020 (KRD): letter of intent due to be sent today (16/04)
Procurement | Award Bunkered Fuel Contract | John Arnold/Sarah Hadland | 2020-01-06 | 2020-05-01 | 2020-01-06 | in progress | Mini-competition for bunker fuel has been re-issued via the LASER Fuel framework for return 17/02 to ensure correct fuel type for Acton Depot. 27/02/20 Award to be given on Gary Alderson return W/C09/03/20 Fuel card requirements need to be confirmed to Commercial Hub. JA - 12.03.20 Needs to be aKOD as over £500K we have chosen our supplier but require sign off at April Cabinet changed date from 24/02/20 to refelct the Cabinet date of 21/04/20 16/04/2020 (KRD): same position as last week.
Procurement | Finish Spec for Occupational Health Contract | John Arnold/Sarah Hadland | 2020-01-06 | 2020-01-31 | 2019-12-06 | Completed | Currently in final stages there are a couple of things to address such as Ill health retirement 30/01/2020 (KRD): just needs to be put into word doc and sent to procurement
Procurement | Confirm Jewson can supply required tools | John Arnold/Sarah Hadland | 2020-01-31 | 2020-02-28 | 2020-01-10 | Completed | Tool list has been priced by Jewson. PO can now be raised.
Procurement | Confirm Office supply route | Sarah Hadland | 2020-02-01 | 2020-02-28 | 2020-01-23 | Completed | Can use Staples contract for initial requirements. PO can now be raised.
Procurement | Place final order for small plant with supplier | John Arnold/Sarah Hadland/ Chirs Welsh | 2020-03-01 | 2020-03-31 | 2020-01-10 | in progress: delayed | List has been created, they have offered a demo before placing order which we will be taking advantage of. Demo for electrical small plant / equipment such as strimmers being held on 06/03/30 JA - 12.03.20 Demo held final list to be created. KRD - 20/03/20 waiting for feedback from Chris Welch's team 02/04/2020 (KRD): position unchanged from last update 09/04/2020 (KRD): JA emailed Chris Welsh on 09/04/2020 to complete. 16/04/2020 (KRD): requires escalation tomorrow (17/04) by JA if this has not been progressed.
Procurement | finalise P.P.E list | John Arnold/Sarah Hadland | 2020-01-06 | 2020-01-31 | 2019-12-06 | Completed | Mini-competition running and tenders due back 24/02
Procurement | Agency contract award | John Arnold/Sarah Hadland | 2020-01-06 | 2020-03-30 | 2019-12-06 | in progress: delayed | Meeting arranged with Pertemps in January 2020 to gather info on current staffing requirements. Potential risk of challenge re: using MSTAR Framework due to LATCOs not being named as permissible users - way forward on this has been agreed by GA. Sarah will review the pricing etc. 24.01.20 06/02/2020 (KRD): need to stipulate requirements. On Sarah Hadland's advice, the required completion date should be moved to March-end. 13/02/2020 (SH) - Meeting to be arranged with Pertemps to agree what they can do under Letter of Intent (subject to senior management agreement). Call-off documentation being completed. 20/03/2020 (SH) - Gary Alderson has signed off Officer Decision to allow Letter of Intent to be issued to Pertemps (being issued 20/03). This will allow them to start work on the contract pending KOD at end of April, when the formal contract will be entered into. 09/04/2020 (KRD): JA and SH meeting with Chuhr 09/04. To confirm position. 16/04/2020 (KRD): position unchanged from last week.
Procurement | finalise H&S system contract (Alcumus) | John Arnold/Sarah Hadland/ Chuhr Nijjar | 2020-01-06 | 2020-01-31 | 2019-12-06 | Completed | Legal have reviewed the Alcumus contract. Comments/proposed amendments have been sent back to IEX (supplier). Have received the revised contract back need to review with Chuhr 30/01/2020 (KRD): Chuhr needs to approve before PO can be created 03.02.20 (JA) Contract signed by EMcK sent to Alcumus PO
Procurement | Finalise Financing Company | John Arnold/Sarah Hadland | 2020-01-06 | 2020-05-29 | 2019-12-06 | in progress (on hold) | List has been finalised by John. The competition for electric vehicles can start January 2020 via Link. 02/04/2020 (KRD): Chuhr needs to sign-off. To be reminded at a meet with Procurement on 02/04/2020. 09/04/2020 (KRD): SH to confirm with Procurement colleagues on what the position is. 16/04/2020 (KRD): tender gone out, finance suppliers to be confirmed by April-end.
Procurement | Approach hire vehicle companies and/or potentially novate Amey vehicles if not comfortable with position | John Arnold/Sarah Hadland |  | 2020-02-28 |  | In progress: delayed | JA is creating a list of Amey contracts we need to novate where the total is under OJEU (£189K) 20/03/2020: agreed that JA, by end of next week, would finalise a list of companies and then this can be matched with Amey's 26/03/20 JA to confirm e-mail with CTS RE vehicle numbers currently we are looking at other suppliers as well 02/04/2020: response re this due on 07/04/2020 09/04/2020 (KRD): pricing and availability info to be received on 15/04.
Procurement | Award Occupational Health Contract | John Arnold/Sarah Hadland | 2020-03-13 | 2020-03-31 | 2020-03-13 | In Progress | 06/02/2020 (KRD): requires final review 13/02/2020 (SH): Tender will be issued 17/02 for return 10/03. 12/03/20 (JA): One Tender back (MediGold) review of Tender to be carried out Friday 13th 20/03/20 (SH) : Clarification meeting w/c 24/03. Then can enter int contract subject to Gary signing OD. 02/04/2020 (KRD): requires Chuhr sign-off. To be reminded 02/04/2020 09/04/2020 (KRD): Chuhr still required to sign off. To be reminded 09/04. 15/04/20 (JA) : Awarded to Medi Gold Award Tender signed off by Gary Alderson & Sarah Hadland. Chuhr to review this week.
Procurement | Award P.P.E supplier contract & place order | John Arnold/Sarah Hadland | 2020-03-13 | 2020-03-31 | 2020-03-13 | In Progress | JA -12/03/20 Tender date pushed back until 12/03/20 review of Tenders to begin from 13/03/20 26/03/2020 - Tender evaluated and Tender Award Report and Officer Decision being drafted. Once signed, suppliers can be informed. 02/04/2020 (KRD): requires Chuhr sign-off. To be reminded 02/04/2020 09/04/2020 (KRD): Chuhr to be pushed again to sign off on 09/04/2020. 15/04/20 (JA): Awarded to Chelmsford. Chuhr to review this week.
Procurement | Storage - find storage for fleet if required | John Arnold/Sarah Hadland | 2020-03-25 | 2020-04-01 | 2020-03-25 | In Progress | Need to find enough storage for the fleet if we cannot do a staggered delivery 20/03/2020 (KRD): phone call with Harrow next week 02/04/2020 (KRD: Harrow can do 10 spaces, will review if they can do more 16/04/2020 (KRD): Housing provided secure garage for tools and small equipment. JA to confirm with supplier.
Note on B1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Milestones should be highlighted bold, with tasks underneath
Note on D1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Where a change is made, this must be noted under 'comments'. What it has changed from and to
Note on E1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Where a change is made, this must be noted under 'comments'. What it has changed from and to
Note on F1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Where a change is made, this must be noted under 'comments'. What it has changed from and to
Note on G1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Where a change is made, this must be noted under 'comments'. What it has changed from and to
Note on B58: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: DATES NEED TO BE ADDED ONCE ELI INFORMATION IS PROVIDED
Note on B114: Killian Rosato-Dooey: We need to specify what tasks are involved to achieve this deliverable
Note on B243: John Arnold: Tasks to complete Milestone

## Depot (hidden)
Milestone>task | Business Plan 14 points | Duration | Start | Status | Finish | Resource Names | Comments | Necessary capacity to deliver? | Necessary expertise to deliver? | Necessary budget to deliver?
Workshops\Garages | 9 | 16 days | Thu 02/01/20 | In progress | Thu 23/01/20
Asbestos work | 9 | 16 days | Thu 02/01/20 | In progress | Thu 23/01/20 | Aspects
Phase 1 Asbestos Removal Plant Room | 9 | 3 days | Thu 02/01/20 | In progress | Sun 05/01/20
Mobilize on site | 9 | 1 day | Thu 02/01/20 | Complete | Thu 02/01/20 | Aspects
Sheet up Plant Room | 9 | 1 day | Thu 02/01/20 | Complete | Thu 02/01/20 | Aspects
Scaffold in Plant Room | 9 | 1 day | Thu 02/01/20 | Complete | Thu 02/01/20 | Aspects
Encapsulate Plant Room | 9 | 1 day | Fri 03/01/20 | Complete | Fri 03/01/20 | Aspects
Air Test Plant Room | 9 | 2 days | Fri 03/01/20 | Complete | Sun 05/01/20 | Riverside
Phase 2 Asbestos Removal Bus Garages | 9 | 15 days? | Fri 03/01/20 | In progress | Thu 23/01/20
Scaffolding | 9 | 3 days | Fri 03/01/20 | Complete | Tue 07/01/20 | Aspects
Sheeting up | 9 | 4 days | Mon 06/01/20 | Complete | Thu 09/01/20 | Aspects
Strip A.I.B. Ceiling Soffit | 9 | 2 days | Fri 10/01/20 | Complete | Mon 13/01/20 | Aspects | 15/01/2020 (KRD): Nishant informed this is delayed
Fine Clean Enclosure | 9 | 2 days | Fri 10/01/20 | Complete | Sun 12/01/20 | Aspects | 15/01/2020 (KRD): Nishant informed this is delayed
Air Test Enclosure | 9 | 2 days | Sat 18/01/20 | Complete | Sun 19/01/20 | Riverside
Strip down Enclosure | 9 | 2 days | Fri 10/01/20 | Complete | Mon 13/01/20 | Aspects | 15/01/2020 (KRD): Nishant informed this is delayed
Dismantle Scaffolding | 9 | 2 days | Wed 22/01/20 | Complete | Thu 23/01/20 | Aspects | 26/01 - Gauri - Completed on time and Certficate of reoccupation is shared with the site manager
Roof Works | 9 | 42 days | Thu 02/01/20 | Delayed: not started | Fri 28/02/20 | Global Waterproofing | End date pushed back to end of Marach but will include Heating completion
Phase 3 Roof Works | 9
Inspections | 9 | 1 day | Thu 02/01/20 | Delayed: not started | Thu 02/01/20 | Global Waterproofing
Pre-Start Meeting | 9 | 1 day | Mon 13/01/20 | Delayed: not started | Mon 13/01/20 | Global Waterproofing
Site Set Up | 9 | 3 days | Mon 20/01/20 | Delayed: not started | Wed 22/01/20 | Global Waterproofing
External Cladding | 9 | 5 days | Thu 23/01/20 | Not started | Wed 29/01/20 | Global Waterproofing
Bird netting | 9 | 2 days | Thu 30/01/20 | Not started | Fri 31/01/20 | Extreme Environmental
Scaffolding/ roof set up | 9 | 2 days | Wed 29/01/20 | Not started | Thu 30/01/20 | Global Waterproofing
Roof Coatings/ Roof lights | 9 | 18 days | Thu 30/01/20 | Not started | Sat 22/02/20 | Global Waterproofing
Finalise | 9 | 2 days | Sun 23/02/20 | Not started | Mon 24/02/20 | Global Waterproofing
Clear Site | 9 | 1 day | Thu 27/02/20 | Not started | Thu 27/02/20 | Global Waterproofing
Completion | 9 | 1 day | Fri 28/02/20 | Not started | Fri 28/02/20 | Global Waterproofing
Heating works | 9 | 20 days? | Mon 02/03/20 | Not started | Fri 27/03/20 | TBD
Re-instating heating at workshops\garages | 9 | 20 days | Mon 02/03/20 | Not started | Fri 27/03/20 | TBD
Clearing of rubbish at the site | 9 | 18 days? | Wed 18/12/19 | Delayed: not started | Fri 10/01/20 | TBD | Looks like has started need to speak to Ony
Clearing of rubbish at the site for lanscaping | 9 | 18 days | Wed 18/12/19 | Delayed: not started | Fri 10/01/20 | TBD
Parking | 9 | 0 days | Mon 02/03/20 | Not started | Mon 02/03/20 | TBD
Parking area for 150 vehicles | 9 | 0 days | TBD | Not started |  | TBD | 24/01-Kevin to provide vehicle diension for parking area mapping with Tony and lease closure with Jessica
20 Electric Charge points | 9 | 0 days | TBD | Not started |  | TBD
All other requirements | 9 | 7 days | Mon 02/03/20 | Not started | Tue 10/03/20 | TBD
Facilities currently in use by AMEY to be provided to GEL | 9 | 7 days | Mon 02/03/20 | Not started | Tue 10/03/20 | TBD

## PMO support (hidden)
Workstream | Key contact/Workstream Lead | Work completed | Outstanding tasks
Finance | Christopher Neale | John Arnold and Killian Rosato-Dooey met with Christoper Neale on 20/11/2019 and transcribed into this Spreadsheet the remaining tasks under the Finance Workstream. The 'Finance' Sheet contains an exhaustive list of remaining tasks that will require weekly monitoring from 02/01/2020. Killian has set up weekly-recurring meetings from January 2020 through go-live between Christopher, John, and himself. | 1) weekly monitoring from January 2020 2) assurance review 3) Killian and John to meet W/C 16/12/2019 to agree upon which tasks under this Workstream have been completed. This needs to be clearly visible in this Spreadhseet.
HR | Sharon Brown | John and Killian met with Sharon Brown on 02/12/2020 to update the HR Workstream Plan. This meeting ensured we have oversight of the exhaustive list of remaining tasks, and other important factors such as responsible officer and timelines. Killian has set up weekly-recurring meetings from January 2020 through go-live between Sharon, John, and himself. | 1) a (working) meeting between Sharon, John, Killian, Chris, and Lara Balogun to address gaps in information. These gaps include task start and finish dates, and task owner information. 2) assurance review 3) Killian and John to meet W/C 16/12/2019 to agree upon which tasks under this Workstream have been completed. This needs to be clearly visible in this Spreadhseet.
ICT (including depot work package) | Shahzad Rehman; Nishant Bannayya | Killian has liaised with Shahzad to ensure the Programme-level Plan (i.e. this Spreadhsheet) contains oversight of the ICT Workstream Plan. This Plan, as reflected in this Spreadhseet, is up-to-date as of 11/12/2019. Requirements for the Depot work package were shared with Nishant on 21/11/2019 in order for plan to be produced. Killian has set up weekly-recurring meetings from January 2020 through go-live between Shahzad, John, and himself. | 1) project plan for the Depot work package 2) assurance review 3) Killian and John to meet W/C 16/12/2019 to agree upon which tasks under this Workstream have been completed. This needs to be clearly visible in this Spreadhseet.
Procurement | Sarah Hadland | Killian and John met with Sarah Hadland on 26/11/2019, and this Spreadsheet contains up-to-date oversight of the workstream plan as of 06/12/2019. Killian has set up weekly-recurring meetings from January 2020 through go-live between Sarah, John, and himself. | 1) assurance review 3) Killian and John to meet W/C 16/12/2019 to agree upon which tasks under this Workstream have been completed. This needs to be clearly visible in this Spreadhseet.
*Health and Safety | TBC |  | 1) meeting with John, Killian, and H&S to take place W/C 16/12/2019 to a) ensure all remaining tasks are captured b) assign task ownership c) assign deadlines d) assurance review (expertise, capacity etc.) 2) Killian and John to meet W/C 16/12/2019 to agree upon which tasks under this work package have been completed. This needs to be clearly visible in this Spreadhseet.
*Legal | Chuhr Nijjar | Killian has liaised with Chuhr to produce a plan for this work package that is up-to-date as of 12/12/2019. Killian has set up weekly-recurring meetings from January 2020 through go-live between Sarah, John, and himself. | 1) Chuhr to provide greater granularity in terms of tasks under milestones, and start and finish dates. 2) Killian and John to meet W/C 16/12/2019 to agree upon which tasks under this work package have been completed. This needs to be clearly visible in this Spreadhsheet. 3) assurance review
*Communications | Keith Lewis |  | 1) project plan needs producing 2) assurance review

## Finance (hidden)
Assurance
Task/Milestone | Business Plan 14 Points | Task owner | Area | Required completion date | Planned start date | Actual start date | Status | Comments | Additional funding required? (Y/N) if yes, specify (£) | Necessary capacity to deliver? | Necessary expertise to deliver? | Necessary budget to deliver?
Interest rate determination on loan for state aid purposes | 3 | Chris Neale | Service Finance & Corporate Finance, & Legal | 2020-02-28 | 2019-11-27 | 2019-10-01 | On track | 27/1/2020 Meeting of Corporate Finance deferred to 30/1 to discuss accounting treatment that might include this 17/1/2020 Meeting requested in Finance for Mon 27/1 re Lease Finance accounting at which will agree next steps for this. 10/1/2020 LINK agreed re lease finance to ensure quotes requested for funding LATCO direct also, so that covered. (Chris separately to look at documenting confirmation that interest rates on any council loans correct to avoid being state aid). 10/12/2019 Chris requested Tim and Sarah re the timing of this, following up request of 11/11, where requested that the quotes include leasing via the Council and also direct to LATCO to show the difference to be charged by Council to avoid providing state aid. 10/12/2019 Chris also followed with Peterborough LATCO re 10/11 request re the calculation of the state aid compliant interest on loans from the council KRD 27/11/2019 - What is involved to get this figure |  | Yes | Yes | Yes
Agree payment mechanism for LBE /GEL contract and arrangement between GEL and LBE | 3 | Chris Neale/ Shabana Kausar / Simon Peet | Service Finance & Corporate Finance, & Legal | 2020-02-15 | 2019-11-27 | 2019-10-01 | In progress | 27/1/2020 Meeting of Corporate Finance deferred to 30/1 to discuss accounting treatment that might include this 23/1/2020 Noted to Simon Peet that await answer and requested he get answer in next meeting with PwC. 9/1/2020 Requested advice from Catherine Porter of PwC and await answer. 6/1/2020 timescale of Jan not likely, however not absolutely nec till later 1/12/2019 Awaits SLA being further developed, to then progress |  | Yes | Yes | Yes
Accounts Payable SLA deliverable and volumes and KPIs | 3 | Liz Lyons (formerly Georgia) | Service Finance, & Accounts Payable | 2020-01-31 | 2019-11-27 | 2019-10-01 | In progress | 25/2/2020 Needs Chuhr and John Arnold to confirm if now sorted. 13/1/2020 Georgia Hoare provided draft to John A, Chris and John P to confirm. 13/1/2020 Georgia Hoare confirmed would complete in next few days what possible now, conferring with John Parmenter where needed, and ensure note of what awaits further decisions, for her successor Liz. 7/1/2020 Georgia Hoare proposed would attend to Wed 8/1/2020 so completed this week. 6/1/2020 reminded Georgia Hoare. 10/12/2019 reminded Georgia Hoare re proforma given 27/11 to her so has info to complete |  | Yes | Yes | Yes
Vehicle lease quotes | 3 | Chris and Sarah | Service Finance and Procurement | 2020-02-02 | 2019-11-27 | 2019-05-01 | In progress | 24/2 Asked LINK to confirm when will provide10/1/2020 Meeting held by Tim with LINK to ensure handover to his successor and that LINK aware of what needed next. 7/1/2020 Chris noted meeting planned with Link 10/1/2020 10/12/2019 Chris requested Tim and Sarah provide their outline planned timetable |  | Yes | Yes | Yes
Insurance | 3 | Chris Neale and Sarah Hadland & Ewan | Service Finance & Insurance | 2020-07-01 | 2020-07-01 | 2020-07-01 | In progress | 8/1/2020 Mary confirmed for Kevin and John that insurance of new fleet subleased to Amey would need be via Amey's insurer. Rest of insurance procurement on track, for earlier awred 9/3/2020. 7/1/2020 Chris organised meeting of John and Kevin with Mary 8/1/20. 22/7/2019 Cabinet report authorised procurement, with 30/8/2019 Draft Tender Document, with 6/9/2019 Agree finalised tender specification, with 20/11/2019 Tenders back, with 21/2/2020 Final decision, 9/3/2020 Award Contract |  | Yes | Yes | Yes
Making tax digital | 3 | John Parmenter | IT Finance | 2020-03-05 |  |  | In progress | 14/1/2020 confirmed on track, with main item required from HR Payroll, due in few weeks, and no items needed from Finance, next update planned for Wed 26/2. 8/1/2020 requested clarification meeting Tues 14/1/2020, James Pugh 9/1 noted main deliverable is from HR Payroll (not Finance) and the project manager that would invite to 14/1/2020 meeting 7/1/2020 John requested meeting including Georgia, John wishing to attend also 6/1/2020 Chris noted the request to John Parmenter 10/12/2019 Chris asked John P to confirm following note here 27/11/2019 - KRD asked Chris please specify dates |  | Yes | Yes | Yes
Register for VAT | 3 | Chris Neale | Service Finance | 31/04/2020 | 2020-01-15 | ? | Keeping check on | 14/1/2020 agreed not likely to be before April 2020 need. 7/1/2020 agreed to discuss further with John Parmenter at 14/1/2020 making tax digital meeting. 10/12/2019- Chris requested dates from John Pamenter following up request of 23/10/2019 KRD 27/11/2019 - Chris please can you specify dates for this task |  | Yes | Yes | Yes
Finalise budget allocation per service | 3 | Chris Neale | Service Finance | 2020-01-31 | 2019-12-02 | 2019-12-02 | Done | 9/1/2020 Completed, though pre any refinement by service or further change re LLW. Chris to share file (copy viewable without links) 29/1/2020. JA 04/12/2019 -JA & CNe met 02/12/2019 and split remaining costs, Chris now to input to complete by mid Jan |  | Yes | Yes | Yes
PAYE registering | 3 | Chris Neale | Service Finance | 2020-05-04 | 2020-01-31 | ? | Not started | 10/12/2019 Chris noted update, provided 23/10.2019, that should not start to register payroll until 4 week before have staff on payroll if do on the phone (max 8 weeks before have staff on payroll, if online), to avoid having payroll fines of £100-£400. KRD 27/11/2019 - Chris please can you specify dates for this task |  | Yes | Yes | Yes
GEL Bank account set up | 3 | Simon Peet / Chris Neale | Corporate Finance / Service Finance | 2020-01-27 | 2020-11-01 | 2020-11-01 | In progress: delayed | Monday 27/1/20 Lloyds confirmed (Hayleigh) that had been told (Gabriel) that should be done by Friday 24/1 and would chase to find out why not and when would. Monday 13/1/2020 Lloyds confirmed had everything for bank account to be opened, hopefully this week, and had SUN indirect submitter form re payroll (sent original in post that day also) that might be completed the following week. 9/1/2020 SUN Indirect Submitter form drafted and given to Lara and to Kayleigh (of Lloyds bank) for final points to be concluded so then when sorted then can be put to Alison to sign, for SUN aspect to be sorted thereafter. Regarding separate (non SUN) point of bank account being set up, Bank have all other information for setting up bank account which can hopefully be set up by 17/1/2020, as bank 6/1/2020 said this can be done in a few days. 9/1/2020 SUN Indirect Submitter form drafted and provided to Karmveer to complete based on Ealing Pension Fund form he completed. 9/1/2020 Deborah confirmed sent in remaining details requested by bank and with which provided for sending in Nov 2019. 7/1/2020 KAP confirmed sent in, and Deborah to provide details of email so Chris can also be in contact with them. 6/1/2020 Chris requested Simon to submit Key Account information for new director Alison to bank, Alison confirmed had left Key Accout information for Simon on 20/12 when Simon on leave, following 6/12/2019 Chris chasing Simon for whether sent as Alison Key information signed left with Simon 20/12 on leave till 6/1. |  | Yes | Yes | Yes
London Living Wage to calculate impact of 20p increase | 3 | Chris Neale | Service Finance | 2020-01-31 | 2020-12-16 |  | In progress | Seeking to start last week Jan 2020 |  | Yes | Yes | Yes
Handover information for GEL New Finance Manager | 3 | Chris Neale | Service Finance | 2020-03-15 | 2020-02-01 | 2020-02-01 | Not started |  |  | Yes | Yes | Yes
Sort out appointment of auditor | 3 | Chris Neale / Simon Peet | Service & Corporate Finance | 2020-02-28 | 2020-02-01 | 2020-01-06 | To do in Feb | 27/1/2020 Chris asked Deloitte again for response this week. 10/1/2020 Simon checking with Deloitte. 7/1/2020 Chris asked Simon to ask Deloitte how wished formalised. 6/1/2019 Chris got info from Simon Peet re Deloittes auditors, and asked Simon how to progress, and from Simon re PwC tax advisor. |  | Yes | Yes | Yes
Sort out if tax advisor required | 3 | Chris Neale / Simon Peet | Service & Corporate Finance | 2020-01-06 | 2020-02-01 | 2020-01-06 | Completed | 9/1/2020 Chris contacted PwC outlining main points on which may seek advice. 6/1/2020 Chris got info from Simon Peet re PwC tax advisor. |  | Yes | Yes | Yes

## Communications (hidden)
Milestone > task | Business Plan 14 Points | Task owner | Dept/team/service responsible | Required completion date | Planned start date | Actual start date | Status | Comments | Additional funding required? (Y/N) if yes, specify (£) | Necessary capacity to deliver? | Necessary expertise to deliver? | Necessary budget to deliver?
Gaining resource (potentially have someone, 0.5FTE)
Writing a comms plan
Milestones:
development of plan
Internal staff comms for Amey staff, countdown (start Feb)
Vehicle deliveries events (post launch)
Staff survey
Social media campaign (post launch)
Video series
Building relationship with local secondary school
*in 16/01 meeting with Keith, it was agreed that a dedicated comms resource will be found to establish the comms workplan

## ICT (hidden)
Up-to-date plan as of 11/12 | [7 empty] | Assurance
Task/Milestone | Business Plan 14 points | Task owner | Area | Required completion date | Planned start date | Status | Comments | Necessary capacity to deliver? | Necessary expertise to deliver? | Necessary budget to deliver?
HR |  |  | HR and BW Team | 2020-04-01 | 2019-11-08 | In progress
Send payroll info to HR |  |  | BW Team | 2019-11-08 | 2019-11-08 | Completed
Payroll file from HR to be received by BW team |  |  | HR | 2019-01-22 | 2019-11-11 | In progress: delayed | 14/01/2020 (KRD): delayed by one week, update from HR on 22/01
HR BACS file updated |  |  | HR | 2020-04-01 | 2020-04-01 | Not started
MTD - VAT Tax codes into iTrent |  |  | HR | 2019-12-31 | 2019-12-31 | Delayed: not started | 14/01/2020 (KRD): change control possibly required according to Shahzad
SUN (Service User) numbers for bank account provided to HR |  | Christopher Neale | Finance | 2019-12-31 | 2019-12-31 | Delayed: in progress | 14/01/2020 (KRD): delayed, hope to have by end of January. No impact as of yet
Business World GEL | 8 | James Pugh | BW Team | 2020-07-07 | 2019-12-19 | In progress
GEL BW Client Build | 8 |  | BW Team | 2020-04-06 | 2019-12-19 | In progress
Design | 8 |  | BW Team | 2019-12-30 | 2019-12-19 | Completed
System set up | 8 |  | BW Team | 2020-01-14 | 2020-01-01 | Completed
Accounts payable | 8 |  | BW Team | 2020-02-04 | 2020-01-15 | In progress
Accounts receivable | 8 |  | BW Team | 2020-02-19 | 2020-02-05 | Not started
Integration | 8 |  | BW Team | 2020-03-05 | 2020-02-20 | Not started
Making tax digital installation of BW module and client | 8 |  | BW Team | 2020-03-05 | 2020-02-20 | Not started
Systems test and fix | 8 |  | BW Team | 2020-03-19 | 2020-03-06 | Not started
Set up balance tables, planner revenue, capital, logistics, actuals data | 8 |  | BW Team | 2020-03-24 | 2020-03-20 | Not started
Set up basic reporting, AP, AR, trial balance | 8 |  | BW Team | 2020-03-30 | 2020-03-24 | Not started
Banking set up facility for manual upload of statement into BW | 8 |  | BW Team | 2020-04-02 | 2020-03-31 | Not started
BW Development and system testing complete | 8 |  | BW Team | 2020-04-06 | 2020-04-03 | Not started
GEL UAT Post Build Test and Train | 8 |  |  | 2020-07-07 | 2020-04-07 | Not started
BW UAT | 8 |  | MS (ICT applications development) | 2020-04-27 | 2020-04-07 | Not started
BW Training | 8 |  | MS (ICT applications development) | 2020-05-04 | 2020-04-21 | Not started
BW - data input | 8 |  | Business/Finance | 2020-05-08 | 2020-05-05 | Not started
Testing, ready for go-live | 8 |  | Business/Finance/HR | 2020-07-02 | 2020-05-11 | Not started
Go live/no go-live decision | 8 |  | Programme Team | 2020-07-03 | 2020-07-03 | Not started
Go live | 8 |  | Finance Apps support | 2020-07-07 | 2020-07-07 | Not started
GEL Business Applications | 8 |  | Supplier and ICT | 2020-06-02 | 2019-09-25 | In progress
Initiation | 8 |  | Supplier PM | 2020-11-14 | 2019-09-25 | Completed
Whitespace Contract (Gcloud) sign-off | 8 |  | LBE/Supplier | 2020-11-29 | 2019-10-22 | Delayed: in progress
ICT technical standards and FOI | 8 |  | LBE ICT PM | 2019-11-18 | 2019-11-07 | Completed
Gcloud ICT requirements and plan | 8 |  | ICT PM / Business PM / Procurement | 2019-11-28 | 2019-10-22 | Completed
Procurement elements | 8 | Sarah Hadland | Procurement | 2019-11-28 | 2019-10-22 | Completed
Sign-off | 8 | Edward Axe | ICT | 2019-11-29 | 2019-11-29 | Delayed: in progress | 21/01/2020 (KRD): still needs to be signed. Meeting arranged for 27/01/2020 to progress. Completion date moved from 29/11/2019 to 31/01/2020.
Data gathering | 8 |  |  | 2019-11-29 | 2019-10-03
Prepare LLPG data | 8 |  | ICT Applications Support | 2019-10-31 | 2019-10-14 | Completed
Prepare FTP | 8 |  | ICT Infrastructure | 2019-11-08 | 2019-10-14 | Completed
FTP LLPG data to WS | 8 |  | ICT Infrastructure | 2019-11-12 | 2019-11-11 | Completed
Whitespace data gather | 8 |  | Supplier PM | 2019-11-28 | 2019-11-13 | Completed
COU process in place | 8 |  | LBE ICT PM | 2019-11-29 | 2019-11-29 | Completed
Whitespace configuration | 8 |  | Supplier PM | 2019-01-02 | 2019-11-29 | Completed
Whitespace mobile configuration | 8 |  | Supplier PM | 2019-11-27 | 2019-11-25 | Completed
Whitespace workshop | 8 |  | Supplier and business | 2019-12-06 | 2019-12-06 | Completed
Internal testing | 8 |  | Supplier PM | 2019-01-10 | 2019-01-06 | Delayed: in progress | 21/01/2020 (KRD): more testing to be done
vehicle kit out | 8 |  | Supplier PM | 2020-02-14 | 2020-02-03 | Not started | 14/01/2020 (KRD): do not know when vehicles will be devlivered and cannot therefore have start and finish date
CRM integration | 8 |  |  | 2020-02-27 | 2019-11-04 | In progress
Contender integrations - proposal | 8 |  | ICT | 2019-11-28 | 2019-11-04 | In progress
Requirement - initial meet with Contender | 8 | Faisal and Michael T | ICT | 2019-11-04 | 2019-11-04 | Completed
Receive quote from Contender | 8 | Faisal and Michael T | ICT | 2019-11-11 | 2019-11-05 | Completed
Confirm Contender quote as acceptable | 8 | Faisal and Michael T | ICT | 2019-11-25 | 2019-11-12 | Completed
Generate PO and send to Contender | 8 |  | ICT PM | 2019-11-28 | 2019-11-26 | Completed
Contender integration specification | 8 | Faisal and Michael T | ICT | 2019-11-29 | 2019-11-29 | Completed
Contender integration development and testing | 8 |  | Contender | 2020-02-27 | 2019-12-02 | In progress
Training | 8 |  | Supplier PM and business | 2020-02-20 | 2020-01-27 | Not started
UAT | 8 |  | Business | 2020-04-06 | 2020-03-10 | Not started
Ready for go-live - parallel running | 8 |  | ICT/Supplier/business | 2020-04-14 | 2020-04-14 | Not started
Analytics delivery | 8 |  | Supplier PM | 2020-05-27 | 2020-04-15 | Not started
Complete go-live by turning off parallel running | 8 |  |  | 2020-06-02 | 2020-06-02 | Not started
GEL ICT Infrastructure and Hardware | 8 |  | ICT PM | 2020-04-06 | 2019-10-01 | In progress
Requirements | 8 |  | DH / ICT PM | 2019-10-01 | 2019-10-01 | Completed
Domain names | 8 |  | ICT Infrastructure | 2019-10-07 | 2019-10-01 | Completed
Site surveys | 8 | Tony Gavaghan | ICT | 2019-10-22 | 2019-10-22 | Completed
Order and receive kit | 8 |  | ICT PM | 2020-01-20 | 2019-12-17 | Delayed: in progress | 20/01/2020 (KRD): cannot happen until the PID is signed off
Order and receive BT lines | 8 |  | ICT Infrastructure | 2020-02-03 | 2019-12-17 | Delayed: not started | 20/01/2020 (KRD): ordered but not yet received
Network/wifi implement | 8 |  | ICT Networks | 2020-02-24 | 2020-02-04 | Not started
Build hardware of site | 8 |  | ICT PM | 2020-02-24 | 2020-01-21 | Delayed: not started
Desktop hardware - implement | 8 |  | ICT PM | 2020-03-02 | 2020-02-25 | Not started
Telephony - implement | 8 |  | ICT PM | 2020-03-09 | 2020-02-25 | Not started
Printers - implement | 8 |  | ICT PM | 2020-03-09 | 2020-02-25 | Not started
Implement furniture | 8 |  | ICT PM | 2020-02-17 | 2020-01-21 | Not started
Test and completion | 8 |  | ICT PM / Business | 2020-04-06 | 2020-03-10 | Not started
Support ICT | 8 |  | ICT PM | 2020-07-09 | 2019-11-27 | In progress
Commercials - ICT | 8 |  | ICT Commercials | 2020-01-16 | 2019-11-27 | In progress: delayed | 14/01/2020 (KRD): due to be finished on 16/01/2020 21/01/2020 (KRD): it has been escalated. It has been sent to Peter Greenham
Business applications support | 8 |  | ICT Applications Support | 2020-07-09 | 2019-12-17 | Delayed: not started | 14/01/2020 (KRD): due to start on 20/01/2020 (change from 17/12/2020) 21/01/2020 (KRD): start date changed to 06/07/2020 (changed from 20/01/2020)
Business world support | 8 |  | ICT Applications Support | 2020-07-09 | 2019-12-17 | Delayed: not started | 14/01/2020 (KRD): due to start on 20/01/2020 (change from 17/12/2020) 21/01/2020 (KRD): start date changed to 06/07/2020 (changed from 20/01/2020)
Network support | 8 |  | ICT Infrastructure | 2020-07-09 | 2019-02-25 | Not started | 14/01/2020 (KRD): due to start on 30/03/2020 (change from 25/02/2020)
Hardware support | 8 |  | ICT Operations | 2020-04-23 | 2019-12-17 | Delayed: not started | 14/01/2020 (KRD): due to start on 30/01/2020 (change from 17/12/2020) 21/01/2020 (KRD): start date changed to 24/02/2020 from 30/01/2020
HOTS sign-off | 8 |  | ICT Operations | 2020-06-25 | 2019-12-17 | Delayed: not started

## Procurement (hidden)
Procurement Purchase Type |  | Business Plan 14 points | Delivery Date | Competition Date | Decision Date (Gary's Authorisation) | Order Date | Responsible Officer/Commercial Hub Support | Update | Outstanding Tasks | Comments | Novation - LATCO/Council | Authority received (from the April 2019 cabinet) | Forward Plan date
Fleet | Done | 12 | May to June 2020 (circa 10 vehicles prior for driver familiarisation, staggered thereafter) | Completed | 28th May 2019 | End of May 2019 | John/Rakhee | May have a delay with some vehicles, Awarded 144 and removed 32T hook lorry. Potentially some delays with vehicle supply. Best VfM hire vehicle supplier identified from ESPO Framework. Meeting arranged to dicus contingency arrangements 21/02. | * Dec 19 - Confirm LBE legal position on late fleet delivery * Jan 20 - Confirm timetable for fleet delivery with suppliers * Feb 20 - Approach hire vehicle companies and/or potentially novate Amey vehicles if not comfortable with position |  | Council (just leased to LATCO) | Rec: 1.1 - Authority Complete | N/A
Light Commercial Fleet |  |  | May to June 2020 (circa 10 vehicles prior for driver familiarisation, staggered thereafter) | In Proces | January 2020 | February 2020 |  |  |  |  | Council | Rec: 1.6 - Delegated Authority to the Director of Environment to hire. | Currently below £500k
Plant |  |  | May to June 2020 (circa 10 vehicles prior for driver familiarisation, staggered thereafter) | Completed | 28th May 2019 | End of May 2019 | John/Rakhee | Awarded Large and Medium Plant. | Small plant is outstanding, need to speak to Chris W re: award for the 1.8T trailers is this still correct? |  | Council (just leased to LATCO) | Rec: 1.4 - Authority Complete | N/A
ICT - Line of Business |  | 8 | March 2020 | Completed | September 2019 | September 2019 | John/Rakhee | Whitespace is the chosen supplier. Contract being finalsed. Need to agree route for hardware - either exceptin or via YPO DPS mini-compettion. | * w/c 02/12 - Confirm whether telematics is required in Whitespace contract. *w/c 05/12 - Confirm whether telematics can be included in Whitespace contract *w/c 05/12 - finalise Whitespace contract and issue for signing. |  | Council (just leased to LATCO) | Rec 1.12 - Delegate authority to Director of Environment to finalise the optimum solutions for delivery. | Currently below £500k
Maintenance | KOD | 9 | May to June 2020 (circa 10 vehicles prior for driver familiarisation, staggered thereafter) | December 2019 | January 2020 | January 2020 | John/Rakhee | Tenders due back w/c 17th February. Expecting at least to bids. |  |  | Council | Rec: 1.2 - Delegated Authority to the Director of Environment to consider the optimum solution for maintenance.
Fuel (Bunker and Shell cards) | KOD | 12 | July 2020 | January 2020 | January 2020 | February 2020 | John/Rakhee | Bunker fuel tender reponses due via the LASER Framework w/c 17th Feb | * w/c - 02/12 - Confirm fuel volumes and other minor details * w/c 09/12 - LASER to issue LBE requirements to confirm supplier interest (supplier interest will then dictate whether direct award or mini-competition) *w/c 16/12 - determine whether using direct award or mini-competition & get agreement to proceed from Gary. timetable to be updated in due course as will change depending on direct award versus mini-compete options. * ASAP - Confirm required details to place Shell card orders |  | LATCO | Rec: 1.3 - Delegated Authority to the Director of Environment to conduct a mini competition or direct award on a framework.
Occupational Health & Drug & Alcohol Testing | OF |  | May 2020 | January 2020 | February 2020 | March 2020 | John/Rakhee | Mini-comp to start week commencing 17th Feb. | * Dec 19 - Tender docs to be completed * Jan 20 - Issue mini competition * Feb 20 - Evaluate & award * March 20 - Order date |  | LATCO | Rec: 1.9 - Authorised the Director of Environment to conduct a mini competition or direct award.
Insurance | KOD | 3 | July 2020 | August | September 2019 | November 2019 | John/Rakhee/Chuhr | LATCO has been included with the new Insurance tender. | Insurance to update |  | Council | ?
Equipment - Hand tools | OD |  | May 2020 | January 2020 | February 2020 | March 2020 | John/Rakhee | Pricing returned via Jewson as Council Material supplier; new account being set up for GEL viaJewson and PO being raised. | *Dec '19 - Confirm whether LBE Materials Contract (via Jewson) looks suitable for these This will then determine further timetable. |  | LATCO | Rec: 1.7 - Authority Complete | N/A
Equipment - Cleaning | N/A |  | May 2020 | January 2020 | February 2020 | March 2020 | John/Rakhee | Likely to now be accessing via arrangements with FM | * Jan 2020 - confirm whether any cleaning materials/suppliers required for procurement *Feb 2020 - identify potential Framework (if required) Timetable to be updated in due course as will change depending on wheter a procurement is required. |  | LATCO | Rec: 1.7 - Authority Complete | N/A
Equipment - Office Supplies | OD |  | May 2020 | May 2020 | May 2020 | June 2020 | John/Rakhee | Likely to now be accessing via arrangements with FM | * May 2020 - Confirm office supplies required (if any required) *June 2020 - place orders for delivery prior to July via LBE Office Depot contract |  | LATCO | Rec: 1.7 - Authority Complete | N/A
Equipment - Supplies (jerricans, dustpans, step ladders) | N/A |  | May 2020 | January 2020 | February 2020 | March 2020 | John/Rakhee | Likely to now be accessing via arrangements with FM | *Dec '19 - Confirm whether LBE Materials Contract (via Jewson) looks suitable for these This will then determine further timetable. |  | LATCO | Rec: 1.7 - Authority Complete | N/A
Furniture | N/A |  | May 2020 | April 2020 | April 2020 | May 2020 | John/Rakhee | Furniture procurement routes available through Framework. Can direct award once furniture requirements estalished. | * April 2020 - confirm furniture required. * May 2020 - source furniture via existing spare items or procure via LBE Office Depot contract. |  | LATCO | Rec: 1.7 - Authority Complete | N/A
Misc (Road tax) | N/A |  | May 2020 | November 2019 | December 2019 | December 2019 | John/Rakhee | These contracts will include a novation clause. | Service Area to arrange | Service Area to arrange | LATCO | Rec: 1.7 - Authority Complete | N/A
PPE | OD | 7 | May 2020 | December 2019 | January 2020 | February 2020 | John/Rakhee | Mini - competition is being run through ESPO Framework. Responses due w/c 24th February. | * Confirm uniform requirements - JA - complete * w/c 02/12 - confirm Framework - SH/JA - send Framework docs to Legal to confirm - SH * w/c 09/12 - confirm branding requirements, delivery timescales, quality & price weighting * w/c 09/12 - issue mini -competition * w/c 13/01 - receive responses * w/c 21/01 - evaluate * w/c 28/01 - interview if required *w/c 03/02 - award contract , place orders (depending on lead times required) |  | LATCO | Rec: 1.7 - Authority Complete | N/A
Storage | N/A |  | April 2020 | November 2019 | December 2019 | March 2020 | John/Rakhee | Clarification require on need for storage. | None -remove? | Not required? | LATCO | Rec: 1.7 - Authority Complete | N/A
Stationery | OD |  | May 2020 | May 2020 | May 2020 | June 2020 | John/Rakhee | Need to set up separate accout with OD. These contracts will include a novation clause. | * May 2020 - Confirm stationery supplies required *June 2020 - place orders for delivery prior to July via LBE Office Depot contract | Using LBE Stationery Contract with Office Depot. | LATCO | Rec: 1.7 - Authority Complete | N/A
Branding |  |  | Unknown | Unknown | Unknown | Unknown | Marcomms/Service | Logo has been received and passed to uniform suppliers. | w/c 02/12 - Communications to confirm branding information/documentation |  | LATCO | Was not in scope at the time.
Agency | KOD |  | July 2020 | December 2019 | February 2020 | March 2020 | John/Rakhee | Have had initial discussions with Pertemps. Propose procurement route is via MSTAR Framework (Direct award to Pertemps). Documentation and pricing being finalised for agreement with GEL MD. | *w/c 09/12 - Gary (?) to confirm okay to proceed with MSTAR Framework; given risks as detailed in Comments section. * Jan 2020 - Complete required documentation for direct award * Feb 2020 - Award contract * March 2020 - Place order |  | LATCO | Rec 1.10 - Authority Complete to negoitaiton with local suppliers.
Health and Safety | OD |  |  | November 2019 | December 2019 | June 2020 | John/Rakhee | We will be using the Council's existing Alcumus contract. This will need to be novated to GEL. Contract agreed | * w/c 02/12 - Finalise Alcumus Contract |  | Council | ?
Financing Company | KOD | 3 | May 2020 | February 2020 | May 2020 | June 2020 | Tim/Finance | Currently have indicative costs. Link Asset Services procurement to commence Late Feb 2020. | * Date TBC - Remaining Pos to be raised. The following vehicles have not had Po’s raised against them: - 20 electric panel vans - 1 Ford Transit van - 2 SWB panel vans Outstanding Plant PO’s - Pedestrian Roller Bomag BW71E-2 X 1 - X10 Double Axel Trailer suitable for 1.8T Excavator (Ifor Williams GX106 Trailer) |  | Council | Rec: 1.5 - Authority Complete | N/A
Mobile Phones | N/A |  | June 2020? | January 2020 | April 2020 | April 2020 | John/Sarah | IT cannot provide the mobile phones required and have advised a competition needs to be undertaken. | *Dec '19 - Confirm the numbers and specifications of phone required. Agree procurement route. *Jan '20 - Start mini competition * Feb '20 - Evaluate * March '20 - Propose for award * April '20 - Award and place order |  | LATCO | ? | N/A?

## HR (hidden)
Theme | Task/Milestone | Task owner | Required completion date | Planned start date | Actual start date | Status | Comments | Additional funding required (Y/N) if yes, specify (£) | Necessary capacity to deliver? | Necessary expertise to deliver? | Necessary budget to deliver?
Pension scheme | Set up a workplace pension | Lara Balogun | 2020-06-06 | 2020-06-05 | 2020-06-07 | Keeping track on
| Determine pension scheme type | Kevin O'Leary |  |  |  | Completed | 28/11/2019: Option to adopt the Government 'Nest' (National Employment Savings Trust) scheme for Amey staff & new recruits who were never part of the previous Ealing TUPE transfer group. Decided June 2019.
| Register with HMRC | Lara Balogun | 2020-05-06 |  |  |  | 1/12 to register with HMRC re PAYE once ready to have payroll
| HMRC to issue Company with Scheme Number | Lara Balogun | 2020-06-06
| Register Company with NEST | Lara Balogun | 2020-06-06 |  |  |  | 1/12 Company registered Oct 19 with Companies House, to register re Pension once registered for PAYE
| Arrange employers Liability insurance | Ewan re Ins/ Chris | 2020-04-01 | 2019-10-01 | 2019-10-01 |  | 1/12 Being done by April 2020 by Ewan as part of new Insurance contract for council
| Arrange scheme - require PAYE and bank account | Chris re bank / Payroll re PAYE then |  | 2019-10-01 | 2019-10-01 |  | 14/1/2020 expect bank account this week, and SUN for payroll the following, as all details provided to bank. Do not need PAYE registration to start till 6wks before start paying PAYE. 6/1/20 Chris requested Simon to get updated Director Alison Reynolds, to bank, as they requested. 1/12/19 started getting bank account hoping earliest in Dec
| Agree contribution levels | Kevin O'Leary | 2019-11-28 |  |  | Completed | 28/11/2019: 5% minimum contribution level was agreed.
| Decide main contact for Nest/ other scheme who makes decisions about the scheme | Kevin O'Leary | 2019-11-28 |  |  | Completed | 28/11/2019: it has been agreed that the GEL MD and the Company Board will hold this decision making authority.
| Names of delegates / internal and external (Finance, Payroll provider) | Lara Balogun/ Chris Neale |  |  |  | Completed
| Specify pay period/frequency | Lara Balogun | 2020-12-20 |  |  | Completed | Monthly - 26th of each month or nearest working day i.e. if 26th falls on Saturday will pay on Friday.
| Broadly equivalent LGPS or Admitted Body Status scheme for ex Ealing employees (up to 17) | Jenny Connett/Chuhr | 2020-06-07 | 2020-05-06 |  | Not started | Needs two months lead in to complete tasks
| Obtain confirmation of the names and details (that are available) of the staff that are to be included in the admitted body. | Sharon Brown | 2020-06-07 | 2020-05-06 |  | Not started | Need Amey to confirm TUPE data and names that need to be put into LGPS
| The application form and first tab of the new employer data request spreadsheet needs to be completed and returned and provided to pensions. The first few columns of the second tab can be completed with the names and basic information. | Chuhr | 2020-06-07 | 2020-05-06 |  | Not started
| Pensions to check with the actuaries to see if they need details of deferred benefits held with Ealing (or if the will extract this from the valuation data they already hold) | Jenny Connett | 2020-06-07 | 2020-05-06 |  | Not started
| Once received the above documents will be sent to the scheme actuaries to access the employers contributions rate (plus any possible deficit payments) and if a bond is required. | Jenny Connett | 2020-06-07 | 2020-05-06 |  | Not started
| The actuaries will then issue an admission summary paper (this might take 6 – 8 weeks, but hopefully will be sooner) | Jenny Connett | 2020-06-07 | 2020-05-06 |  | Not started
| A report will need to go to the Pensions Fund Panel (this will need to be submitted two weeks before the meeting date. I am not sure of the exact date it will be in June / July 2020) | Jenny Connett | 2020-06-07 | 2020-05-06 |  | Not started | report written and fully signed off by 15/6/2020. PFP meeting confirmed as 02/07/2020
Tupe transfer | Develop a TUPE transfer process and ensure smooth transition of Amey staff to the LATCO | Sharon Brown | 2020-06-01 | 2020-01-31 |  |  | Need to take into account Amey's Mobilation Plan/current non contact wth Amey HR rep
| Request early version of all Employee Liability Information documents | Sharon Brown |  | 2020-02-28 |  |  | 28/11/2019: When will the employer liability information be received as per the exit agreement? Will it include ID checks and driver information?
| Complete due diligence/gap analysis of ELI | Sharon Brown |  | 2020-02-28 |  |  | 28/11/2019: What LATCo provisions are envisaged, as formulating them is a task in itself? SB: need to have productive dialogue with Amey HR re completion of TUPE spreadsheet. Amey mobilition plan states information to be provided 22/6/20!
| Identify and agree which roles/who should transfer | HR/ GEL Mgmt Team | 2020-06-01 | 2020-04-29 |  |  | 16/12 SB: Can't do this until Amey have provided TUPE list
| Develop proposals for any measures, including negotation on any new contractual provisions. | HR/ GEL Mgmt Team | 2020-06-01 | 2020-04-29 |  |  | 03/12/2019: need discussion with TU - need to jointly agreed and send measures letter re any proposed changes
| Develop staff consultation plan | HR/ GEL Mgmt Team | 2020-06-01 | 2020-04-29 |  |  | 03/12/2019: consultation plan needs to be devised in January 2020. Amey's mobilation plan suggests agreeing timetable for consultation in April, 18/5/20-19/6/20 to carry out consulation meetings and issuing letters to staff
| Agree consultation plan with trade unions | HR/KO'L | 2020-06-01 | 2020-04-29
| Develop the staff consultation information, and consult | Sharon Brown | 2020-06-01 | 2020-04-29
| Manage the staff transfer process | Sharon Brown | 2020-06-07 | 2020-06-06 |  |  | 28/11/2019: LBE's HR Shared Service Centre can be mobilised as a virtual team to support the TUPE document checking process for eligibility to work docs/checks
| Ensure payroll provider has TUPE transfer payroll data for payroll | Ealing/Amey Payroll contacts | 2020-06-07 | 2020-06-06 |  |  | Need to facilitate introduction of Ealing and Amey payroll contact
| Staff induction | Sharon Brown/ Gel Mgmt team/KO'L | 2020-07-06 | 2020-01-03 |  |  | Depends on what induction /training is being requested and provided by whom
Recruitment (Managing Director) (Finance Lead) (HR Manager) (Transport Manager, tbd depending on Amey discussions) | Review GEL's company structure and reporting lines | Sharon Brown | 2020-02-28 |  |  | In progress
| Develop recruitment process for posts | Sharon Brown | 2020-02-28 |  |  | In progress | 16/12 Interim Director already in place, Council Director to make decision about this pending Board being set up
| Develop JDs and person specs | Sharon Brown/ Gel Mgmt team/KO'L | 2020-02-28 |  |  | In progress | 16/12 Hays Recruitment Agency commissioned to recruit to HR and Finance roles
| Develop pay, benefits, and T&Cs for each post | Sharon Brown/ Gel Mgmt team/KO'L | 2020-02-28 |  |  | In progress | Using ACAS T&C's for new posts
| Develop a specimen contract of employment | Sharon Brown | 2020-02-28 |  |  | In progress | Using ACAS T&C's for new posts
| Work with Procurement to ensure an agency supplier is in place for temp staff | HR/John Arnold | 2020-02-28 | 2020-01-16 | 2020-01-16 | In progress | Pertemps identified by Mstar framework. John and Sarah in discussions with them and all on target. Pertemps currently providing Hillingdon so will replica.
Policies and Procedures | Review existing AMEY policies and procedures, amending to fit GEL (NEW STARTERS) | HR/KO'L | 28/2/20 | 2020-06-01 |  | In progress
| Redundancy benefits policy | GEL HR Manager |  | 2019-07-01 | ? | In progress | 16/12 Need to discuss the policy element in more detail, decide what we want the policies to look like i.e. use ACAS. John & SB reviewing current drafts
| Job evaluation procedure |  |  |  | ? | In progress
| Pay policy (base pay; overtime; bonuses; shift and other allowances) |  |  |  | ? | In progress
| Performance management |  |  |  | ? | In progress
| Sickness absence |  |  |  | ? | In progress
| Holiday policy and booking process |  |  |  | ? | In progress
| Overtime recording process |  |  |  | ? | In progress
| Signing in, signing out procedure |  |  |  | ? | In progress
| Other absences (paid; unpaid; procedure; entitlement) |  |  |  | ? | In progress
| Sick pay policy |  |  |  | ? | In progress
| Maternity/paternity/adoption/parental leave |  |  |  | ? | In progress
| Working Time Regulations/limits/opting out policy |  |  |  | ? | In progress
| Working week/working patterns/rest breaks/toil/overtime |  |  |  | ? | In progress
| Disciplinary procedure |  |  |  | ? | In progress
| Grievance procedure |  |  |  | ? | In progress
| Equal opportunities |  |  |  | ? | In progress
| Health and safety |  |  |  | ? | In progress
| Smoking at work |  |  |  | ? | In progress
| Harassment policy |  |  |  | ? | In progress
| Personal records and data protection |  |  |  | ? | In progress
| Handling organisational change policy |  |  |  | ? | In progress
| References policy |  |  |  | ? | In progress
| Handbook (reference to Modern Slavery Act 2015 Regs/Anti corruption policy/Bribery Act 2010). Company property (care, reporting damage, returning, storing, handover, keep it safe) |  |  |  | ? | In progress
| Email/internet policy |  |  |  | ? | In progress
| Mobile phone policy |  |  |  | ? | In progress
| Expenses policy |  |  |  | ? | In progress
| Review existing AMEY policies and procedures, amending to fit GEL (TUPE EMPLOYEES) | Sharon Brown | 2020-07-30 | 2020-06-30 |  |  | 16/12 Awaiting these being supplied. This can be done post transfer, as will need to consult on any changes proposed with staff group and the TU's.
| Redundancy benefits policy | GEL HR Manager | TBA | TBA |  | Not started
| Job evaluation procedure |  | TBA | TBA |  | Not started
| Pay policy (base pay; overtime; bonuses; shift and other allowances) |  | TBA | TBA |  | Not started
| Performance management |  | TBA | TBA |  | Not started
| Sickness absence |  | TBA | TBA |  | Not started
| Holiday policy and booking process |  | TBA | TBA |  | Not started
| Overtime recording process |  | TBA | TBA |  | Not started
| Signing in, signing out procedure |  | TBA | TBA |  | Not started
| Other absences (paid; unpaid; procedure; entitlement) |  | TBA | TBA |  | Not started
| Sick pay policy |  | TBA | TBA |  | Not started
| Maternity/paternity/adoption/parental leave |  | TBA | TBA |  | Not started
| Working Time Regulations/limits/opting out policy |  | TBA | TBA |  | Not started
| Working week/working patterns/rest breaks/toil/overtime |  | TBA | TBA |  | Not started
| Disciplinary procedure |  | TBA | TBA |  | Not started |  |  |  |  | s
| Grievance procedure |  | TBA | TBA |  | Not started
| Equal opportunities |  | TBA | TBA |  | Not started
| Health and safety |  | TBA | TBA |  | Not started
| Smoking at work |  | TBA | TBA |  | Not started
| Harassment policy |  | TBA | TBA |  | Not started
| Personal records and data protection |  | TBA | TBA |  | Not started
| Handling organisational change policy |  | TBA | TBA |  | Not started
| References policy |  | TBA | TBA |  | Not started
| Handbook (reference to Modern Slavery Act 2015 Regs/Anti corruption policy/Bribery Act 2010). Company property (care, reporting damage, returning, storing, handover, keep it safe) |  | TBA | TBA |  | Not started
| Email/internet policy |  | TBA | TBA |  | Not started
| Mobile phone policy |  | TBA | TBA |  | Not started
| Expenses policy |  | TBA | TBA |  | Not started
Establish trade union working arrangement | Review scope and content of any Amey recognition/ collective agreements | Sharon Brown/Amey HR | 2019-07-29 | 2019-07-01 | 28/11/20 | In progress | 1/12 SB: Not sure if this complete. We've had first offical meeting with the TU's, not seen any recognition/collective agreements.
| Identify local reps/shop stewards and what the consultative requirements are |  | 2020-07-06 | 2020-06-06 |  | Not started | Could discuss with Dean Gilligan at next TU meeting
| Develop any changes/protocols for LATCo and trade union facilities |  | 2020-06-07 | 2020-11-28 |  | In progress
Review any other people related contracts/ arrangements with Procurement | Payroll/HR provider | Andrew Scully/ Lara Balogun | 2020-06-01
Post Transfer | Training & Development Plan | GEL HR
| Apprenticeship Programme | GEL HR
| Employment links with local employers and schools | GEL HR
Note on B1: Killian Rosato-Dooey: Milestones highlighted
Note on G1: Killian Rosato-Dooey: Not started In progress Completed
Note on B13: Killian Rosato-Dooey: We need to specify what tasks are involved to achieve this deliverable

## Health and Safety (hidden)
Assurance
Task/Milestone | Task owner | Required completion date | Planned start date | Actual start date | Status | Comments | Additional funding required? Y/N (if yes, specify) | Necessary capacity to deliver? | Necessary expertise to deliver? | Necessary budget to deliver?
Recruitment of a health and safety consultant to deliver workplan | John Arnold and Somayya Yaqub | 2020-01-27 | 2020-01-06 |  | Not started
Secure requisite approval and funding | John Arnold | 2020-01-07 | 2020-01-06 |  | Not started
Develop job description | John Arnold and Somayya Yaqub | 2020-01-14 | 2020-01-07 |  | Not started
Develop person specification | John Arnold and Somayya Yaqub | 2020-01-14 | 2020-01-07 |  | Not started
Appoint candidate to start W/C 27/01/2020 | Health and safety consultant | 2020-01-27 | 2020-01-14
Agree approach to the develop of route risk assessments |  | 2019-08-26 |  |  |  | have Amey's Risk Assessments which we can use as a start point
Understand COSHH requirements across the service | Health and safety consultant | 2019-09-30 |  |  |  | have Amey's COSHH Assessments which we can use as a start point
Health and Safety | Health and safety consultant | 2019-10-28 |  |  |  | Need to develop a H&S Policy have a draft one for GEL from the HSE website
Environment | Health and safety consultant | 2019-10-28 |  |  |  | Need to develop a Policy
Develop risk assessments for all operations | Health and safety consultant | 2019-12-16 |  |  |  | have Amey's Risk Assessments which we can use as a start point
Develop Safe Systems of Work for waste operations | Health and safety consultant | 2019-12-16 |  |  |  | Have Amey's SSOW can be used as a start point
Identify training requirements for day one and on an ongoing basis | Health and safety consultant | 2020-02-03 |  |  |  | Ask Amey for their training matrix and highlight the training they actually carry out
Approval of risk assessments | Health and safety consultant | 2020-02-24 |  |  |  | Need to speak to LBE H&S for support RE. using Amey's Risk Assessments as a start point of the contract and review as we go during the 1st 6 months of GEL
Undertake route risk assessments | Health and safety consultant | 2020-02-24 |  |  |  | Have Amey's RRRA
Approval of Safe Systems of Work | Health and safety consultant | 2020-02-24 |  |  |  | Need to speak to LBE H&S for support RE. using Amey's SSOW as a start point of the contract and review as we go during the 1st 6 months of GEL
Undertake Fire Risk Assessment on the new depot area | Health and safety consultant | 2020-03-23 |  |  |  | Should be pre existing as LBE depot
Develop evacuation plan for depot | Health and safety consultant | 2020-04-20 |  |  |  | Should be pre existing as LBE depot
Approval of route risk assessments | Health and safety consultant | 2020-04-27 |  |  |  | Need to speak to LBE H&S for support RE. using Amey's RRRA as a start point of the contract and review as we go during the 1st 6 months of GEL
Training and dissemination of risk assessments | Health and safety consultant | 2020-06-29 |  |  |  | Training will be carried out as part of the induction (induction plan to still be drafted)
Training and dissemination of route risk assessments | Health and safety consultant | 2020-06-29 |  |  |  | Training will be carried out as part of the induction (induction plan to still be drafted)
Training and dissemination of Safe Systems of Work | Health and safety consultant | 2020-06-29 |  |  |  | Finance will need to be involved in this as there will be a cost element I.E overtime paid to amey to train the staff before go live date
H&S policy | Health and safety consultant

## Legal (hidden)
Milestone > task | Task owner | Area | Required completion date | Planned start date | Actual start date | Status | Comments |  | Necessary expertise to deliver? | Necessary budget to deliver?
Additional funding required? Y/N (if yes, specify)
Variation of articles to be approved by Cabinet | Helen Harris | Legal Services | 2020-03-17 | 17.3.2020 | ? | In progress: delayed | 09/12/2019: Articles - wrong version attached to the October Cabinet Report. Will need to go back to February Cabinet to amend the articles. 20/01/2020: will now go to March Cabinet, delayed from Feb Cabinet
Shareholder representative appointment | Helen Harris | Legal Services | 10.01.20 |  |  | Completed | 09/12/2019: Gary Alderson appointed at October 2019 Cabinet
New director to appoint to replace Tim Smith and obtain authority to indemnify new director | Helen Harris | Legal Services | 2020-02-28 |  | 2020-01-07 | In progress: delayed | 09/12/2019: HH & Ross to decide who to appoint as director to replace TS. HH has delegated authority to appoint directors and to give indemnities to directors. 20/01/2020 (KRD): approval required from Alison and Ross to indemnify Kieran Read. This task has been delayed from a completion date of 10/01/2020 to end of Feb.
Ealing Side Gel Governance - Directors Training | Helen Harris | Legal Services | 15.1.20 |  |  | In progress; delayed
Arranging training with TLT | Helen Harris | Legal Services | 2020-02-13 |  |  | In progress: delayed | 20/01/2020 (KRD): still in process of setting date of training itself, in liaison with TLT lawyers. Delaying required completion date from 10/01 to mid-Feb
Provision of training to Ealing Directors | Helen Harris | Legal Services | 2020-02-28 |  |  | Not started: delayed | 9/12/2019 HH to arrange training via TLT and include all relevant officers 20/01/2020 (KRD): delayed as training hasn't been fully arranged yet
Company secretarial services | Kevin O'Leary | Legal Services | 2020-01-03 |  |  | Completed
Broadway Living to be approached | Kevin O'Leary | GEL | 24.12.2019 |  |  | Completed | Maxine Sawford to set bridgehouse up as a supplier for GEL to use.
Provision of company secretarial services to GEL | Kevin O'Leary | Legal Services | 2020-01-03 | ? | ? | Completed | 09/12/2019: KL to speak to BL - Phillip Brown on secretarial services pending
Service Provision Agree - GEL and LBE | Chuhr Nijjar | Legal Services | 2020-01-10 | 1.10.19 | ? | In progress: delayed
Agreement for the provision of services from GEL to LBE to KL | Chuhr Nijjar | Legal Services | 2020-01-17 |  |  | In progress: delayed | 09/12/2019 Ongoing - meeting every 2 weeks. Colleagues are updating specs, default provisions and KPIs. Aim to complete draft by Xmas and send to Kevin O'Leary early new year. HH suggestion for GE to meet with client departments to agree prices and other important issues. CNi to raise with Clients at meeting on Tuesday. 20/01/2020 (KRD): Chuhr said the agreement will be written by 24/01
Completion of Agreement - executed by both parties |  |  | 1.7.20 |  |  | Not started
SLA support services (Support Services Agreement) | Chuhr Nijjar | Legal Services | 20.2.20 | 1.2.20 | ? | In progress | 09/12/2019: CNi has written to colleagues on ICT, FM, HR and Finance to ascertain which contracts will need to progress specs for the support services agreement.
Draft SLA to KL covering heads listed below |  |  | 20.2.20 | 1.2.20
Completion of SLA |  |  | 1.7.20 | 1.2.20
obtain details from HR | Chuhr Nijjar | Legal Services | 20.2.20 | 1.2.20 | ? | ?
obtain details fromLegal Services | Chuhr Nijjar | Legal Services | 20.2.20 | 1.2.20 | ? | ?
obtain details from Finance | Chuhr Nijjar | Legal Services | 20.2.20 | 1.2.20 | 2020-10-01 | In progress | 13/1/2020 Georgia confirmed working on SLA re payments for this week. 6/1/2020 reminded Georgia and John 27/11/2019 Georgia Hoare (& John Parmenter) have Accounts Payable KPIs and deliverables and have been requested to shape to propose to John Arnold, for incorporation into legal agreement
obtain details from ICT | Chuhr Nijjar | Legal Services | 20.2.20 | 1.2.20 | ? | In progress
obtain details from FM | Chuhr Nijjar | Legal Services | 20.2.20 | 1.2.20 | ? | In progress
obtain details from Payroll | Chuhr Nijjar | Legal Services | 20.2.20 | 1.2.20 | ? | In progress
obtain details fromPensions Administration | Chuhr Nijjar | Legal Services | 20.2.20 | 1.2.20 | ? | In progress
obtain details from Procurement Services | Chuhr Nijjar | Legal Services | 20.2.20 | 1.2.20 | ? | In progress
Novation of existing contracts | Chuhr Nijjar | Legal Services | 2020-05-02 | 1.1.20 | 2020-01-20 | In progress | 09/12/2019: Any Amey or LBE contracts to novate to GE. CNi to liasing with colleagues.
Identify Amey contracts to Novate |  |  | 1.7.20 | 20.1.20 | 20.1.20 | In progress | 20/01/20 JA to identify the contracts
Loan agreement/funding facility agreement | Chuhr Nijjar | Legal Services | 1.3.20 | 1.1.20 | 1.12 | In progress | 09/12/2019: CNi to liaise with Finance and client officers, including re interest rate
Draft Loan Agreement to KL |  |  | 1.3.20 | 1.1.20 | 1.1.20 | In progress | 20/01/2020 (KRD): Chuhr emailing Chris
Completion of Loan Agreement |  |  | 1.7.20 | 1.7.20 |  | Not started
Novation of procured contracts | Chuhr Nijjar | Legal Services | 2020-03-02 | ? | ? | In progress | 09/12/2019: CNi working with procurement stream.
Identify other Contracts to Novate |  |  | 1.7.20 | 20.1.20 | 20.1.20 | In progress | 20/01/20 CNi to identify the contracts with colleagues
TUPE information to insert into Services Agreement | Chuhr Nijjar | Legal Services/HR | 1.7.20 | 2019-12-16 | 2019-12-16 | In progress
Pensions | Chuhr Nijjar | Legal Services/HR | 2.5.2020 |  |  |  | 09/12/2019: Meeting with HR who are progressing these arrangements and have been advised to obtain pension panel authority for admission agreement.
NEST for new staff | Shahzad Ayub | Legal Services/HR | 2020-06-06 |  |  | Not started
Authority to enter into Admission Agreement from Pension Panel |  |  | 2020-05-02
LGPS - Admission Agreement draft to KL | Chuhr Nijjar | Legal Services/HR | 2020-03-02
Procurements | Chuhr Nijjar | Legal Services/ Commercial Hub | 2020-03-02 | 1.1.20 |  |  | 09/12/2019: Numerous procurements which will need to be completed before GE commences services provision.
Vehicle procurement - approve & finalise agreements | Chuhr Nijjar | Legal Services/ Commercial Hub | 2020-03-02 | 1.1.20 |  |  | 20/01/2020 Check status with SH on 23/1
Agreement with Amey to lease vehicles to Amey |  |  | 2020-03-02 | 1.1.20
Vehicle Finance Lease | Chuhr Nijjar | Legal Services/ Commercial Hub | 2020-03-02 | 1.1.20 |  |  | 20/01/2020 Check status with CNe
Vehicle maintenance procurement - approve & finalise agreements | Chuhr Nijjar | Legal Services/ Commercial Hub | 2020-03-02 | 1.1.20 |  |  | 20/01/20 Tender out, updated documents out today. Tender return in February
Hire vehicles procurement - approve & finalise agreements | Chuhr Nijjar | Legal Services/ Commercial Hub | 2020-03-02 | 1.1.20
Staffing agencies procurement - approve & finalise agreements | Chuhr Nijjar | Legal Services/ Commercial Hub | 2020-03-02 | 1.1.20
Equipment procurement -approve & finalise agreements | Chuhr Nijjar | Legal Services/ Commercial Hub | 2020-03-02 | 1.1.20
Other products and services procurement -approve & finalise agreements | Chuhr Nijjar | Legal Services/ Commercial Hub | 2020-03-02 | 1.1.20
Insurance procurement approve & finalise agreements | Chuhr Nijjar (TLT) | Legal Services/ Commercial Hub | 2020-03-02 | 1.1.20 |  |  | 09/12/2019 Ewan Taylor in Insurance will be instructing contracts team on the procurement
Property Leases & Licences | Jackie Adams |  | 1.7.20 | 1.1.20 | 1.1.20 | In progress
Heads of terms from LSH | Jackie Adams |  | 1.3.20 | 1.1.20 | 1.1.20 | In progress | 20/1/20 EM to instruct LSH for heads of terms
Lease or Licence Draft | Jackie Adams | Commercial Hub/ Legal Services | 6.3.20 | 1.1.20 |  |  | 09/12/2019 CNi keeping a watching brief.
Completion of Lease or Licence |  |  | 1.7.20
Sub Lease to Vehicle Maintenance operator |  |  | 1.7.20 |  | 13.1.20
AMEY dispute
AMEY dispute | Justin Morley | Legal Services | ? | ? |  |  | 6.9.19 - CNi to talk to JM re impact of dispute on GEL set up . Amey completing schedule for their claim to be provided before Xmas when we will have a better idea of strength of claim.
Note on G1: Killian Rosato-Dooey: Not started In progress Completed
Note on A2: John Arnold: Milestone
Note on A3: John Arnold: Tasks to complete Milestone

## GEL tasks (hidden)
Assurance
Task/Milestone | Task owner | Area | Required completion date | Planned start date | Actual start date | Status | Comments | Necessary capacity to deliver? | Necessary expertise to deliver? | Necessary budget to deliver?
Apprenticeships | GEL Mgt Team/ HR Manager | HR
Training and development | GEL Mgt Team/ HR Manager | HR
Links with Local employers | GEL Mgt Team/ HR Manager | HR
Links to local Schools | GEL Mgt Team/ HR Manager | HR
Business partnership | GEL Mgt Team/ HR Manager | HR
Business plan review of numbers | GEL Mgt Team/ Chris Neale | Finance
Contingency planning & financal implications | GEL Mgt Team/ Chris Neale | Finance
Running Check on the Loan from LBE - GEL | GEL Mgt Team | Finance
Draft Letter of appointment to Chair | GEL Mgt Team
Review of specs | GEL Mgt Team
GDPR and what it means for GEL | GEL Mgt Team
Licences | GEL Mgt Team
LATCO Network Membership | GEL Mgt Team
FTA membership | GEL Mgt Team
Electric vehicles confirmation | GEL Mgt Team
IWM & GM Memberships | GEL Mgt Team
ICT costs final review | GEL Mgt Team
Shchedule of Meetings for GEL board | GEL Mgt Team
Pay differententails | GEL Mgt Team
update Business plan | GEL Mgt Team
Service effeciences | GEL Mgt Team
Audit | GEL Mgt Team
Vehcile Livery | GEL Mgt Team
Data, (Bin Survey) | GEL Mgt Team
Vehicles taken home | GEL Mgt Team
Parking plan ( should be captured by Depot | GEL Mgt Team
Tax Advice | GEL Mgt Team
Storage | GEL Mgt Team
FORS | maintenance supplier
Alternative fuels for future
vehicle washing
CPC Driver trianing | John Arnold/Kevin O'Leary + Consultant
CPC Management trianing | John Arnold/Kevin O'Leary + Consultant
Parking issues @ depot | John Arnold/ Earl McKenzie/ Kevin O'Leary
Site house keeping
Tennants to work together
HWRC indepth look at service
Understanding costs and income line by line
CIWM Membership
Waste carriers licence | John Arnold/ Kevin Oleary
O Licence | John Arnold/Kevin O'Leary + Consultant
ABP Permit (free)
Ascertain if there are any Amey vehicles LBE would like to buy | John Arnold | Fleet | 2020-07-01
Negotiate deal with Amey | John Arnold/ Earl McKenzie/ Kevin O'Leary | Fleet | 2020-07-01
Work Out who COTC Holder Is | John Arnold/ Earl McKenzie/ Kevin O'Leary | Fleet | 2020-07-01
Apply for O Licence | John Arnold/Kevin O'Leary + Consultant | Fleet | 2020-07-01
Transport Manager CPC holder(Green Recruitment time) | John Arnold/Kevin O'Leary + Consultant | Fleet | 2020-07-01
O Licence Granted | John Arnold/Kevin O'Leary + Consultant | Fleet | 2020-07-01
V5s handed over | John Arnold/Kevin O'Leary + Consultant | Fleet | 2020-07-01
Keys and spares handed over | John Arnold/Kevin O'Leary + Consultant | Fleet | 2020-07-01
Maintenance records handed over | John Arnold/Kevin O'Leary + Consultant | Fleet | 2020-07-01
MOT records handed over | John Arnold/Kevin O'Leary + Consultant | Fleet | 2020-07-01
LOLER records handed over | John Arnold/Kevin O'Leary + Consultant | Fleet | 2020-07-01
Understand current defect process | John Arnold/Kevin O'Leary + Consultant | Fleet | 2020-07-01
Busniess related only non public
pay differences
Annualised hours GM
optmisation waste
cleansing spec
loader numbers on teams
cross over GM and streets
effecincies
Bank holiday working
Pay rises (speak to Chris re %)
use of ICT going digital GM & Streets
Branding
Governance
Review of notes
Fuel Amey usage and GEL usage how to control
GEL Tasks | Tacho Kit Ordered |  |  |  | 2020-07-01
GEL Tasks | Defect Process Established |  |  |  | 2020-07-01
GEL Tasks | Develop Training Pack |  |  |  | 2020-07-01
GEL Tasks | Get communal keys and codes alongside any keys to parks etc. |  |  |  | 2020-07-01
GEL Tasks | Notify West Waste of change of operator and understand what needs to be done at the tip |  |  |  | 2020-07-01
GEL Tasks | Print Training Pack |  |  |  | 2020-07-01
GEL Tasks | Undertake licence checks on all drivers |  |  |  | 2020-07-01
GEL Tasks | Develop plan for 3 months licence checks |  |  |  | 2020-07-01

## Half day event notes (hidden)
Monthly to do list (Key tasks)
Month | Milestone | Comments | Task owner
2020-01-01
2020-01-01 | Vehicle update | finalise vehicle plan after update this will feed into novation of amey fleet | JA, KOL, SH
2020-01-01 | first GEL Board Meeting |  | KOL, AR, MB, KR
2020-01-01 | Director training for board directors |  | HH, KOL
2020-01-01 | Review of new contract | Contract in draft should be ready by end of Jan 20 | KOL, JA, EMK, CB, CN(legal)
2020-01-01 | continue Vehicle maintenance Tender | tender is out | KOL, JA, SH, VH
2020-01-01 | Chase Amey for TUPE data and policies | Requested from amey chased 07.01.2020 | JA, SB
2020-01-01 | Start Bin survey | required for accurate data to begin optimisation of waste rounds before go live if possible | JA, KOL, CP, DP
2020-01-01 | Start applications for licences | Use as a critcal friend (waiting for P2P to finalise on system so a PO can be raised) | JA, KOL
2020-01-01 | seek support from FTA and LATCO Network
2020-02-01 | JA has miss placed
2020-03-01
2020-03-01 | finalise fleet arrangements with LBE and Amey | Agree that vehicles can be delivered as they come and used by Amey up to July 20 | GA, EMK, JA, KOL, CB CN(Legal)
2020-03-01 |  | If not agreed temp storage required
2020-03-01 | staff consultation
2020-03-01 | Making Tax Digital sorted
2020-03-01 | Bin survey completed by end of Mar
2020-04-01
first delivey of fleet end of Apr 20
storage if not agreed with Amey
ICT testing of BW begins
Gel Management team working from Greenford if not before
2020-05-01
P.P.E start to be delivered
tools and equipment start to be delivered
Gloves start to be delivered
Fuel timeline Agreement with Amey finalised
Trainer Trainer for software etc. in place
Confirmation of licences in place
continued staggered delivery of fleet and plant
June
Inductions staggered over month
Risk Assesments in place
TUPE lists (final sent across from amey)
Maintenance provider ready to go

## BP Tasks (hidden)
KEY ACTION 1 – Develop a workforce Strategy that addresses the vision and values of the business and partners as set out above.
KEY ACTION 2 – Develop a mobilisation and implementation plan that will meet the initial service specification requirements as set out above.
KEY ACTION 3 – Finalise all necessary Governance arrangements to allow Greener Ealing to operate in accordance with all legal requirements.
KEY ACTION 4 – Create a new management structure fit for a modern customer focused service organisation
KEY ACTION 5 – AS part of the Workforce strategy (see key action 1) establish consultation and communications processes with the trade unions and workforce.
KEY ACTION 6 – commence recruitment campaigns for Greener Ealing Senior Management Team
KEY ACTION 7 – Develop a set of Greener Ealing Health and Safety Policies and corresponding management arrangements
KEY ACTION 8 – Develop implementation plans for all ICT business support systems
KEY ACTION 9 – Decide on the future vehicle maintenance arrangements for Greener Ealing.
KEY ACTION 10 - Develop Key Performance and Business Indicators for Greener Ealing.
KEY ACTION 11 – Develop a Communications and Marketing Plan for Greener Ealing including new branding.
KEY ACTION 12 – Develop a Greener Ealing Carbon Reduction Action Plan
KEY ACTION 13 – Develop a Business Development Plan for Greener Ealing following mobilisation.
KEY ACTION 14 – Develop a Greener Ealing Annual Community Plan

## All tasks>milestones (hidden)
Workstream | Task/Milestone | Business Plan 14 Points | Task owner | Area | Required completion date | Planned start date | Actual start date | Status | Comments
Health & Safety | Secure requisite approval and funding for H&S consultant |  | John Arnold |  | 31.01.20 | 2020-01-06 | 2020-01-06 | Complete | Part of set up can use part of the £2.5M set aside for unforseen set up
Depot | Mobilize on site |  | Aspects |  | Thu 02/01/20 | Thu 02/01/20 | Thu 02/01/20 | Complete
Depot | Sheet up Plant Room |  | Aspects |  | Thu 02/01/20 | Thu 02/01/20 | Thu 02/01/20 | Complete
Depot | Scaffold in Plant Room |  | Aspects |  | Thu 02/01/20 | Thu 02/01/20 | Thu 02/01/20 | Complete
Depot | Encapsulate Plant Room |  | Aspects |  | Fri 03/01/20 | Fri 03/01/20 | Fri 03/01/20 | Complete
Depot | Air Test Plant Room |  | Riverside |  | Sun 05/01/20 | Fri 03/01/20 | Fri 03/01/20 | Complete
Depot | Sheeting up |  | Aspects |  | Thu 09/01/20 | Mon 06/01/20 | Mon 06/01/20 | Complete
ICT | Send payroll info to HR |  |  | BW Team | 2019-11-08 | 2019-11-08 |  | Completed
ICT | Data gathering | 8 |  |  | 2019-11-29 | 2019-10-03 |  | Completed
ICT | Prepare LLPG data | 8 |  | ICT Applications Support | 2019-10-31 | 2019-10-14 |  | Completed
ICT | Prepare FTP | 8 |  | ICT Infrastructure | 2019-11-08 | 2019-10-14 |  | Completed
ICT | FTP LLPG data to WS | 8 |  | ICT Infrastructure | 2019-11-12 | 2019-11-11 |  | Completed
ICT | Whitespace data gather | 8 |  | Supplier PM | 2019-11-28 | 2019-11-13 |  | Completed
ICT | COU process in place | 8 |  | LBE ICT PM | 2019-11-29 | 2019-11-29 |  | Completed
ICT | Requirement - initial meet with Contender | 8 | Faisal and Michael T | ICT | 2019-11-04 | 2019-11-04 |  | Completed
ICT | Receive quote from Contender | 8 | Faisal and Michael T | ICT | 2019-11-11 | 2019-11-05 |  | Completed
ICT | Confirm Contender quote as acceptable | 8 | Faisal and Michael T | ICT | 2019-11-25 | 2019-11-12 |  | Completed
ICT | Generate PO and send to Contender | 8 |  | ICT PM | 2019-11-28 | 2019-11-26 |  | Completed
ICT | Requirements | 8 |  | DH / ICT PM | 2019-10-01 | 2019-10-01 |  | Completed
ICT | Domain names | 8 |  | ICT Infrastructure | 2019-10-07 | 2019-10-01 |  | Completed
ICT | Site surveys | 8 | Tony Gavaghan | ICT | 2019-10-22 | 2019-10-22 |  | Completed
Legal | Ealing Side Gel Governance - Directors |  | Helen Harris | Legal Services | 10.01.20 |  |  | Completed
Legal | Shareholder representative appointment |  | Helen Harris | Legal Services | 10.01.20 |  |  | Completed | 09/12/2019: Gary Alderson appointed at October 2019 Cabinet
Legal | New director to appoint to replace Tim Smith and obtain authority to indemnify new director |  | Helen Harris | Legal Services | 10.1.20 |  |  | Completed | 09/12/2019: HH & Ross to decide who to appoint as director to replace TS. HH has delegated authority to appoint directors and to give indemnities to directors.
Legal | Company secretarial services |  | Kevin O'Leary | Legal Services | 2020-01-03 |  | 2019-12-16 | Completed | Kevin is using the company that Broadway living use
Legal | Broadway Living to be approached |  | Kevin O'Leary | GEL | 24.12.2019 |  |  | Completed | Maxine Sawford to set bridgehouse up as a supplier for GEL to use.
Legal | Provision of company secretarial services to GEL |  | Kevin O'Leary | Legal Services | 2020-01-03 |  |  | Completed | 09/12/2019: KL to speak to BL - Phillip Brown on secretarial services pending
Depot | Phase 1 Asbestos Removal Plant Room |  |  |  | Sun 05/01/20 | Thu 02/01/20 |  | Completed
Depot | Scaffolding |  | Aspects |  | Tue 07/01/20 | Fri 03/01/20 |  | Completed
HR | Determine pension scheme type |  | Kevin O'Leary | Payroll | 2019-11-28 |  |  | Completed | 28/11/2019: Option to adopt the Government 'Nest' (National Employment Savings Trust) scheme for Amey staff & new recruits who were never part of the previous Ealing TUPE transfer group. Decided June 2019.
HR | Agree contribution levels |  | Kevin O'Leary |  | 2019-11-28 | 2019-11-28 | 2019-11-28 | Completed | 28/11/2019: 5% minimum contribution level was agreed.
HR | Decide main contact for Nest/ other scheme who makes decisions about the scheme |  | Kevin O'Leary |  | 2019-11-28 | 2019-11-28 | 2019-11-28 | Completed | 28/11/2019: it has been agreed that the GEL MD and the Company Board will hold this decision making authority.
HR | Names of delegates / internal and external (Finance, Payroll provider) |  | Lara Balogun/ Chris Neale |  | 2019-11-28 | 2019-11-28 | 2019-11-28 | Completed
HR | Specify pay period/frequency |  | Lara Balogun |  | 2020-12-20 | 2020-12-20 | 2020-12-20 | Completed | Monthly - 26th of each month or nearest working day i.e. if 26th falls on Saturday will pay on Friday.
HR | Review GEL's company structure and reporting lines | 4 | Sharon Brown | HR | 2020-02-28 |  |  | Completed | Base structure already in place, any further changes will be post go live
HR | Develop JDs and person specs for HR Manager & Head of Finance Roles. | 4 | Sharon Brown/ Gel Mgmt team/KO'L | HR | 2020-02-28 | 2020-01-06 | 2020-12-16 | Completed | 16/12 Hays Recruitment Agency commissioned to recruit to HR and Finance roles
Finance | Finalise budget allocation per service | 3 | Chris Neale | Service Finance | 2020-01-31 | 2019-12-02 | 2019-12-02 | Completed | 9/1/2020 Completed, though pre any refinement by service or further change re LLW, and C to share (with links taken off) with John 29/1/2020. JA 04/12/2019 -JA & CNe met 02/12/2019 and split remaining costs, Chris now to input to complete by mid Jan & send to service
Legal | Agreement for the provision of services from GEL to LBE to KL |  | Chuhr Nijjar | Legal Services | 2020-01-31 | 2019-12-01 |  | Delayed | 09/12/2019 Ongoing - meeting every 2 weeks. Colleagues are updating specs, default provisions and KPIs. Aim to complete draft by Xmas and send to Kevin O'Leary early new year. HH suggestion for GE to meet with client departments to agree prices and other important issues. CNi to raise with Clients at meeting on Tuesday.
HR | Request early version of all Employee Liability Information documents | 5 | Sharon Brown | Interim HR Lead | 2019-12-19 | 2019-12-19 | 2019-12-19 | Delayed | 28/11/2019: When will the employer liability information be received as per the exit agreement? Will it include ID checks and driver information? 13/01/2020: on 10/01/2020 John confirmed request had beeen received, delay due to individual been away for previous month
Finance | Vehicle lease quotes | 3 | Chris and Sarah | Service Finance and Procurement | 2020-02-02 | 2019-11-27 | 2019-05-01 | In progress | 10/1/2020 Meeting held by Tim with LINK to ensure handover to his successor and that LINK aware of what needed next. 7/1/2020 Chris noted meeting planned with Link 10/1 10/12/2019 Chris requested Tim and Sarah provide their outline planned timetable
Finance | GEL Bank account set up | 3 | Simon Peet / Chris Neale | Corporate Finance / Service Finance | 2020-01-27 | 2020-11-01 | 2020-11-01 | In progress: delayed | Monday 27/1/20 Lloyds confirmed (Hayleigh) that had been told (Gabriel) that should be done by Friday 24/1 and would chase to find out why not and when would. 13/1/2020 SUN form emailed and posted to Bank, expecting that approved in week commencing 20/1/2020. 9/1/2020 SUN Indirect Submitter form drafted and given to Lara and to Kayleigh (of Llloyds bank) for final points to be concluded so then when sorted then can be put to Alison to sign, for SUN aspect to be sorted thereafter. Regarding separate (non SUN) point of bank account being set up, Bank have all other information for setting up bank account which can hopefully be set up by Friday 17/1/2020, as bank 6/1/2020 said this can be done in a few days. 9/1/2020 SUN Indirect Submitter form drafted and provided to Karmveer to complete based on Ealing Pension Fund form he completed.7/1/2020 KAP confirmed sent in, and Deborah to provide details of email so Chris can also be in contact with them. 6/1/2020 Chris chased Simon to submit Key Account information for new director Alison to bank, Alison confirmed had left Key Accout information for Simon on 20/12 when Simon on leave, following 6/12/2019 Chris chasing Simon for whether sent as Alison Key information signed left with Simon 20/12 on leave till 6/1.
Finance | London Living Wage to calculate impact of 20p increase | 3 | Chris Neale | Service Finance | 2020-01-31 | 2020-12-16 | 2020-01-06 | In progress | Seeking to start last week Jan 2020
ICT | HR |  |  | HR and BW Team | 2020-04-01 | 2019-11-08 | 2019-11-08 | In progress
ICT | GEL Business Applications | 8 |  | Supplier and ICT | 2020-06-02 | 2019-09-25 | 2019-09-25 | In progress
ICT | Initiation | 8 |  | Supplier PM | 2020-11-14 | 2019-09-25 | 2019-09-25 | In progress
ICT | Whitespace Contract (Gcloud) sign-off | 8 |  | LBE/Supplier | 2020-11-29 | 2019-10-22 | 2019-10-22 | In progress
ICT | ICT technical standards and FOI | 8 |  | LBE ICT PM | 2019-11-18 | 2019-11-07 | 2019-11-07 | In progress
ICT | Gcloud ICT requirements and plan | 8 |  | ICT PM / Business PM / Procurement | 2019-11-28 | 2019-10-22 | 2019-10-22 | In progress
ICT | Procurement elements | 8 | Sarah Hadland | Procurement | 2019-11-28 | 2019-10-22 | 2019-10-22 | In progress
ICT | CRM integration | 8 |  |  | 2020-02-27 | 2019-11-04 | 2019-11-04 | In progress
ICT | Contender integrations - proposal | 8 |  | ICT | 2019-11-28 | 2019-11-04 | 2019-11-04 | In progress
ICT | GEL ICT Infrastructure and Hardware | 8 |  | ICT PM | 2020-04-06 | 2019-10-01 | 2019-10-01 | In progress
Legal | Greener Ealing Ltd Company arrangements |  | Helen Harris | Legal Services | 2020-02-28 |  |  | In progress
Legal | Variation of articles |  | Helen Harris | Legal Services | 2020-02-28 | 28.2.2020 | 28.2.2020 | In progress | 09/12/2019: Articles - to go back to a future Cabinet meeting
Legal | Ealing Side Gel Governance - Directors |  | Helen Harris | Legal Services | 10.1.20 |  |  | In progress
Legal | Ealing Side Gel Governance - Directors Training |  | Helen Harris | Legal Services | 15.1.20 |  |  | In progress
Legal | Arranging training with TLT |  | Helen Harris | Legal Services | 10.1.2020 |  |  | In progress
Legal | Service Provision Agree - GEL and LBE |  | Chuhr Nijjar | Legal Services | 2020-01-10 | 1.10.19 | 1.10.19 | In progress
Legal | SLA support services (Support Services Agreement) |  | Chuhr Nijjar | Legal Services | 20.2.20 | 1.2.20 | 1.2.20 | In progress | 09/12/2019: CNi has written to colleagues on ICT, FM, HR and Finance to ascertain which contracts will need to progress specs for the support services agreement.
Legal | Draft SLA to KL covering heads listed below |  |  |  | 20.2.20 | 1.2.20 | 2019-12-16 | in Progress
Legal | Completion of SLA |  |  |  | 1.7.20 | 1.2.20 | 2019-12-16 | in progress
Legal | obtain SLA details from HR |  | Chuhr Nijjar | Legal Services | 20.2.20 | 1.2.20 | 2019-12-16 | in progress
Legal | obtain SLA details fromLegal Services |  | Chuhr Nijjar | Legal Services | 20.2.20 | 1.2.20 | 2019-12-16 | in progress
Legal | obtain SLA details from Finance |  | Chuhr Nijjar | Legal Services | 20.2.20 | 1.2.20 | 2020-10-01 | In progress | 13/1/2020 Georgia provided draft to John A, John P and Chris. 13/1/2020 Georgia confirmed working on SLA re payments for this week. 6/1/2020 reminded Georgia and John 27/11/2019 Georgia Hoare (& John Parmenter) have Accounts Payable KPIs and deliverables and have been requested to shape to propose to John Arnold, for incorporation into legal agreement
Legal | obtain SLA details from ICT |  | Chuhr Nijjar | Legal Services | 20.2.20 | 1.2.20 | 1.2.20 | In progress
Legal | obtain SLA details from FM |  | Chuhr Nijjar | Legal Services | 20.2.20 | 1.2.20 | 1.2.20 | In progress
Legal | obtain SLA details from Payroll |  | Chuhr Nijjar | Legal Services | 20.2.20 | 1.2.20 | 1.2.20 | In progress
Legal | obtain SLA details fromPensions Administration |  | Chuhr Nijjar | Legal Services | 20.2.20 | 1.2.20 | 1.2.20 | In progress
Legal | obtain SLA details from Procurement Services |  | Chuhr Nijjar | Legal Services | 20.2.20 | 1.2.20 | 1.2.20 | In progress
Legal | Novation of existing contracts |  | Chuhr Nijjar | Legal Services | 2020-05-02 | 1.1.20 | 1.1.20 | In progress | 09/12/2019: Any Amey or LBE contracts to novate to GE. CNi to liasing with colleagues.
Legal | Loan agreement/funding facility agreement |  | Chuhr Nijjar | Legal Services | 1.3.20 | 1.1.20 | 1.1.20 | In progress | 09/12/2019: CNi to liaise with Finance and client officers, including re interest rate
Legal | Draft Loan Agreement to KL |  |  |  | 1.3.20 | 1.1.20 | 2019-12-16 | in progress
Legal | Completion of Loan Agreement |  |  |  | 1.7.20 | 1.1.20 | 2019-12-16 | in progress | Will proress when have the instructions, from Finance Chris Neale, post internal finance discussion and agreement re interest rate
Legal | Novation of procured contracts |  | Chuhr Nijjar | Legal Services | 2020-03-02 |  |  | In progress | 09/12/2019: CNi working with procurement stream.
Legal | Procurements |  | Chuhr Nijjar | Legal Services/ Commercial Hub | 2020-03-02 | 1.1.20 | 01.01.20 | in progress | 09/12/2019: Numerous procurements which will need to be completed before GE commences services provision.
Legal | Vehicle procurement - approve & finalise agreements |  | Chuhr Nijjar | Legal Services/ Commercial Hub | 2020-03-02 | 1.1.20 | 01.01.20 | in progress
Legal | Vehicle Finance Lease & Sub Lease |  | Chuhr Nijjar | Legal Services/ Commercial Hub | 2020-03-02 | 1.1.20 | 01.01.20 | in progress
Legal | Vehicle maintenance procurement - approve & finalise agreements |  | Chuhr Nijjar | Legal Services/ Commercial Hub | 2020-03-02 | 1.1.20 | 01.01.20 | in progress
Legal | Hire vehicles procurement - approve & finalise agreements |  | Chuhr Nijjar | Legal Services/ Commercial Hub | 2020-03-02 | 1.1.20 | 01.01.20 | In progress
Legal | Staffing agencies procurement - approve & finalise agreements |  | Chuhr Nijjar | Legal Services/ Commercial Hub | 2020-03-02 | 1.1.20 | 01.01.20 | in progress
Legal | Equipment procurement -approve & finalise agreements |  | Chuhr Nijjar | Legal Services/ Commercial Hub | 2020-03-02 | 1.1.20 | 01.01.20 | in progress
Legal | Insurance procurement approve & finalise agreements |  | Chuhr Nijjar (TLT) | Legal Services/ Commercial Hub | 2020-03-02 | 1.1.20 | 01.01.20 | in progress | 09/12/2019 Ewan Taylor in Insurance will be instructing contracts team on the procurement
Legal | Property Leases & Licences |  | Jackie Adams |  | 2020-07-01 | 2020-01-01 | 2020-01-01 | in progress
Legal | Heads of terms from LSH |  | Jackie Adams |  | 1.3.20 | 1.1.20 | 1.1.20 | in progress | need to speak to Gary for update
Legal | Lease or Licence Draft |  | Jackie Adams | Commercial Hub/ Legal Services | 6.3.20 | 1.1.20 | 1.1.20 | in progress | 09/12/2019 CNi keeping a watching brief.
Legal | Completion of Lease or Licence |  |  |  | 1.7.20 |  |  | in progress
Legal | AMEY dispute |  | Justin Morley | Legal Services | N/A | N/A | N/A | in progress | 6.9.19 - CNi to talk to JM re impact of dispute on GEL set up . Amey completing schedule for their claim to be provided before Xmas when we will have a better idea of strength of claim.
Procurement | Confirmation of Fleet Delivery time line |  | John Arnold/Sarah Hadland | Procurement | 2020-02-28 | 2020-01-09 | 2019-12-19 | in progress | May be a delay with certain vehicles, however, the contingency is to use manufacturers demo vehicles and/or have an arrangement with Hitachi or TPPL/GoPlant can provide short term hire (minimum 2 months). Meeting end of January; if not comfortable with position - approach hire vehicle companies and/or potentially novate Amey rubbish vehicles.
Procurement | Award Maintenance contract once Tender has finished |  | John Arnold/Sarah Hadland/ Kevin O'Leary/ Vincent Hunt/ Chuhr Nijjar | Procurement | 2020-03-31 | 2019-11-01 | 2019-11-01 | in progress | Tender has been issued and is due back 17/01.
Procurement | Award Bunkered Fuel Contract |  | John Arnold/Sarah Hadland | Procurement | 2020-02-28 | 2020-01-06 | 2020-01-06 | in progress | Mini-competition for bunker fuel has been issued via the LASER Fuel framework w/c 06/01; for return on 20/01. Fuel card requirements need to be confirmed to Commercial Hub.
Procurement | Finish Spec for Occupational Health Contract |  | John Arnold/Sarah Hadland | Procurement | 2020-01-31 | 2020-01-06 | 2019-12-06 | in progress | Currently in final stages there are a couple of things to address such as Ill health retirement
Procurement | Confirm Jewson can supply required tools |  | John Arnold/Sarah Hadland | Procurement | 2020-02-28 | 2020-01-31 | 2020-01-10 | in progress | Tool list created and ready to be sent to Jewson
Procurement | Confirm Office supply route |  |  |  | 2020-02-28 |  |  |  | confirm with ICT and procurement suppliers for office supplys
Procurement | Place final order for small plant with supplier |  | John Arnold/Sarah Hadland/ Chirs Welsh | Procurement | 2020-03-31 | 2020-03-01 | 2020-01-10 | in progress | List has been created, they have offered a demo before placing order which we will be taking advantage of.
Procurement | finalise P.P.E list |  | John Arnold/Sarah Hadland | Procurement | 2020-01-31 | 2020-01-06 | 2019-12-06 | in progress | Amey have supplied PPE information we are waiting for size confirmation before committing to volumes etc. to attach as part of the Tender
Procurement | Agency contract award |  | John Arnold/Sarah Hadland | Procurement | 2020-02-29 | 2020-01-06 | 2019-12-06 | in progress | Meeting arranged with Pertemps in January 2020 to gather info on current staffing requirements. Potential risk of challenge re: using MSTAR Framework due to LATCOs not being named as permissible users - way forward on this has been agreed by GA.
Procurement | finalise H&S system contract (Alcumus) |  | John Arnold/Sarah Hadland/ Chuhr Nijjar | Procurement | 2020-01-31 | 2020-01-06 | 2019-12-06 | in progress | Legal have reviewed the Alcumus contract. Comments/proposed amendments have been sent back to IEX (supplier).
Procurement | Finalise Financing Company |  | John Arnold/Sarah Hadland | Procurement | 2020-02-29 | 2020-01-06 | 2019-12-06 | in progress | List has been finalised by John. The competition for electric vehicles can start January 2020 via Link.
Health & Safety | Recruitment of a health and safety consultant to deliver workplan |  | John Arnold and Kevin O'Leary |  | 2020-03-01 | 2020-01-06 | 2020-01-06 | in progress | Kevin has contacted a H&S colleauge who knows the industary and will assist with the below tasks
Health & Safety | Develop job requirements for H&S consultant |  | John Arnold and Kevin O'Leary |  |  |  |  | in progress
Health & Safety | Appoint candidate to start 01/03/20 |  | John Arnold and Kevin O'Leary |  |  |  |  | In progress
Depot | Workshops\Garages |  |  |  | Thu 23/01/20 | Thu 02/01/20 | Thu 02/01/20 | in progress
Depot | Asbestos work |  | Aspects |  | Thu 23/01/20 | Thu 02/01/20 | Thu 02/01/20 | in progress
Depot | Phase 2 Asbestos Removal Bus Garages |  |  |  | Thu 23/01/20 | Fri 03/01/20 | Fri 03/01/20 | in progress
Depot | Strip A.I.B. Ceiling Soffit |  | Aspects |  | Mon 13/01/20 | Fri 10/01/20 | Fri 10/01/20 | In progress
HR | Arrange employers Liability insurance |  | Ewan re Ins/ Chris |  | 2020-04-01 | 2019-10-01 | 2019-10-01 | In progress | 1/12/2019 Being done by April 2020 by Ewan as part of new Insurance contract for council
HR | Arrange scheme - require PAYE and bank account |  | Chris re bank / Payroll re PAYE then |  | 2020-01-31 | 2019-10-01 | 2019-10-01 | in progress | 14/1/2020 expect bank account this week, and SUN for payroll the following, as all details provided to bank. IT updated. Do not need PAYE registration to start till 6wks before start paying PAYE. 6/1/2020 Chris requested Simon to get details re updated Director Alison Reynolds, to bank, as they requested. 1/12/2019 started getting bank account, earliest hope is Dec 2019
HR | Develop recruitment process for posts | 4 | Sharon Brown | HR | 2020-02-28 | 2020-02-01 | 2020-12-16 | In progress | 16/12/2019 Interim Director already in place, Council Director to make decision about this pending Board being set up. Done for HR Manager & Finance roles but needs process written down for white and blue collar staff.
HR | Develop pay, benefits, and T&Cs for each post above | 4 | Sharon Brown/ Gel Mgmt team/KO'L | HR | 2020-02-28 | 2020-01-06 | 2020-12-16 | In progress | Using ACAS T&C's for new posts. Need to consider how to evaluate any new posts/could use benchmarking data for industry norm.
HR | Develop a specimen contract of employment | 4 | Sharon Brown | HR | 2020-02-28 | 2020-01-17 | 2020-01-06 | In progress | Using ACAS T&C's for new posts and template contract
HR | Work with Procurement to ensure an agency supplier is in place for temp staff | 4 | HR/John Arnold | GEL HR & John | 2020-02-28 | 2020-01-16 | 2020-01-16 | In progress | John seeing Pertemps on Thursday 16th January. Using M-Star framework. Captured in procurement plan.
HR | Create policies and procedures as per ACAS for GEL NEW STARTERS | 7 | HR/KO'L | GEL HR & KO'L | 31/04/2020 | 2020-03-01 | 2020-01-06 | In progress | Already have ACAS example policies.
HR | Redundancy benefits policy | 7 | GEL HR Manager | HR | 31/04/2020 | 2020-03-01 | 2020-01-06 | In progress | Already have ACAS example policies.
HR | Job evaluation procedure | 7 | Sharon Brown/ Gel Mgmt team/KO'L |  | 31/04/2020 | 2020-03-01 | 2020-01-06 | In progress | Already have ACAS example policies.
HR | Pay policy (base pay; overtime; bonuses; shift and other allowances) | 7 | Sharon Brown/ Gel Mgmt team/KO'L |  | 31/04/2020 | 2020-03-01 | 2020-01-06 | In progress | Already have ACAS example policies.
HR | Performance management | 7 | Sharon Brown/ Gel Mgmt team/KO'L |  | 31/04/2020 | 2020-03-01 | 2020-01-06 | In progress | Already have ACAS example policies.
HR | Sickness absence | 7 | Sharon Brown/ Gel Mgmt team/KO'L |  | 31/04/2020 | 2020-03-01 | 2020-01-06 | In progress | Already have ACAS example policies.
HR | Holiday policy and booking process | 7 | Sharon Brown/ Gel Mgmt team/KO'L |  | 31/04/2020 | 2020-03-01 | 2020-01-06 | In progress | Already have ACAS example policies.
HR | Overtime recording process | 7 | Sharon Brown/ Gel Mgmt team/KO'L |  | 31/04/2020 | 2020-03-01 | 2020-01-06 | In progress | Already have ACAS example policies.
HR | Signing in, signing out procedure | 7 | Sharon Brown/ Gel Mgmt team/KO'L |  | 31/04/2020 | 2020-03-01 | 2020-01-06 | In progress | Already have ACAS example policies.
HR | Other absences (paid; unpaid; procedure; entitlement) | 7 | Sharon Brown/ Gel Mgmt team/KO'L |  | 31/04/2020 | 2020-03-01 | 2020-01-06 | In progress | Already have ACAS example policies.
HR | Sick pay policy | 7 | Sharon Brown/ Gel Mgmt team/KO'L |  | 31/04/2020 | 2020-03-01 | 2020-01-06 | In progress | Already have ACAS example policies.
HR | Maternity/paternity/adoption/parental leave | 7 | Sharon Brown/ Gel Mgmt team/KO'L |  | 31/04/2020 | 2020-03-01 | 2020-01-06 | In progress | Already have ACAS example policies.
HR | Working Time Regulations/limits/opting out policy | 7 | Sharon Brown/ Gel Mgmt team/KO'L |  | 31/04/2020 | 2020-03-01 | 2020-01-06 | In progress | Already have ACAS example policies.
HR | Working week/working patterns/rest breaks/toil/overtime | 7 | Sharon Brown/ Gel Mgmt team/KO'L |  | 31/04/2020 | 2020-03-01 | 2020-01-06 | In progress | Already have ACAS example policies.
HR | Disciplinary procedure | 7 | Sharon Brown/ Gel Mgmt team/KO'L |  | 31/04/2020 | 2020-03-01 | 2020-01-06 | In progress | Already have ACAS example policies.
HR | Grievance procedure | 7 | Sharon Brown/ Gel Mgmt team/KO'L |  | 31/04/2020 | 2020-03-01 | 2020-01-06 | In progress | Already have ACAS example policies.
HR | Equal opportunities | 7 | Sharon Brown/ Gel Mgmt team/KO'L |  | 31/04/2020 | 2020-03-01 | 2020-01-06 | In progress | Already have ACAS example policies.
HR | Health and safety | 7 | Sharon Brown/ Gel Mgmt team/KO'L |  | 31/04/2020 | 2020-03-01 | 2020-01-06 | In progress | Already have ACAS example policies.
HR | Smoking at work | 7 | Sharon Brown/ Gel Mgmt team/KO'L |  | 31/04/2020 | 2020-03-01 | 2020-01-06 | In progress | Already have ACAS example policies.
HR | Harassment policy | 7 | Sharon Brown/ Gel Mgmt team/KO'L |  | 31/04/2020 | 2020-03-01 | 2020-01-06 | In progress | Already have ACAS example policies.
HR | Personal records and data protection | 7 | Sharon Brown/ Gel Mgmt team/KO'L |  | 31/04/2020 | 2020-03-01 | 2020-01-06 | In progress | Already have ACAS example policies.
HR | Handling organisational change policy | 7 | Sharon Brown/ Gel Mgmt team/KO'L |  | 31/04/2020 | 2020-03-01 | 2020-01-06 | In progress | Already have ACAS example policies.
HR | References policy | 7 | Sharon Brown/ Gel Mgmt team/KO'L |  | 31/04/2020 | 2020-03-01 | 2020-01-06 | In progress | Already have ACAS example policies.
HR | Handbook (reference to Modern Slavery Act 2015 Regs/Anti corruption policy/Bribery Act 2010). Company property (care, reporting damage, returning, storing, handover, keep it safe) | 7 | Sharon Brown/ Gel Mgmt team/KO'L |  | 31/04/2020 | 2020-03-01 | 2020-01-06 | In progress | Already have ACAS example policies.
HR | Email/internet policy | 7 | Sharon Brown/ Gel Mgmt team/KO'L |  | 31/04/2020 | 2020-03-01 | 2020-01-06 | In progress | Already have ACAS example policies.
HR | Mobile phone policy | 7 | Sharon Brown/ Gel Mgmt team/KO'L |  | 31/04/2020 | 2020-03-01 | 2020-01-06 | In progress | Already have ACAS example policies.
HR | Expenses policy | 7 | Sharon Brown/ Gel Mgmt team/KO'L |  | 31/04/2020 | 2020-03-01 | 2020-01-06 | In progress | Already have ACAS example policies.
HR | Review scope and content of any Amey recognition/ collective agreements | 5 | Sharon Brown/Amey HR | HR | 2019-07-06 | 2019-06-01 | 2019-11-28 | In progress | 1/12 SB: Not sure if this complete. We've had first offical meeting with the TU's, not seen any recognition/collective agreements.
HR | Develop any changes/protocols for LATCo and trade union facilities | 5 | Sharon Brown/ Gel Mgmt team/KO'L |  | 2020-07-06 | 2019-11-28 | 2019-11-28 | In progress | Had initial meeting, regular TU meetings on going.
GEL Tasks | Waste carriers licence |  | John Arnold/ Kevin Oleary |  | 2020-03-01 | 2020-01-06 | 2020-01-06 | in progress | Awaiting for all GEL directors to be added to companies house (X3 directors)
GEL Tasks | Ascertain if there are any Amey vehicles LBE would like to buy |  | John Arnold/ Earl McKenzie/ Kevin O'Leary | Fleet | 2020-03-01 | 2020-01-06 | 2019-12-16 | In Progress | We have requested an updated fleet list with costs so we can make an informed decision
Finance | Insurance | 3 | Chris Neale and Sarah Hadland & Ewan | Service Finance & Insurance | 2020-07-01 | 2020-07-01 | 2020-07-01 | In progress | 8/1/2020 Mary confirmed for Kevin and John that insurance of new fleet subleased to Amey would need be via Amey's insurer. Rest of insurance procurement on track. 7/1/20 Chris organised meeting of John and Kevin with Mary 8/1/20. 22/7/19 Cabinet report authorised procurement, with 30/8/2019 Draft Tender Document, with 6/9/2019 Agree finalised tender specification, with for award 9/3/2020 20/11/2019 Tenders back, with 21/2/2020 Final decision, 9/3/2020 Award Contract
Finance | Making tax digital | 3 | John Parmenter | IT Finance | 2020-03-05 |  |  | In progress | 14/1/2020 confirmed on track, with main item required from HR Payroll, due in few weeks, and no items needed from Finance, next update planned for Wed 26/2. 8/1/2020 requested clarification meeting Tues 14/1/2020 7/1/2020 John requested meeting including Georgia, John wishing to attend also 6/1/2020 Chris noted the request to John Parmenter 10/12/2019 Chris asked John P to confirm following note here 27/11/2019 - KRD asked Chris please specify dates
Finance | Register for VAT | 3 | Chris Neale | Service Finance | 2020-02-28 | 2020-01-15 |  | In progress | 7/1/2020 agreed to discuss further with John Parmenter at 14/1/2020 makingtax digital meeting. 10/12/2019- Chris requested dates from John Pamenter following up request of 23/10/2019 KRD 27/11/2019 - Chris please can you specify dates for this task
Finance | Interest rate determination for state aid purposes | 3 | Chris Neale | Service Finance & Corporate Finance, & Legal | 2020-02-28 | 2019-11-27 | 2019-10-01 | in progress | 27/1/2020 Meeting of Corporate Finance deferred to 30/1 to discuss accounting treatment that might include this 17/1/2020 Meeting requested in Finance for Mon 27/1 re Lease Finance accounting at which will agree next steps for this. 10/1/2020 LINK agreed re lease finance to ensure quotes requested for funding LATCO direct also, so that covered. (Chris separately to look at documenting confirmation that interest rates on any council loans correct to avoid being state aid). 10/12/2019 Chris requested Tim and Sarah re the timing of this, following up request of 11/11, where requested that the quotes include leasing via the Council and also direct to LATCO to show the difference to be charged by Council to avoid providing state aid. 10/12/2019 Chris also followed with Peterborough LATCO re 10/11 request re the calculation of the state aid compliant interest on loans from the council KRD 27/11/2019 - What is involved to get this figure
Finance | Accounts Payable SLA deliverable and volumes and KPIs | 3 | Georgia Hoare | Service Finance, & Accounts Payable | 2020-01-31 | 2019-11-27 | 2019-10-01 | In progress | 13/1/2020 Georgia Hoare confirmed would complete in next few days what possible now, conferring with John Parmenter where needed, and ensure note of what awaits further decisions, for her successor Liz. 7/1/2020 Georgia Hoare proposed would attend to Wed 8/1/2020 so completed this week. 6/1/2020 reminded Georgia Hoare. 10/12/2019 reminded Georgia Hoare re proforma given 27/11 to her so has info to complete At 6/1/2020 getting at risk of timescale
Finance | Agree payment mechanism for LBE /GEL contract and arrangement between GEL and LBE | 3 | Chris Neale/ Shabana Kausar / Simon Peet | Service Finance & Corporate Finance, & Legal | 2020-02-15 | 2019-11-27 | 2019-10-01 | In progress | 27/1/2020 Meeting of Corporate Finance deferred to 30/1 to discuss accounting treatment that might include this 23/1/2020 Noted to Simon Peet that await answer and requested he get answer in next meeting with PwC. 1/12 Awaits SLA being further developed, to then progress At 6/1/2020 timescale of Jan not likely, however not absolutely nec till later
Health & Safety | Agree approach to the develop of route risk assessments |  | Health and safety consultant & GEL Board |  |  |  |  | Not started | have Amey's Risk Assessments which we can use as a start point
Health & Safety | Understand COSHH requirements across the service |  | Health and safety consultant & GEL Board |  |  |  |  | Not started | have Amey's COSHH Assessments which we can use as a start point
Health & Safety | Health and Safety |  | Health and safety consultant & GEL Board |  |  |  |  | Not started | Need to develop a H&S Policy have a draft one for GEL from the HSE website
Health & Safety | Environment |  | Health and safety consultant & GEL Board |  |  |  |  | Not started | Need to develop a Policy
Health & Safety | Develop risk assessments for all operations |  | Health and safety consultant & GEL Board |  |  |  |  | Not started | have Amey's Risk Assessments which we can use as a start point
Health & Safety | Develop Safe Systems of Work for waste operations |  | Health and safety consultant & GEL Board |  |  |  |  | Not started | Have Amey's SSOW can be used as a start point
Health & Safety | Identify training requirements for day one and on an ongoing basis |  | Health and safety consultant & GEL Board |  |  |  |  | Not started | Ask Amey for their training matrix and highlight the training they actually carry out
Health & Safety | Approval of risk assessments |  | Health and safety consultant & GEL Board |  |  |  |  | Not started | Need to speak to LBE H&S for support RE. using Amey's Risk Assessments as a start point of the contract and review as we go during the 1st 6 months of GEL
Health & Safety | Undertake route risk assessments |  | Health and safety consultant & GEL Board |  |  |  |  | Not started | Have Amey's RRRA
Health & Safety | Approval of Safe Systems of Work |  | Health and safety consultant & GEL Board |  |  |  |  | Not started | Need to speak to LBE H&S for support RE. using Amey's SSOW as a start point of the contract and review as we go during the 1st 6 months of GEL
Health & Safety | Undertake Fire Risk Assessment on the new depot area |  | Health and safety consultant & GEL Board |  |  |  |  | Not started | Should be pre existing as LBE depot
Health & Safety | Develop evacuation plan for depot |  | Health and safety consultant & GEL Board |  |  |  |  | Not started | Should be pre existing as LBE depot
Health & Safety | Approval of route risk assessments |  | Health and safety consultant & GEL Board |  |  |  |  | Not started | Need to speak to LBE H&S for support RE. using Amey's RRRA as a start point of the contract and review as we go during the 1st 6 months of GEL
Health & Safety | Training and dissemination of risk assessments |  | Health and safety consultant & GEL Board |  |  |  |  | Not started | Training will be carried out as part of the induction (induction plan to still be drafted)
Health & Safety | Training and dissemination of route risk assessments |  | Health and safety consultant & GEL Board |  |  |  |  | Not started | Training will be carried out as part of the induction (induction plan to still be drafted)
Health & Safety | Training and dissemination of Safe Systems of Work |  | Health and safety consultant & GEL Board |  |  |  |  | Not started | Finance will need to be involved in this as there will be a cost element I.E overtime paid to amey to train the staff before go live date
Health & Safety | H&S policy |  | Health and safety consultant & GEL Board |  |  |  |  | Not started
Finance | PAYE registering | 3 | Chris Neale | Service Finance | 2020-05-04 | 2020-01-31 |  | Not started | 10/12/2019 Chris noted update, provided 23/10.2019, that should not start to register payroll until 4 week before have staff on payroll if do on the phone (max 8 weeks before have staff on payroll, if online), to avoid having payroll fines of £100-£400. KRD 27/11/2019 - Chris please can you specify dates for this task
HR | Set up a workplace pension |  | Lara Balogun | Payroll | 2020-06-06 | 2020-06-05 |  | Not started
ICT | Payroll file from HR to be received by BW team |  |  | HR | 2020-01-15 | 2019-11-11 |  | Not started
ICT | HR BACS file updated |  |  | HR | 2020-04-01 | 2020-04-01 |  | Not started
ICT | MTD - VAT Tax codes into iTrent |  |  | HR | 2019-12-31 | 2019-12-31 |  | Not started
ICT | SUN (Service User) numbers for bank account provided to HR |  | Christopher Neale | Finance | 2019-12-31 | 2019-12-31 |  | Not started
ICT | Business World GEL | 8 | James Pugh | BW Team | 2020-07-07 | 2019-12-19 |  | Not started
ICT | GEL BW Client Build | 8 |  | BW Team | 2020-04-06 | 2019-12-19 |  | Not started
ICT | Design | 8 |  | BW Team | 2019-12-30 | 2019-12-19 |  | Not started
ICT | System set up | 8 |  | BW Team | 2020-01-14 | 2020-01-01 |  | Not started
ICT | Accounts payable | 8 |  | BW Team | 2020-02-04 | 2020-01-15 |  | Not started
ICT | Accounts receivable | 8 |  | BW Team | 2020-02-19 | 2020-02-05 |  | Not started
ICT | Integration | 8 |  | BW Team | 2020-03-05 | 2020-02-20 |  | Not started
ICT | Making tax digital installation of BW module and client | 8 |  | BW Team | 2020-03-05 | 2020-02-20 |  | Not started
ICT | Systems test and fix | 8 |  | BW Team | 2020-03-19 | 2020-03-06 |  | Not started
ICT | Set up balance tables, planner revenue, capital, logistics, actuals data | 8 |  | BW Team | 2020-03-24 | 2020-03-20 |  | Not started
ICT | Set up basic reporting, AP, AR, trial balance | 8 |  | BW Team | 2020-03-30 | 2020-03-24 |  | Not started
ICT | Banking set up facility for manual upload of statement into BW | 8 |  | BW Team | 2020-04-02 | 2020-03-31 |  | Not started
ICT | BW Development and system testing complete | 8 |  | BW Team | 2020-04-06 | 2020-04-03 |  | Not started
ICT | GEL UAT Post Build Test and Train | 8 |  |  | 2020-07-07 | 2020-04-07 |  | Not started
ICT | BW UAT | 8 |  | MS (ICT applications development) | 2020-04-27 | 2020-04-07 |  | Not started
ICT | BW Training | 8 |  | MS (ICT applications development) | 2020-05-04 | 2020-04-21 |  | Not started
ICT | BW - data input | 8 |  | Business/Finance | 2020-05-08 | 2020-05-05 |  | Not started
ICT | Testing, ready for go-live | 8 |  | Business/Finance/HR | 2020-07-02 | 2020-05-11 |  | Not started
ICT | Go live/no go-live decision | 8 |  | Programme Team | 2020-07-03 | 2020-07-03 |  | Not started
ICT | Go live | 8 |  | Finance Apps support | 2020-07-07 | 2020-07-07 |  | Not started
ICT | Sign-off | 8 | Edward Axe | ICT | 2019-11-29 | 2019-11-29 |  | Not started
ICT | Whitespace configuration | 8 |  | Supplier PM | 2019-01-02 | 2019-11-29 |  | Not started
ICT | Whitespace mobile configuration | 8 |  | Supplier PM | 2019-11-27 | 2019-11-25 |  | Not started
ICT | Whitespace workshop | 8 |  | Supplier and business | 2019-12-06 | 2019-12-06 |  | Not started
ICT | Internal testing | 8 |  | Supplier PM | 2019-01-10 | 2019-01-06 |  | Not started
ICT | vehicle kit out | 8 |  | Supplier PM | 2020-02-14 | 2020-02-03 |  | Not started
ICT | Contender integration specification | 8 | Faisal and Michael T | ICT | 2019-11-29 | 2019-11-29 |  | Not started
ICT | Contender integration development and testing | 8 |  | Contender | 2020-02-27 | 2019-12-02 |  | Not started
ICT | Training | 8 |  | Supplier PM and business | 2020-02-20 | 2020-01-27 |  | Not started
ICT | UAT | 8 |  | Business | 2020-04-06 | 2020-03-10 |  | Not started
ICT | Ready for go-live - parallel running | 8 |  | ICT/Supplier/business | 2020-04-14 | 2020-04-14 |  | Not started
ICT | Analytics delivery | 8 |  | Supplier PM | 2020-05-27 | 2020-04-15 |  | Not started
ICT | Complete go-live by turning off parallel running | 8 |  |  | 2020-06-02 | 2020-06-02 |  | Not started
ICT | Order and receive kit | 8 |  | ICT PM | 2020-01-20 | 2019-12-17 |  | Not started
ICT | Order and receive BT lines | 8 |  | ICT Infrastructure | 2020-02-03 | 2019-12-17 |  | Not started
ICT | Network/wifi implement | 8 |  | ICT Networks | 2020-02-24 | 2020-02-04 |  | Not started
ICT | Build hardware of site | 8 |  | ICT PM | 2020-02-24 | 2020-01-21 |  | Not started
ICT | Desktop hardware - implement | 8 |  | ICT PM | 2020-03-02 | 2020-02-25 |  | Not started
ICT | Telephony - implement | 8 |  | ICT PM | 2020-03-09 | 2020-02-25 |  | Not started
ICT | Printers - implement | 8 |  | ICT PM | 2020-03-09 | 2020-02-25 |  | Not started
ICT | Implement furniture | 8 |  | ICT PM | 2020-02-17 | 2020-01-21 |  | Not started
ICT | Test and completion | 8 |  | ICT PM / Business | 2020-04-06 | 2020-03-10 |  | Not started
ICT | Support ICT | 8 |  | ICT PM | 2020-07-09 | 2019-11-27 |  | Not started
ICT | Commercials - ICT | 8 |  | ICT Commercials | 2019-12-03 | 2019-11-27 |  | Not started
ICT | Business applications support | 8 |  | ICT Applications Support | 2020-07-09 | 2019-12-17 |  | Not started
ICT | Business world support | 8 |  | ICT Applications Support | 2020-07-09 | 2019-12-17 |  | Not started
ICT | Network support | 8 |  | ICT Infrastructure | 2020-07-09 | 2019-02-25 |  | Not started
ICT | Hardware support | 8 |  | ICT Operations | 2020-04-23 | 2019-12-17 |  | Not started
ICT | HOTS sign-off | 8 |  | ICT Operations | 2020-06-25 | 2019-12-17 |  | Not started
Legal | Provision of training to Ealing Directors |  | Helen Harris | Legal Services | 15.1.20 |  |  | Not started | 9/12/2019 HH to arrange training via TLT and include all relevant officers
Legal | Completion of Agreement - executed by both parties |  |  |  | 1.7.20 |  |  | Not started
Legal | TUPE information to insert into Services Agreement |  | Chuhr Nijjar | Legal Services/HR | ? | ? |  | Not started | Requst to Amey sent 19.12.2019 awaiting update. Amey was chased WC 06.01.20
Legal | Pensions |  | Chuhr Nijjar | Legal Services/HR | 2020-03-02 | ? |  | Not started | 09/12/2019: Meeting with HR who are progressing these arrangements and have been advised to obtain pension panel authority for admission agreement.
Legal | NEST for new staff |  | Shahzad Ayub | Legal Services/HR | 2020-05-02 | 2020-04-02 | ? | Not started
Legal | Authority to enter into Admission Agreement from Pension Panel |  |  |  | 2020-05-02 |  |  | Not started
Legal | LGPS - Admission Agreement draft to KL |  | Chuhr Nijjar | Legal Services/HR | 2020-03-02 | ? |  | Not started
Legal | Other products and services procurement -approve & finalise agreements |  | Chuhr Nijjar | Legal Services/ Commercial Hub | 2020-03-02 | 1.1.20 | 01.01.20 | Not started
Procurement | Approach hire vehicle companies and/or potentially novate Amey vehicles if not comfortable with position |  | John Arnold/Sarah Hadland | Procurement | 2020-02-28 |  |  | Not started
Procurement | Award Occupational Health Contract |  | John Arnold/Sarah Hadland | Procurement | 2020-03-31 |  |  | Not started
Procurement | Award P.P.E supplier contract & place order |  | John Arnold/Sarah Hadland | Procurement | 2020-02-28 |  |  | Not started
Procurement | Storage - find storage for fleet if required |  | John Arnold/Sarah Hadland | Procurement | 2020-02-29 |  |  | Not started | Need to find enough storage for the fleet if we cannot do a staggered delivery
Depot | Fine Clean Enclosure |  | Aspects |  | Sun 12/01/20 | Fri 10/01/20 |  | Not started
Depot | Air Test Enclosure |  | Riverside |  | Sun 19/01/20 | Sat 18/01/20 |  | Not started
Depot | Strip down Enclosure |  | Aspects |  | Mon 13/01/20 | Fri 10/01/20 |  | Not started
Depot | Dismantle Scaffolding |  | Aspects |  | Thu 23/01/20 | Wed 22/01/20 |  | Not started
Depot | Roof Works |  | Global Waterproofing |  | Fri 28/02/20 | Thu 02/01/20 |  | Not started
Depot | Phase 3 Roof Works | [6 empty] | Not started
Depot | Inspections |  | Global Waterproofing |  | Thu 02/01/20 | Thu 02/01/20 |  | Not started
Depot | Pre-Start Meeting |  | Global Waterproofing |  | Mon 13/01/20 | Mon 13/01/20 |  | Not started
Depot | Site Set Up |  | Global Waterproofing |  | Wed 22/01/20 | Mon 20/01/20 |  | Not started
Depot | External Cladding |  | Global Waterproofing |  | Wed 29/01/20 | Thu 23/01/20 |  | Not started
Depot | Bird netting |  | Extreme Environmental |  | Fri 31/01/20 | Thu 30/01/20 |  | Not started
Depot | Scaffolding/ roof set up |  | Global Waterproofing |  | Thu 30/01/20 | Wed 29/01/20 |  | Not started
Depot | Roof Coatings/ Roof lights |  | Global Waterproofing |  | Sat 22/02/20 | Thu 30/01/20 |  | Not started
Depot | Finalise |  | Global Waterproofing |  | Mon 24/02/20 | Sun 23/02/20 |  | Not started
Depot | Clear Site |  | Global Waterproofing |  | Thu 27/02/20 | Thu 27/02/20 |  | Not started
Depot | Completion |  | Global Waterproofing |  | Fri 28/02/20 | Fri 28/02/20 |  | Not started
Depot | Heating works |  | TBD |  | Fri 27/03/20 | Mon 02/03/20 |  | Not started
Depot | Re-instating heating at workshops\garages |  | TBD |  | Fri 27/03/20 | Mon 02/03/20 |  | Not started
Depot | Clearing of rubbish at the site |  | TBD |  | Fri 10/01/20 | Wed 18/12/19 |  | Not started
Depot | Clearing of rubbish at the site for lanscaping |  | TBD |  | Fri 10/01/20 | Wed 18/12/19 |  | Not started
Depot | Parking |  | TBD |  | Mon 02/03/20 | Mon 02/03/20 |  | Not started
Depot | Parking area for 150 vehicles |  | TBD |  |  | TBD |  | Not started
Depot | 20 Electric Charge points |  | TBD |  |  | TBD |  | Not started
Depot | All other requirements |  | TBD |  | Tue 10/03/20 | Mon 02/03/20 |  | Not started
Depot | Facilities currently in use by AMEY to be provided to GEL |  | TBD |  | Tue 10/03/20 | Mon 02/03/20 |  | Not started
HR | Register with HMRC |  | Lara Balogun |  | 2020-05-06 | 2020-04-06 |  | Not started | 1/12 to register with HMRC re PAYE once ready to have payroll
HR | HMRC to issue Company with Payroll Scheme Number |  | Lara Balogun |  | 2020-06-06 | N/A |  | Not started
HR | Register Company with NEST |  | Lara Balogun |  | 2020-06-06 | 2020-05-06 |  | Not started | 1/12 Company registered Oct 19 with Companies House, to register re Pension once registered for PAYE
HR | Develop a TUPE transfer process and ensure smooth transition of Amey staff to the LATCO | 5 | Sharon Brown | Interim HR Lead | 2020-06-01 | 2020-01-31 |  | Not started | Need to take into account Amey's Mobilation Plan/current non contact wth Amey HR rep
HR | Complete due diligence/gap analysis of ELI | 5 | Sharon Brown | Interim HR Lead | 2020-06-01 | 2020-02-28 |  | Not started | 28/11/2019: What LATCo provisions are envisaged, as formulating them is a task in itself? SB: need to have productive dialogue with Amey HR re completion of TUPE spreadsheet. Amey mobilition plan states information to be provided 22/6/20!
HR | Identify and agree which roles/who should transfer | 5 | HR/ GEL Mgmt Team |  | 2020-06-01 | 2020-02-28 |  | Not started | 16/12 SB: Can't do this until Amey have provided TUPE list
HR | Develop proposals for any measures, including negotation on any new contractual provisions. | 5 | HR/ GEL Mgmt Team |  | 2020-06-01 | 2020-04-01 |  | Not started | 03/12/2019: need discussion with TU - need to jointly agreed and send measures letter re any proposed changes
HR | Develop staff consultation plan | 5 | HR/ GEL Mgmt Team |  | 2020-06-01 | 2020-04-29 |  | Not started | 3/12/2019: consultation plan needs to be devised in January 2020. Amey's mobilation plan suggests agreeing timetable for consultation in April, 18/5/20-19/6/20 to carry out consulation meetings and issuing letters to staff
HR | Agree consultation plan with trade unions | 5 | HR/KO'L | Earl? | 2020-06-01 | 2020-04-29 |  | Not started
HR | Develop the staff consultation information, and consult | 5 | Sharon Brown |  | 2020-06-01 | 2020-04-29 |  | Not started
HR | Manage the staff transfer process | 5 | Sharon Brown | Andrew Scully as overall manager of shared service | 2020-07-06 | 2020-06-06 |  | Not started | 28/11/2019: LBE's HR Shared Service Centre can be mobilised as a virtual team to support the TUPE document checking process for eligibility to work docs/checks
HR | Ensure payroll provider has TUPE transfer payroll data for payroll | 5 | Ealing/Amey Payroll contacts | HR and Amey | 2020-06-07 | 2020-06-06 |  | Not started | Need to facilitate introduction of Ealing and Amey payroll contact
HR | Staff induction | 5 | Sharon Brown/ Gel Mgmt team/KO'L | GEL HR & ICT | 2020-07-06 | 2020-04-01 |  | Not started | To be developed by new HR Manager in conjunction with MD. ICT element being covered by ICT project plan
HR | Review existing AMEY policies and procedures, amending to fit GEL (POLICIES REQUIRED FROM AMEY) | 7 | Sharon Brown |  | 2020-07-30 | 2020-06-30 |  | Not started | 16/12 Awaiting these being supplied. This can be done post transfer, as will need to consult on any changes proposed with staff group and the TU's.
HR | Redundancy benefits policy | 7 | GEL HR Manager | HR | TBA | TBA |  | Not started
HR | Job evaluation procedure | 7 | Sharon Brown/ Gel Mgmt team/KO'L |  | TBA | TBA |  | Not started
HR | Pay policy (base pay; overtime; bonuses; shift and other allowances) | 7 | Sharon Brown/ Gel Mgmt team/KO'L |  | TBA | TBA |  | Not started
HR | Performance management | 7 | Sharon Brown/ Gel Mgmt team/KO'L |  | TBA | TBA |  | Not started
HR | Sickness absence | 7 | Sharon Brown/ Gel Mgmt team/KO'L |  | TBA | TBA |  | Not started
HR | Holiday policy and booking process | 7 | Sharon Brown/ Gel Mgmt team/KO'L |  | TBA | TBA |  | Not started
HR | Overtime recording process | 7 | Sharon Brown/ Gel Mgmt team/KO'L |  | TBA | TBA |  | Not started
HR | Signing in, signing out procedure | 7 | Sharon Brown/ Gel Mgmt team/KO'L |  | TBA | TBA |  | Not started
HR | Other absences (paid; unpaid; procedure; entitlement) | 7 | Sharon Brown/ Gel Mgmt team/KO'L |  | TBA | TBA |  | Not started
HR | Sick pay policy | 7 | Sharon Brown/ Gel Mgmt team/KO'L |  | TBA | TBA |  | Not started
HR | Maternity/paternity/adoption/parental leave | 7 | Sharon Brown/ Gel Mgmt team/KO'L |  | TBA | TBA |  | Not started
HR | Working Time Regulations/limits/opting out policy | 7 | Sharon Brown/ Gel Mgmt team/KO'L |  | TBA | TBA |  | Not started
HR | Working week/working patterns/rest breaks/toil/overtime | 7 | Sharon Brown/ Gel Mgmt team/KO'L |  | TBA | TBA |  | Not started
HR | Disciplinary procedure | 7 | Sharon Brown/ Gel Mgmt team/KO'L |  | TBA | TBA |  | Not started
HR | Grievance procedure | 7 | Sharon Brown/ Gel Mgmt team/KO'L |  | TBA | TBA |  | Not started
HR | Equal opportunities | 7 | Sharon Brown/ Gel Mgmt team/KO'L |  | TBA | TBA |  | Not started
HR | Health and safety | 7 | Sharon Brown/ Gel Mgmt team/KO'L |  | TBA | TBA |  | Not started
HR | Smoking at work | 7 | Sharon Brown/ Gel Mgmt team/KO'L |  | TBA | TBA |  | Not started
HR | Harassment policy | 7 | Sharon Brown/ Gel Mgmt team/KO'L |  | TBA | TBA |  | Not started
HR | Personal records and data protection | 7 | Sharon Brown/ Gel Mgmt team/KO'L |  | TBA | TBA |  | Not started
HR | Handling organisational change policy | 7 | Sharon Brown/ Gel Mgmt team/KO'L |  | TBA | TBA |  | Not started
HR | References policy | 7 | Sharon Brown/ Gel Mgmt team/KO'L |  | TBA | TBA |  | Not started
HR | Handbook (reference to Modern Slavery Act 2015 Regs/Anti corruption policy/Bribery Act 2010). Company property (care, reporting damage, returning, storing, handover, keep it safe) | 7 | Sharon Brown/ Gel Mgmt team/KO'L |  | TBA | TBA |  | Not started
HR | Email/internet policy | 7 | Sharon Brown/ Gel Mgmt team/KO'L |  | TBA | TBA |  | Not started
HR | Mobile phone policy | 7 | Sharon Brown/ Gel Mgmt team/KO'L |  | TBA | TBA |  | Not started
HR | Expenses policy | 7 | Sharon Brown/ Gel Mgmt team/KO'L |  | TBA | TBA |  | Not started
HR | Identify local reps/shop stewards and what the consultative requirements are | 5 | Sharon Brown/ Gel Mgmt team/KO'L |  | 2020-07-06 | 2020-06-01 |  | Not started | Could discuss with Dean Gilligan at next TU meeting
GEL Tasks | Negotiate deal with Amey |  | John Arnold/ Earl McKenzie/ Kevin O'Leary | Fleet | 2020-04-01 | 2020-02-01 |  | Not Started | We have a fleet consultant who will assist the project in the O Licence application and check that our plans keep us compliant
GEL Tasks | Work Out who COTC Holder Is |  | John Arnold/ Earl McKenzie/ Kevin O'Leary | Fleet | 2020-07-01 | 2020-02-01 |  | Not Started | We have a fleet consultant who will assist the project in the O Licence application and check that our plans keep us compliant
GEL Tasks | Apply for O Licence |  | John Arnold/Kevin O'Leary + Consultant | Fleet | 2020-07-01 | 2020-02-01 |  | Not Started | We have a fleet consultant who will assist the project in the O Licence application and check that our plans keep us compliant
GEL Tasks | Transport Manager CPC holder(Green Recruitment time) |  | John Arnold/Kevin O'Leary + Consultant | Fleet | 2020-07-01 | 2020-02-01 |  | Not Started | We have a fleet consultant who will assist the project in the O Licence application and check that our plans keep us compliant
GEL Tasks | O Licence Granted |  | John Arnold/Kevin O'Leary + Consultant | Fleet | 2020-07-01 | 2020-02-01 |  | Not Started | We have a fleet consultant who will assist the project in the O Licence application and check that our plans keep us compliant
GEL Tasks | V5s handed over |  | John Arnold/Kevin O'Leary + Consultant | Fleet | 2020-07-01 | 2020-02-01 |  | Not Started | We have a fleet consultant who will assist the project in the O Licence application and check that our plans keep us compliant
GEL Tasks | Keys and spares handed over |  | John Arnold/Kevin O'Leary + Consultant | Fleet | 2020-07-01 | 2020-02-01 |  | Not Started | We have a fleet consultant who will assist the project in the O Licence application and check that our plans keep us compliant
GEL Tasks | Maintenance records handed over |  | John Arnold/Kevin O'Leary + Consultant | Fleet | 2020-07-01 | 2020-02-01 |  | Not Started | We have a fleet consultant who will assist the project in the O Licence application and check that our plans keep us compliant
GEL Tasks | MOT records handed over |  | John Arnold/Kevin O'Leary + Consultant | Fleet | 2020-07-01 | 2020-02-01 |  | Not Started | We have a fleet consultant who will assist the project in the O Licence application and check that our plans keep us compliant
GEL Tasks | LOLER records handed over |  | John Arnold/Kevin O'Leary + Consultant | Fleet | 2020-07-01 | 2020-02-01 |  | Not Started | We have a fleet consultant who will assist the project in the O Licence application and check that our plans keep us compliant
GEL Tasks | Understand current defect process |  | John Arnold/Kevin O'Leary + Consultant | Fleet | 2020-07-01 | 2020-02-01 |  | Not Started | We have a fleet consultant who will assist the project in the O Licence application and check that our plans keep us compliant
GEL Tasks | Make sure each round/beat has a map and a road list of each day |  | John Arnold/Kevin O'Leary |  | 2020-07-01 | 2020-05-01 |  | Not Started
GEL Tasks | Highlight assisted and ensured collections on each round |  | John Arnold/Kevin O'Leary |  | 2020-07-01 | 2020-05-01 |  | Not Started
Finance | Handover information for GEL New Finance Manager | 3 | Chris Neale | Service Finance | 2020-03-15 | 2020-02-01 | 2020-02-01 | Not started
Finance | Sort out appointment of auditor | 3 | Chris Neale / Simon Peet | Service & Corporate Finance |  | 2020-02-01 |  | In progress | 27/1/2020 Chris asked Deloitte again for response this week. 7/1/2020 Chris asked Simon to ask Deloitte how wished formalised. 7/1/2020 Chris to contact Deloitte re how to appoint. 6/1/2019 Chris got info from Simon Peet re Deloittes auditors, and asked Simon how to progress, and from Simon re PwC tax advisor.
Finance | Sort out if tax advisor required | 3 | Chris Neale / Simon Peet | Service & Corporate Finance |  | 2020-02-01 |  | Completed | 9/1/2020 Chris contacted PwC outlining main points on which may seek advice. 6/1/2020 Chris got info from Simon Peet re Deloittes auditors, and asked Simon how to progress, and from Simon re PwC tax advisor.
HR | Broadly equivalent LGPS or Admitted Body Status scheme for ex Ealing employees (up to 17) |  | Jenny Connett/Chuhr |  | 2020-07-06 | 2020-05-06 |  | Not Started | Needs two months lead in to complete tasks
HR | What are the tasks under the above milestone? |  | Jenny Connett/Chuhr |  | 2020-07-06 | 2020-05-06 |  | Not Started | Need Amey to confirm TUPE data and names that need to be put into LGPS
HR |  |  | Jenny Connett/Chuhr |  | 2020-07-06 | 2020-05-06 |  | Not Started | SB emailed Jenny re tasks on 13/1/20
HR |  |  | Jenny Connett/Chuhr |  | 2020-07-06 | 2020-05-06 |  | Not Started
HR |  |  | Jenny Connett/Chuhr |  | 2020-07-06 | 2020-05-06 |  | Not Started
HR | Training & Development Plan |  | GEL HR |  | POST GO LIVE
HR | Apprenticeship Programme |  | GEL HR |  | POST GO LIVE
HR | Employment links with local employers and schools |  | GEL HR |  | POST GO LIVE
GEL Tasks | ABP Permit (free) |  |  |  | POST GO LIVE
Note on B54: John Arnold: Milestone
Note on B55: John Arnold: Tasks to complete Milestone