## Sheet1
Ealing Risk Management
Street Services
Risk (Threat to achievement of business objective) | Objective | Risk Type | Assessment of Risk (Assume NO controls in place) |  |  |  | Risk Control Measures |  | Control Owners | Assessment of Residual Risk (With controls in place)
|  |  | Impact (Severity) | Likelihood (Probability) |  | Risk Rating |  |  |  | Impact (Severity) | Likelihood (Probability) | Residual Risk Rating
ECSW0005 - Employee relations Amey providing TUPE data only 28 days before go live (creates pressure as little time to resolve data issues) Risk Owner : John Arnold |  | People | Major | Likely |  | High | • | Early data request Request earlier information from Amey, have Agency supplier ready for day one to reduce/ fill any gaps. GEL have already begun to recruit senior team for key positions such as HR manager and Finance manager for GEL. First draft of ELI data received W/C 20/04/2020. Implemented | John Arnold | Moderate | Possible | Medium
|  |  | 4 | 4 | 20 |  |  |  |  | 3 | 3 | 12
ECSW0006 - Maintaining statutory services Non-delivery of vehicles for waste collections Risk Owner : John Arnold |  | Service Delivery | Major | Likely |  | High | • | Short-term hire/novation Utilise a combination approach of: A) Novate some of Amey fleet across for short term B) Short term hire and charge back to the suppliers (term in vehicle tender contract) C) use the suppliers demo fleet where possible to plug gaps In Progress | John Arnold | Moderate | Unlikely | Low
|  |  | 4 | 4 | 20 |  |  |  |  | 3 | 2 | 9
ECSW0007 - Contract Amey relationship breakdown making mobilisation problematic and service inherited very poor. Risk Owner : John Arnold |  | Contractual/Partnership | Major | Possible |  | Medium | • | Enhanced contract management LBE team continue engagement with Amey and monitor contract performance Implemented & Ongoing | John Arnold | Moderate | Possible | Medium
|  |  | 4 | 3 | 16 |  |  |  |  | 3 | 3 | 12
ECSW0008 - Priorities and objectives Fleet delivered all at once, i.e. weekend before go live (impacts on all services as vehicle familiarisation training required may not be finished impacts service throughout the rest of the week) Risk Owner : John Arnold |  | Service Delivery | Major | Possible |  | Medium | • | Negotiate with suppliers to deliver at suitable times In Progress | John Arnold | Minor | Unlikely | Low
|  |  | 4 | 3 | 16 |  |  |  |  | 2 | 2 | 6
ECSW0009 - Service delivery No Amey agreement achieved which results in insufficient storage space |  | Service Delivery | Major | Possible |  | Medium | • | Reach agreement with suppliers Reach agreement with suppliers to store vehicles In Progress | John Arnold | Minor | Unlikely | Low
|  |  | 4 | 3 | 16 |  |  |  |  | 2 | 2 | 6
Risk Owner : John Arnold
ECSW0010 - Service delivery COVID-19 presents significant risk to the Greener Ealing Programme. The risk presented by the pandemic could affect these key areas of the Programme: - supply chains - the building of ICT business systems requisite to normal service delivery - workforce (if a third of the workforce were to be absent resultant of COVID-19, this would affect both the delivery of the programme and the delivery of normal service post go-live. Risk Owner : John Arnold |  | People | Major | Very Likely |  | High | • | Dialogue with supply chains Keep an open dialog with suppliers weekly where possible order now and store E.G tools, Bags, ICT Hardware. In Progress | John Arnold | Moderate | Likely | Medium
|  |  | 4 | 5 | 24 |  |  |  |  | 3 | 4 | 15
[7 empty] | • | (workforce) early recruitment Letter of intent given to GEL Agency supplier to start early recruitment. Default position if third of work force affected, operate a reduced service inline with Legal requirements such as waste collections. In Progress | John Arnold