## Sheet1
Ealing Risk Management
Greener Ealing Ltd
Risk (Threat to achievement of business objective) | Objective | Risk Type | Assessment of Risk (Assume NO controls in place) |  |  |  | Risk Control Measures |  | Control Owners | Assessment of Residual Risk (With controls in place)
|  |  | Impact (Severity) | Likelihood (Probability) |  | Risk Rating |  |  |  | Impact (Severity) | Likelihood (Probability) | Residual Risk Rating
GEL0001 - Other legislation and/or regulation There is a risk that the overall induction programme is not completed by the end of August 2020. The elements of induction that are legally required are the following: - right to work checks; - driver licence checks; - staff one-to-ones. Risk Owner : John Arnold |  | Legal & Regulatory
[5 empty] | 0 | [6 empty] | 0
GEL0002 - Budgetary management and control Sickness absence resulting in various and significant operational and financial continuity issues. Risk Owner : Killian Rosato-Dooey |  | Financial Reporting | Major | Likely |  | High | • | Monthly sickness monitoring Monthly sickness monitoring by operational/business area and time of year. Proposed | Killian Rosato-Dooey | Moderate | Likely | Medium
|  |  | 4 | 4 | 20 |  |  |  |  | 3 | 4 | 15
[7 empty] | • | Ensuring compliance with relevant government regulations and guidance concerning COVID-19. Ensuring compliance with relevant government regulations and guidance concerning COVID-19. In Progress | John Arnold
GEL0004 - Business continuity Increased use of agency staff. Risk Owner : John Arnold |  | Financial Reporting | Moderate | Very Likely |  | Medium | • | Monthly monitoring report Reviewing the monthly monitoring report for sickness absence levels. Proposed | John Arnold | Moderate | Likely | Medium
|  |  | 3 | 5 | 18 |  |  |  |  | 3 | 4 | 15
GEL0005 - Budgetary management and control Inclement weather or other environmental/health disaster. Risk Owner : Killian Rosato-Dooey |  | Financial Reporting | Moderate | Possible |  | Medium | • | Contingency planning Contingency planning to mitigate the impact financially and reputationally from inclement weather affecting service delivery. Proposed | Killian Rosato-Dooey | Moderate | Possible | Medium
|  |  | 3 | 3 | 12 |  |  |  |  | 3 | 3 | 12
GEL0006 - Loss or damage of assets Wear and tear costs to fleet. Risk Owner : John Arnold |  | Safeguarding Assets | Moderate | Likely |  | Medium | • | Monthly monitoring report Review monthly monitoring report to identify areas/vehicles, number of vehicles. Defects will be reported by GoPlant. Proposed | John Arnold | Moderate | Likely | Medium
|  |  | 3 | 4 | 15 |  |  |  |  | 3 | 4 | 15
[7 empty] | • | Training/induction of drivers Training and induct drivers to reduce likelihood of irresponsible vehicle usage resulting in wear and tear. This will also include ensuring only those trained to operate vehicles. Proposed | John Arnold
GEL0007 - Budgetary management and control Increased cost of fuel. Risk Owner : John Arnold |  | Financial Reporting | Moderate | Possible |  | Medium | • | Monthly monitoring report Reviewing service delivery, performance/efficiency and making changes as appropriate in light of increased fuel costs. Proposed | John Arnold | Moderate | Possible | Medium
|  |  | 3 | 3 | 12 |  |  |  |  | 3 | 3 | 12
GEL0008 - Financial losses Insurance claims. Risk Owner : Killian Rosato-Dooey |  | Financial Reporting | Moderate | Likely |  | Medium | • | Reporting; compliance Specifically in relation to premises lease contract and building insurance policy. Training and health and safety compliance to ensure staff operate in such a way as to reduce the likelihood of insurance claims against GEL. Proposed | Killian Rosato-Dooey | Moderate | Likely | Medium
|  |  | 3 | 4 | 15 |  |  |  |  | 3 | 4 | 15