## GEL RISKS
Risk Management Report
Finance (Greener Ealing Ltd)
Risk (Threat to achievement of business objective) | Objective | Risk Type | Assessment of Risk (Assume NO controls in place) |  |  |  |  | Risk Control Measures |  | Control Owners | Assessment of Residual Risk (With controls in place) |  |  |  | Status | Mitigating Measures
|  |  | Impact (Severity) | Likelihood (Probability) |  | Risk Rating |  |  |  |  | Impact (Severity) |  | Likelihood (Probability) | Residual Risk Rating
HR0002 - Other legislation and/or regulation There is a risk that the overall induction programme is not completed by the end of August 2020. The elements of induction that are legally required are the following: - right to work checks; - driver licence checks; - staff one-to-ones. Risk Owner : John Arnold |  | Legal & Regulatory | Major | Unlikely |  | Medium |  | • | Right to work checks Remote right to work checks are being conducted. On-site HR system is carrying out eligibility checks. Implemented & Ongoing | John Arnold | Moderate |  | Unlikely | Low
|  |  | 4 | 2 | 12 | [5 empty] | 3 |  | 2 | 9
[8 empty] | • | Driver licence checks Contract set up with DVLA and checks have been commenced. In Progress | John Arnold
Closed
[8 empty] | • | Staff one-to-ones One-to-ones are for the purposes of gathering information not captured within the ELI data (for example, where a member of staff was fulfilling interim duties). Partially Implemented | John Arnold
FIN0001 - Business continuity Increased agency staff usage beyond normal levels. Risk Owner : Ops Managers |  | Financial Reporting | Major | Likely |  | High |  | • | Weekly monitoring reports Monthly monitoring reports of agency spend and monthly sickness absence received from Medigold Implemented & Ongoing | Ops Managers | Major |  | Likely | High |  | * Increase in agency cost is classified as high risk due to various internal and external elements affecting the business, mainly sickness and holiday absences. Management is concentrating on monthly absence reconciliation and reviewing services deployment. * The company is exploring agency market and ensuring suitable providers are on board in any event.
|  |  | 4 | 4 | 20 | [5 empty] | 4 |  | 4 | 20
Open
FIN0005 - Financial management performance Excess use of overtime (beyond normal levels) Risk Owner : Ops Managers |  | Financial Reporting | Major | Likely |  | High |  | • | Weekly spend review of services Review includes: - hours used - type of work overtime granted for Implemented & Ongoing | Ops Managers | Major |  | Likely | High |  | * Forecast for financial year 22/23 assumes 7% increase on overtime in comparison to 21/22 mainly due to HGV drivers’ issues. The weekly report to analyse agency spend is being produced. The current overspend is covered by efficiency savings but further overtime cost increase will have a significant impact on company's financial position. * Forecast for financial year 21/22 assumes 18% increase on overtime mainly due to HGV drivers’ issues. The current overspend is covered by efficiency savings but further overtime cost increase will have a significant impact on company's financial position.
|  |  | 4 | 4 | 20 | [5 empty] | 4 |  | 4 | 20 | Open
FIN0006 - Budgetary management and control Budget misalignment Risk Owner : Katarina Pohancenikova |  | Financial Reporting | Major | Likely |  | High |  | • | Budget phasing Budget for 22/23 assumed a loss of £389k Action plan to be provided to close the gap. GEL Finance team to ensure budget misalignment does not occur between GEL activities and LBE provisions. In Progress | Katarina Pohancenikova | Major |  | Likely | High |  | * Full year forecast projects a loss of £531k with GEL 22/23 pay award impact in the full year projection with additional funding of £340k from LBE not projected in the forecast yet. Additional LBE funding, in year savings and cost control measures, profitable 3rd party contracts, lease refinancing and release of end of contract damaged contributed to agreeing the pay award. The emerging pressures (pay award, HGV drivers’ shortage, NI increase, increase in costs and services, increase in fuel prices) have been highlighted to the Council. We have re-opened the discussion with our Council’s colleagues in regards to revises Services agreement and introduced new items within the Dead of Variation which should assist GEL to recover any statutory and market pressures in the future. * Full year forecast projects a profit of £49k. Lease refinancing of 37 RCV vehicles and release of end of contract damaged for these vehicles contributed to current year financial position. * Updated full year forecast projects a loss of £183k. We are awaiting confirmation on lease refinancing for RCVs which should contribute to improving the current year financial position. The emerging pressures (HGV drivers’ shortage, NI increase, increase in costs and services, increase in fuel prices) have been highlighted to the Council. We have re-opened the discussion with our Council’s colleagues in regards to the revise services agreement and within the Dead of Variation introduced new items which should assist GEL to recover any statutory and market pressures in the future. * It is now anticipated that the Cabinet will agree the GEL Business Plan in 9th February and that GELs income expectations will largely be met. However, the company business plan is showing a budgeted loss of £389k for financial year 2022/23. As we have adopted a cautious approach and including the emerging pressures and highlighted to the Council that these may need to be recovered from the Council. We will present a management action plan to the Board in April in order to contain/absorb the pressures. * Budget misalignment in financial year 21/22 has been estimated at £0.723k. GEL reports any budget gaps to the Council with breakdowns of costs and efficiency implemented. * GEL has submitted company business plan with the budgeted loss of £389k for financial year 2022/23. Management has submitted company business plan with the budgeted loss of £389k for financial year 2022/23. We have also identified some of the emerging pressures and highligthed to the Council that these may need to be recovered from the Council.
|  |  | 4 | 4 | 20 | [5 empty] | 4 |  | 4 | 20 | Open
FIN0009 - Recruitment and Retention Brexit workforce impact Risk Owner : William Gilmour |  | HR | Minor | Unlikely |  | Low |  | • | Monthly HR report GEL HR team to monitor the right to work requirements for EU citizens after Brexit; reviewing confirmation of EU settlement status. Implemented & Ongoing | William Gilmour | Minor |  | Rare | Low |  | * At present not a high risk as workforce is all compliant to latest regulations, may become an issue if legislation changes on existing EU workers employed by GEL.
|  |  | 2 | 2 | 6 | [5 empty] | 2 |  | 1 | 4 | Open
FIN0010 - Budgetary management and control Brexit impact on Fleet Risk Owner : Masoud Inayat |  | Financial Reporting | Major | Likely |  | High |  | • | Reporting and monitoring Review the market situation, impact on supply chain, ensure the business deals with potential issues in advance and have contingency plan in place Implemented & Ongoing | Michael Aherne | Major |  | Likely | High |  | * Part supplies for the large part of the fleet have now settled but delivery of sweeper machine items still an issue. At any stage current economical factors could easily rock the supply chain Go Plant Fleet Services our workshop contractor have expressed concerns their industry’s engineer rates have soared and therefore may be forced to renegotiate GEL’s contractual agreement and look at the possibility to revise the 3% capped annual increase *GEL is experiencing supply issues of larger parts for Faun Zoeller bin lifting mechanism from Germany. The supplies are taking longer to arrive, meaning vehicles are out of service for longer. We have 1 vehicle off road for 3 weeks at the moment with possibility of another damaged in the next few days. We are liaising with the contractors to find a solution to resolve the issues and minimise the impact on our service. * GEL have resolved existing supply issues with Tail Lifs parts with local supply chain, however we are experiencing extremely long lead times for parts which include semi-conductor components. We have separately been advised by Mercedes UK that no orders for new Refuse Collection Vehicle (RCV) chassis can be placed at present and that anticipated build times are beyond 12 months. * GEL are encountering parts supply issue for component supplies for our vehicle Tail-lift systems, where the manufacturer has now transferred outside of the UK. * Initial issues were primarily directly linked to Brexit disruption of goods inwards due to revised customs/trade processes and checks on incoming part supplies, which now seem to have reduced, where possible GEL has arranged with subcontractors/suppliers to increase holdings on key items.
|  |  | 4 | 4 | 20 | [5 empty] | 4 |  | 4 | 20 | Open
FLEET0001 - Financial losses Insurance claims. Risk Owner : Masoud Inayat |  | Financial Reporting | Moderate | Possible |  | Medium |  | • | Reporting; compliance Specifically in relation to training and health and safety compliance to ensure staff operate in such a way as to reduce the likelihood of insurance claims against GEL. Additional Fire and Flood risk review being included as part Zurich renewal quote Implemented & Ongoing | Michael Aherne | Moderate |  | Likely | Medium |  | * The work carried out as part of the BSI accreditation process and Business Refresh inductions will help support the way in which operatives work aligned to their specific training and Health and Safety Compliance. * We do need full sight of confirm depot lease to clarify our responsibilities and to confirm out assigned operating demise, at that point the elements outlined by the Zurich best practice in Fire and Flood document need to be reassessed.
|  |  | 3 | 3 | 12 | [5 empty] | 3 |  | 3 | 12 | Open
FLEET0002 - Loss or damage of assets Wear and tear costs to fleet. Risk Owner : Masoud Inayat |  | Safeguarding Assets | Moderate | Possible |  | Medium |  | • | Monthly monitoring report Review monthly monitoring report to identify areas/vehicles, number of vehicles. Defects will be reported by GoPlant. Implemented & Ongoing | Michael Aherne | Moderate |  | Likely | Medium |  | * With 3 year bumper to bumper warranty on all RCV’s coming to an end June 2023, this inevitably will have impact on the increased annual maintenance spend * The issue of operational failure of food waste vehicles may result in GEL being limited in the use of the vehicles such that they only can be deployed either on a short or long-term period collecting non-food material streams, which will have an impact of the overall capacity and delivery of the waste collection operation. At the moment there are 3 vehicles off the road and had to be replaced with the hired vehicles. There are on-going discussions with the related parties to find a solution to the problem with a meeting set up at the beginning of September. GEL is seeking a legal advice and the Council will need to assign the warranties for these vehicles to GEL. GEL is also seeking an independent fleet expert advice to support potential claims. * We should be shortly in receipt of engineering report regarding the above. There is a possibility that GEL will be forced to take legal advice if food waste is found to be the key factor in rear axle being overloaded and causing Chassis to bend. LBE original tendered specs clearly highlighted vehicles were being procured for Food Collection rounds. * GEL has experienced a number of rear suspension air bag failures on one of our 7 16t RCV vehicles employed primarily on food waste collection activities. Both vehicle chassis and body manufactures have been engaged in investigating and getting a resolve to the issue. The issue may result in GEL being limited in the use of the vehicles such that they are only can be deployed either on a short or long term period collecting non-food material streams, which will have an impact of the overall capacity and delivery of the waste collection operation * We have not seen any significant increase in the level of either reportable insurance or in-service damages over the last period, and the defect management and rectification process is working reasonably well with GPLFS at present. There is a concern that GPLFS are having difficulty in maintaining core levels of Managerial and Engineer resource, which may have an impact as vehicle fleet enters in second full operational year.
|  |  | 3 | 3 | 12 | [5 empty] | 3 |  | 3 | 12
[8 empty] | • | Training/induction of drivers Training and induct drivers to reduce likelihood of irresponsible vehicle usage resulting in wear and tear. This will also include ensuring only those trained to operate vehicles. 4 driving assessors are now on the contract. Implemented & Ongoing | Michael Aherne | Moderate |  | Possible | Medium
[11 empty] | 3 |  | 3 | 12
Open
[8 empty] | • | Telematics and driver behaviour Weekly report monitoring drive behaviour linked to the Telematics software Implemented & Ongoing | Michael Aherne |  | Moderate | Possible | Medium
[12 empty] | 3 | 3 | 12 |  | * Weekly monitoring report prepared and reviewed by SMT
FLEET0003 - Budgetary management and control Increased cost of fuel. Risk Owner : Masoud Inayat |  | Financial Reporting | Major | Likely |  | High |  | • | Monthly monitoring report Reviewing service delivery, performance/efficiency and making changes as appropriate in light of increased fuel costs. Carbon reduction measures being undertaken, including review of operational mileage and excessive vehicle idling Implemented & Ongoing | Michael Aherne | Major |  | Likely | High |  | * From start of contract July 2020 to now price of Diesel has nearly doubled (£0.88ppl to £1.53ppl). Fuel rates show some stability in the last few weeks but unexpected rise of 8% to 10% in any given week is to be accepted as the new norm. Alternative drop in fuel sources such as HVO still 30% higher than Diesel. Bin compacting cycles increased from 1 to 3 on DMR and Residual collection RCV’s,and this will help to reduce fuel usage and provide small but incremental value to C02 reduction. *The fuel rates show some stability in the last few weeks but we don’t expect the fuel price to stay stable for a long term. We continue to monitor the current fuel prices and usage on a weekly basis. * Fuel price from February to May 2022 have gone up by 20% and on occasional week prices soared by 40%. With Eastern crises still continuing fuel rates show some stability but have no confidence price per litre will stay stable for the long-term. * The uncertainties and deduction of energy supply caused by the ongoing emergency in Eastern Europe have a direct impact on bunkered diesel and gas oil prices with a 16% in fuel price in the last week with further increases projected. Supply of fuel does seem to be available at present, and GEL are investigating a switch to Hydrotreated Vegetable Oil (HVO) as such we have confirmed with Manufactures of all of the larger Refuse Collection Vehicles (RCV) that these are compatible to operating onto HVO fuel. * Information relayed by LBE to GEL seems to indicate that LBE Facilities Management service are no longer looking to support any GEL electric vehicle charging installations. Therefore GEL will have to resort to direct contact with electrical infrastructure suppliers and look at potential other mean of providing charging to our planned electric vehicle procurement. This will have an impact on the Carbon reduction measures outlined in our 2022 Carbon reduction plan * Increased cost of fuel is now seen as a High Risk underpinned by extremely volatile energy supply market and factors relating to both Covid 19 and Brexit, which has seen our own bulk fuel price increase 29% from contact start point in July 2020 The planned control measures relating to the measurement and management of fuel use are in place across the contract, and the first phase of Carbon reduction relating to vehicle excessive idling is delivering demonstratable savings, albeit relatively minor in value being achieved. Ongoing in-service optimisation of core operational services is being undertaken, with an expectation of reduced fuel usage in elements of the trade and garden waste collection activities. From a budget perspective our 21/22 budget price per litre is £0.930 and our latest cost per litre is £1.175 per litre giving an 26% increase in cost. Our 21/22 USLD fuel budget usage per week is 15,100 litres, and our actual average weekly USLD is 13,200 litres, which equates to a projected differential of some 1,900 litres. Should the cost of fuel rise by further 5% and the contingency be used there are a number of short and longer term options that will need to be reviewed and potentially implemented these being: • Reduction in core service provision as presently delivered • Operating at budget deficit for the provision of fuel/revised provision • Significant change in collection methodology to support fewer operational vehicles being deployed • Significant change in vehicle fuel technology, which may also require extensive depot infrastructure changes.
|  |  | 4 | 4 | 20 | [5 empty] | 4 |  | 4 | 20
Open
HR0003 - Budgetary management and control Sickness absence resulting in various and significant operational and financial continuity issues. Risk Owner : William Gilmour / Masoud Inayat |  | HR | Major | Likely |  | High |  | • | Monthly sickness monitoring Monthly sickness monitoring by operational/business area and time of year. In Progress | William Gilmour | Major |  | Likely | High | Open | * In 22/23 forecast assumes on average 1 day of sickness per employee for grades 1 to 4 (operatives, loaders, drivers). This figure includes long term as well as short term absence. The sickness absence is being monitored on a monthly basis, the results are reviewed and actioned. * Sickness absence is closely linked to some of already mentioned risks. 21/22 forecast assumes 8 days of sickness per employee for grades 1 to 4 (operatives, loaders, drivers). Any further increases in days will have an impact on company’s financial results.
|  |  | 4 | 4 | 20 | [5 empty] | 4 |  | 4 | 20
[8 empty] | • | Ensuring compliance with relevant government regulations and guidance concerning COVID-19. Ensuring compliance with relevant government regulations and guidance concerning COVID-19. Implemented & Ongoing | Michael Aherne
[11 empty] | Moderate |  | Possible | Medium |  | * We are monitoring the current situation with monkeypox disease, and we will implement government guidance where required. * The government has removed remaining domestic restrictions in England. Whilst risk remains low Guidance is available on revention. *Covid related absence is monitored periodicly for possible impact on the business .
[11 empty] | 3 |  | 3 | 12 | Open
HR0004 - Budgetary management and control Inclement weather or other environmental/health disaster. |  | Financial Reporting | Minor | Unlikely |  | Low |  | • | Contingency planning Contingency planning to mitigate the impact financially and reputationally from inclement weather affecting service delivery. Implemented & Ongoing | Michael Aherne | Minor |  | Unlikely | Low |  | * Existing climate change and long-term forecast of weather patterns does not indicate a significant additional risk to operations that is not covered off by the existing GEL BCP.
|  |  | 2 | 2 | 6 | [5 empty] | 2 |  | 2 | 6
Open
Risk Owner : Masoud Inayat
FIN0010 - Recruitment of HGV Drivers Inability of Pertemps and/or GEL to recruit and retain HGV Drivers - leading to service disruption Risk Owner : Ops Managers and SMT |  | Financial Reporting | Major | Likely |  | High |  | • | Weekly staff numbers monitor Seek to recruit GEL Drivers directly from the open market; reduce dependancy on agency for this type of employee; establish a pool of (No) HGV Drivers from: 1. External Recruitment, 2. Internal training of existing GEL staff, 3. Consider employment benefit package for HGV Drivers. In Progress |  | Major |  | Likely | High |  | * In addition to measures being taken to directly employ/training of HGV Drivers GEL has engaged with LBE to develop training opportunities for unemployed local residents utilising section 106 funding and the HGV training mechanism in place with GEL suppliers
|  |  | 4 | 4 | 12 |  | 20 |  |  |  | 4 |  | 4 | 20
Open
FIN0011 - Stakeholder funding reduction Core Income reduction Risk Owner : Katarina Pohancenikova |  | Financial Reporting | Major | Likely |  | High |  | • | Regular meetings Establishing regular communication channels with the stakeholder. The company is also looking at the potential investment opportunities outside of the main stakeholder requirements. In Progress |  | Major |  | Likely | High |  | * We have agreed to provide GEL Management Accounts on a quarterly basis to LBE and regular catch up meetings to be established. * Monthly financial review meetings with LBE Finance to be introduced from April 2022 to discuss potential requirements and risk effecting stakeholder funding. * GEL management looking at potential new investment opportunities as a new source of additional invome.
|  |  | 4 | 4 | 20 |  | 20 |  |  |  | 4 |  | 4 | 20
Open
FIN0012 - Failing to establish in new fields, areas Failure to deliver contracted services Risk Owner : SMT |  |  | Moderate | Possible |  | Medium |  | • | Company strategy reviews Plans to implement effective strategies for the future growth and stability. Proposed |  | Moderate |  | Likely | Medium |  | * Bin Wash Proposal to be agreed with LBE to carry out communal food bin cleaning, wash street bins and provide commercial bin service. * The control measure to mitigate the risk is to prepare a thorough review of potential investment opportunities with implementing the worst-case scenarios outcome.
|  |  | 3 | 3 | 12 |  | 20 |  |  |  | 3 |  | 3 | 12
Open
H&S0001 - Non-compliance with H&S Failure to comply with regulations Risk Owner : Masoud Inayat |  | H&S | Minor | Rare |  | Low |  | • | Regular monitoring and reviews GEL has its in house H&S team that is experienced in providing guidance and advice across the business. Implemented & Ongoing |  | Minor |  | Rare | Low |  | * Final LBE review and sign off of revised Fire Management protocols and processes linked to the depot Fuel station has been agreed and implemented * A great deal of work is still being undertaken is liaison with LBE to review/implement updated Fire management protocols and processes, especially in relation to the depot fuel station. This is an outstanding area of concern where we appear to be unable to reach agreement with LBE on the detail and scope of required measures to operate and refuel the bunkered fuel tanks and this may require input from an external agency in order for us to resolve this issue.
|  |  | 2 | 1 | 3 |  | 20 |  |  |  | 2 |  | 1 | 4
Open
FLEET0004 - Risk of major service failure / reputation damage Service Failure Risk Owner : SMT |  |  | Moderate | Possible |  | Medium |  | • | Contingency planning & Strategy implementation Implementing contingency plans and stategy of the management. In Progress |  | Moderate |  | Likely | Medium |  | * Setting up a Contingency plan and updates provided on a regular basis.
|  |  | 3 | 3 | 12 |  | 20 |  |  |  | 3 |  | 3 | 12 | Open
HR0004 - Data Security Data breach / fraud Risk Owner : William Gilmour |  |  | Minor | Rare |  | Low |  | • | Regular meetings Regular training, ensuring everyone understands importance of data protection compliance. In Progress |  | Minor |  | Rare | Low |  | * Less reliance on paper records and stricter access controls to offices and cupboards.
|  |  | 2 | 1 | 3 |  | 20 |  |  |  | 2 |  | 1 | 4 | Open
HR0005 - Internal Controls Number of SMT staff leaving in a short space of time Risk Owner : William Gilmour |  |  | Minor | Rare |  | Low |  | • | Planning Succession plans were required to mitigate against proposed retirements, etc. In Progress |  | Minor |  | Rare | Low |  | * Ensuring that staff are valued for the contribution they make and feel committed to work for GEL.
|  |  | 2 | 1 | 3 |  | 20 |  |  |  | 2 |  | 1 | 4 | Open
FIN0012 - Pay Award Failure to agree on pay award for 22/23 Risk Owner: MD, Head of HR, Head of Finance |  |  | Major | Likely |  | High |  | • | Meetings with GMB, LBE We have budgeted for up to 2.5% pay increase for 2022/23. The GMB Union have stated that an award of around 5% is more realistic. In Progress |  | Major |  | Likely | High |  | * The recently agreed pay award has removed the possibility of industrial action, at least for this year, and we are taking steps to implement efficiencies to offset the costs of paying for this award. The time spent seeking to identify efficiencies and seeking approval from the council to make up the shortfall, is of concern and should be avoided for 2023/24. We are in discussions with the council to adjust the contract terms to include an inflationary indexation. * GEL Management have been meeting with the GMB during the past 5 months in respect of 2022/23 pay review. During that time we discussed the cost of living crisis and the Unions have made reference repeatedly to the CPI and RPI indicators running around 8.8% at the of July 2022. Whilst we are appreciative of the very real hardships faced by our employees, we are restricted in terms of how much we can realistically afford without securing certainty from the Council that they will fund any deficit (above the 2.5% in our budget). We have considered efficiency options which may help but we are still some way off any agreement. The discussions are on-going and we will keep the Board appraised.
|  |  | 4 | 4 | 12 |  | 20 |  |  |  | 4 |  | 4 | 20
Open